Integrated Project

Call identifier: FP6-Citizens-3

Priority 7: Citizens and Governance in a knowledge based society

Part B

# Front page

Proposal full title: Mental change, Accelerating into the European future of e.governament and knowledge economy

Proposal acronym: M-CHANGE

Date of preparation: 9th December 2003

Type of instrument: Integrated Project

List of participants:

| Participant no. | Participant name | Participant short name |
| --- | --- | --- |
| 1 (coordinator) | Regione Toscana | Regione Toscana |
| 2 | Laboratory Education Research - EgoCreaNet at Florence University | LRE - EgoCreanet |
| 3 | Dipartimento di sociologia e comunicazione dell'universita' di Roma la sapienza | UOR |
| 4 | Istituto Cooperativo per l’Innovazione | ICIE |
| 5 | EBS Executive Training Centre | EBS |
| 6 | Universite Louis Pasteur | ULP |
| 7 | TERRA HUMANA Clean Technology Engineering Ltd | TERRA |
| 8 | PLATO Cork | PLATO CORK |
| 9 | The Intellectual Capital Research Institute of Ireland Ltd | ICRI |
| 10 | Public Institution Strategic Self-Management Institute | SSI |
| 11 | Høgskolen i Stavanger (Stavanger University College) | SUC |
| 12 | Rogaland Kurs –og kompetansesenter | RKK |
| 13 | Politechnika Wroclawska | PWR |
| 14 | Byweb 2 Formação e Informática Unipessoal, Lda | BYWEB |
| 15 | Instituto Superiore Tecnico | IST |
| 16 | IPA Automation Engineering | IPA |
| 17 | Universitatea Dunarea de Jos din Galati | UDJG |
| 18 | ASOCIATIA pentru DEZVOLTAREA CREATIVITATII | ADC |
| 19 | BIC Group s. r. o. | BIC GROUP |
| 20 | Amnim d.o.o., center za znanstveno vizualizacijo | CSV |
| 21 | Jozef Stefan Institute | IJS |

Co-ordinator name: Simone Sorbi

Co-ordinator organisation name: Regione Toscana

Co-ordinator e-mail: s.sorbi@regione.toscana.it

Co-ordinator fax: +39 055 4382426

# Contents page

Front page	1

Contents page	2

Proposal summary page	4

B1.	Scientific and technological objective of the project and state of the art.	5

B1.1.	Objectives	5

B1.2.	Needs – Justification of the project	8

B1.3.	SWOT Analysis of the Objectives of the M-Change proposal	10

B1.4.	M-CHANGE R&D detailed studies and sector-targeted programs	13

B1.5.	Scientometric Exploration of the Indicators for a Knowledge-Based Economy	14

B1.6.	State-of-the-art	15

B2.	Relevance to the objectives of Priority 7	17

B3.	Potential impact	19

B3.1.	Innovation-related activities	19

B3.2.	Exploitation and/or dissemination plans to ensure use of the project results	20

B3.3.	Added Value at the European Level of M-Change strategic Activities	21

B3.4.	Contribution to standards	22

B4.	Outline implementation plan	23

B4.1.	Research, technological development and innovation activities	23

B4.2.	Training activities	23

B4.3.	Management Activities	24

B5.	Description of the consortium	26

B6.	Description of project management	29

B7.	Project resources	32

B7.1.	IP Project Effort Form	33

B8.	Detailed implementation plan – first 18 months	36

B8.1.	Technical content & framework structure of dissemination	36

B8.2.	Activities of the Mental Change project	38

B8.3.	Detailed work description	41

B8.4.	M-Change Gantt chart (first 18 months)	45

B8.5.	M-Change Pert Diagram (first 18 months)	46

B8.6.	WORKPLAN - AFTER 18 /MONTH	61

B9.	B.9 Other issues	64

B9.1.	Contributions to European Governance	64

B9.2.	Contributions to European Governance	64

B9.3.	Empowerment	64

B10.	Gender issues	66

B10.1.	Gender action plan	66

B10.2.	Gender issues	66

B10.3.	Ethical issues form	68

Appendix A - Profiles of the M-Change Consortium partners	69

1 - Regione Toscana – Italy	69

2 - LRE-EGO-CreaNET – -FACULTY OF SCIENCE –University of Florence, Italy	72

3 - UOR – Dipartimento di Sociologia e Comunicazione dell’Università di Roma La Sapienza, Italy	74

4 - ICIE S.c.r.l. - Istituto Cooperativo per l’InnovazionE, Italy	76

5 – EBS - EBS Executive Training Centre, Estonia	78

6 – ULP - Céreq Alsace, Université Louis Pasteur, Strasbourg I, France	80

7 – TERRA - TERRA HUMANA Clean Technology Engineering Ltd., Hungary	82

8 - Plato Cork, Ireland	83

9 - ICRI - The Intellectual Capital Research Institute of Ireland Limited, Ireland	83

10 - SSI - Public Institution Strategic Self-Management Institute, Lithuania	84

11 – SUC - Stavanger University College (Norway)	84

12 – RKK – Rogaland Training and Education Centre, Norway	85

13 - PWR - Politechnika Wroclawska, Wroclaw Center for Technology Transfer (WCTT), Technical University of Wroclaw, Poland	87

14 – BYWEB - Byweb 2 Formação e Informática Unipessoal Lda, Portugal	89

15 - IST Instituto Superiore Tecnico, Potugal	90

16 - IPA Automation Engineering, ROMANIA	92

17 - UDJC - Universitatea Dunarea de Jos din Galati, ROMANIA	93

18 – ADC – ASOCIATIA pentru DEZVOLTAREA CREATIVITATII, ROMANIA	95

19. BIC Group s. r. o., SLOVAKIA	96

20 - CSV - Amnim d.o.o. / Center za Znanstveno Vizualizacijo, SLOVENIA	97

21. IJS - Institut "Jožef Stefan", Ljubljana, SLOVENIA	98

# Proposal summary page

Proposal full title: M-change, Accelerating into the European future of e.governament and knowledge economy

Proposal acronym: M-Change

Strategic objectives addressed

The main strategic objective is to understand the role of knowledge dynamics in processes of learning and competence-building at the level of regions, sectors, social groups, institutions and organisations, and, further, to relate this to issues of competitiveness, regional development and economic and social cohesion. This multidisciplinary research is addressed to  large, comprehensive and representative territorial and organisational configurations affecting the potential for innovation and economic development (National and Regional Interest Groups). It will examine how different arenas for learning and competence building are inter-connected in specific patterns for shaping different national and regional systems, as well as the implications for the EU open process of co-ordination.

Proposal abstract, copied from Part A

Contemporary European society is experiencing a socio-economic crisis, mainly due to the deep changes emanating from the transition to a post-industrial society. Examples include the high rates of structural unemployment in most MS and AS, especially in the sector of young graduates—and other vital policy issues that demand regional adjustment strategies in the context of European integration. The mission of the M-Change project is to investigate the development towards a new paradigm for co-operative and comparative education, social capital, intellectual capital and knowledge management skills to integrate multidisciplinary knowledge at regional levels in order to contribute to supporting quality based competitive innovation that favours European Knowledge dynamics in economic and societal development. The project will investigate the development of a new integration strategy by means of Public/Private networking management that will be co-organised in various regions of Europe based on a grouping approach that supports participative democracy by citizens. Hence, the impact of the project will envisage stimulating the creation of innovation driven clusters and business networks in both MS and AS regions of Europe. In this way European citizens will be offered an unprecedented opportunity to access, share and diffuse information and best practice by means of an interactive e.Editorial system both within European regions and across regional and national borders.

The results of the project will foster better citizen-centred governance initiatives by improving the capacity to develop a trans-national framework based on an open information system. This system is designed to enhance understanding of knowledge dynamics to facilitate the dissemination of this understanding through an infrastructure of life long learning, competence-building and shared best-practice.

The M-Change proposal is based on an aggregation of Regional (RIG) and/or National (NIG) Interest Groups - horizontal networks, but also of Thematic Interest Groups (TIG) in vertical networks. These are networked online Groupings or Clusters that will be capable of aggregating interconnected companies and governmental institutions (SMEs, Trade associations, Universities, Regional or National agencies). The Groupings or Clusters will be developed and managed by the corresponding project partner and will become non-official, yet effective and inclusive, partners within the project.

# Scientific and technological objective of the project and state of the art.

## Objectives

The main strategic objective of the M-Change project is to understand the role of knowledge dynamics in processes of learning and competence-building at the level of regions, sectors, social groups, institutions and organisations, and to relate this to issues of competitiveness, regional development and economic and social cohesion. This multidisciplinary research will address a large, comprehensive and representative territorial and organisational configuration affecting the potential for innovation and economic development (National and Regional Interest Groups). It will examine how different arenas for learning and competence building are inter-connected in specific patterns for shaping different national systems, as well as the implications for the EU open process of co-ordination.

Main sub-objectives and directions of the project Mental-Change:

1.1.1 Investigating the state-of-the-art and design the promotion and organisation of the partnership between the State, the University, the private productive sector (especially SMEs) and civil society, with the explicit purpose of providing an effective contribution to understanding the role of knowledge dynamics in processes of learning and competence-building.

1.1.2 In the developmental context of the European Knowledge Society, based on a joint partnership, the project will contribute finding the activities oriented to recognise, to analyse, to evaluate Regional best practices that are useful for a future-oriented perspective, the trends and the real potentiality of the Knowledge Economy development, with the aim of contributing to the building of the European Knowledge Society.

1.1.3 Assessing the capacity to develop a bottom-up information system that will be accessible to citizens, managers and policy makers with respect to the developmental key issues for a society’s sustainable and equitable development of the Knowledge Economy in Europe.

1.1.4 Building up a trans-national framework able to:

- achieve an information open system;

- undertake initiatives for lifelong digital training;

- disseminate best practices and new skills for improving knowledge dynamics at the level of regions, sectors, social groups, institutions and organisations;

- value the existing achievements towards the issues like competitiveness and regional development in the context of economic and social cohesion.

- feature the key access for promoting European Economic and social growth in the  contemporary globalisation context of the Knowledge driven Economy.

1.1.5 Directing the integration of the multi-disciplinary knowledge at Regional levels, ranging from socio-economic concepts, including critical and creative thinking to Science & Technology innovation, throughout using advanced ICT interactive methods of planning the results of the knowledge dynamics strategies.

1.1.6 Stimulating the EU open process of co-ordination as a vital resource and capacity for acquiring, using and disseminating innovative multi-disciplinary knowledge; these are critical factors by which Regional governments can help develop the competitiveness of the European Knowledge Economy.

1.1.7 Creating, based on the M-Change, of an enhanced conceptual and organisational model for a citizen centred e-governmental European strategy, founded on supporting participatory democracy to strengthen the European Research Area, that will offer an unprecedented opportunity for European Citizens to access, to share and to diffuse information by means of an interactive e.Editorial system, both within European Regions and, particularly, across Regional and National borders.

In syntheses, the M-Change project will contribute to supporting European Knowledge dynamics for economic and societal development, considering the changes of mentality required, as well as emergent factors generated beyond a new strategy of integration between Public/Private networking management, which will be co-organised in various regions of Europe by a grouping approach supporting participative citizen-centric democracy. .

### Tangible outcomes

Structural and institutional outcomes: RIGs and/or NIGs achieved in every partner country; TIGs on specific topics, covering the main fields acting in the multidisciplinary research M-Change achieved at the European level. When necessary and appropriate, specific institutional structures will be created to support the achievement of project tasks and to assure the project continuation after the ending of the EU funding.

### Specific research outcomes

- Identifying and assessing the existing information at Regional, National and European level; decision on organisation of pools in the project’s regions,  interpretation of findings;

- Assessment of the state-of-the-art: achievement and / or revision of existing questionnaires/research instruments to assess the state-of-the-art of the partnership between the State, the University, the private productive sector (especially SMEs) and civil society;

- Achievement of a comprehensive synthesis on the state-of-the-art of the partnership between the State, the University, the private productive sector (especially SMEs) and civil society. It is envisaged that this will provide an effective contribution to understanding the role of knowledge dynamics in processes of learning and competence-building; the main topics of these studies are:

- information policy in knowledge dynamics, law and ethics Information management, methods and practice, lessons of the past and visions of the future;

- Knowledge dynamics information and organisational design, options and choices for the development of a knowledge-based society in a multi-dimensional economic context;

- Forecasting of the impact of knowledge dynamics on economic and social development; topics for specific targeted research projects and co-ordination actions;

- team e.Work in human-media interfaces, criteria and methodology, and systems development, and intellectual property issues in a distribution and use of knowledge dynamics information;

- Competitive intelligence in knowledge management network economy, decision making and decision support systems in grouping aggregation, social trends in the knowledge-based society and their implications for quality of life;

- Innovation strategies and complexity management, Knowledge management concepts, methods and practice; Knowledge dynamics and organisational design for SMEs / University, aggregation oriented to favour capital investment attraction;

- Economy of science; marketing and market infrastructure of science innovation; production potential efficiency of regional economy in a developmental knowledge driven economy;

- Investigation of social structure dynamics, social-psychological and ethno/international processes into a sociological provision of governmental system transformation;

- Democratization of public life, Regional and National governmental renewal in correlation of international relations in Europe, obtained by means of public opinion poll, interviewing, testing, monitoring, probability methods and social processes prognostication;

- Sociology of science and technology, sociology of innovation, intellectual property and the commercialisation of research and innovation, technology foresight and social science - the dynamics of knowledge flow, acquisition and use;

- Organizational and intellectual capital issues in relation to alignment of the networking extended enterprises around financial dynamics in a knowledge based changing patterns and assets in Europe.

- Organisation of specific actions (e-debates, work-shops, conferences etc.) and achieving of synthesis to recognize, to analyse, to evaluate Regional best practices useful for a future-oriented perspective, the trends and the real potentiality of the Knowledge Economy development, with the aim to favour the building of the European Knowledge Society.

- Formulation of an enhanced conceptual and organizational model for a citizen centred e-governmental European strategy, founded on supporting participatory democracy to strengthening the European Research Area, that will offer an unprecedented opportunity for European Citizen to access and to share and diffuse information by means of an interactive e. Editorial system, both within European Regions and across Regional and National borders.

### Dissemination specific outcomes

A unitary and coherent dissemination strategy and action plan was structured within the Education Research Wireless Laboratory (ERWL) concept (see also B.1.6). The main instrument of this laboratory will be the Knowledge Economy Portal (KEP), able to systematise and classify specialised Knowledge Economy issues that can have a  large impact both at a Regional Level and across Europe.

The organisation - functions of the ERWL (as detailed described in 1.6) are subdivided in four basic elements of the M-Change INDUCATOR-based dissemination strategy through using ICT tools:

A) Inducator (incubator + educator) networked function co-organized by partners for setting together cognitive Knowledge Economy priority problems;

B) e.Editor networked function for setting Knowledge Management net-learning materials & tools;

C) Front Office function co-organised by partners for setting advisors and stakeholders Meetings with SME’ s entrepreneurs and developing innovative networking business models and collaborative marketing and commercial plans.

D) Knowledge Economy Portal, as a function co-organized by partners for setting ICT interactive implementation & dissemination processes.

Usual dissemination activities (press releases, radio-TV-news papers interventions, links on web-pages etc.) will be also envisaged and will be object of a detailed plan, which will be set up in the Project Handbook. For more details on dissemination tangible outcomes, see also par. 2 above and 1.6.

### Managerial specific outcomes

Achievement of the Project Handbook as the main managerial tool, enabling a good scheduling, tasks sharing, activities assessment, heading of the administrative and financial issues.

Project’s main features:

- Holistic approach: The Founding Fathers of an United Europe understand that the goal of developing a European collaborative Economy cannot be reached by a simple sum of National policies. This is because the historical reality of Europe has more richness than the simple sum of its Nations, and it is based on an extensive Regional characterization of people, languages, cultures and economies. Hence, for improving the future, European integration remains indispensable to consider the knowledge dynamics evolution of Citizens and workers living in the European Regions as a potential source of better establishes territorial socio-economic synergies, that can provide the best contribution to joining, and leading, the future world wide Knowledge Economy.

- Joint Partnership Activities: The mission of the project will be carried out by means of Joint Partnership Activities well oriented to study and to disseminate the needs in the changes of mentality that are included in contemporary developmental challenges (both, in the new entrepreneurship’s performances and in occupational life and also in the development of a permanent education systems - Net-Learning, in the context of European enlargement to the complete geographical and historical extension).

- Multi-targeting: The project will examine different arenas for learning and competence building inter-connected in specific patterns for shaping Regional national systems, as well as the implications for building of the European Knowledge Society, oriented to change forwarding a continuous innovation, and at the same time in which the Knowledge Worker can obtain greater employment possibilities and new opportunities to increase the quality of the life of European citizens.

- Multidisciplinary: The aggregation of Regional (RIG) and/or National (NIG) Interest Groups in horizontal networks, but also of Thematic Interest Groups (TIG) in vertical thematic networks will direct to several basically different topics and fields of action, consequently requesting specific expertise. Multidisciplinary research teams will be involved from each member of the already heterogeneous RIG / NIG partnership.

- Reliability: the M-Change projects is meant to value the existing achievements in the partnership regions, to add value to these by the creation of a reliable model, which will enable an enhanced further development of the Knowledge Economy.

The project M-Change will demonstrate the importance of promoting public-private Regional partnerships; implementing the understanding and the clever utilizations of bottom-up strategies in e-government and in e-governance initiatives involving all relevant stakeholders; ensuring effective governmental Regional support; capturing economic opportunities and enabling businesses; responding to the challenges of competition of SMEs in the globalization context; and focusing on European Citizen’ identity.

The Regional Interest Grouping European coalition (E.RIGs) will be represented by a comprehensive range of companies and research organisations of primary and secondary industrial and commercial sectors, including also Universities and Local Governmental Institutions, oriented to collect and also to design and implement best practices of cooperation of territorial entrepreneurial development.

Citizen’s participation to e.Governance stand up to benefit a great deal from an E.RIGs opportunities offered by the project M-Change through a collaborative and feasible use of ICT, obtained through giving data produced by partners to an open access to a great and relevant knowledge dissemination across trans-national distances. In this way it can be possible to grow up the best system of knowledge dynamic co-organization based on a down-top method of knowledge sharing of the best practices in developing at Regional level convergent strategies oriented to the growth of the European economy future development.

Given the genuine willingness of the M-Change project partnership to do this knowledge building system oriented to bridge regional and European governments into a validation agreement with National responsibilities, the project certainly can favour into a broader interdependent European ICT transparent environment open to a large impact and a good approach to understand knowledge dynamics permitting to show to European Citizen and relevant stakeholders a good documentation on line that will aim to accelerate an equitable and inclusive Knowledge Economy growth in Europe.

## Needs – Justification of the project

The European Regional networking of various Governmental local Institutions and Centres of Research and SMEs has more or less defined features and effectively acts in very different degrees across Europe, in MS and AS. Several obvious deficiencies may be nominated:

- lack of coherence, joint efforts and/or of integrate planning systems;

- irrational or inadequate use of resources;

- overlapping of different programs;

- lack of long-term programs or of the awareness of the responsible institutions to involve in these;

- non-valuing of existing achievements, lack of good practice dissemination;

- ignoring or misunderstanding of various social partners’ or stakeholders’ role in the Region, in the process of the implementation of the social and economic cohesion;

- resistance in e.Society development due to the old mentalities, adverse feedback of the systems, unawareness or improper ways of implementing the IST policies, institutions and tools;

- random development and implementation of e-Government policies, due to local and regional factors, unknown, not well known or neglected;

- non-coherent Human Resources Development policies etc.

All of these aspects have essential negative impacts on the general level of education and training, unemployment level, citizens’ participation at governance etc. It is not well used the huge regional potential in the synergic approach of the complex socio-economic problems, involving education and M-Change as sine qua non conditions of an effective e-Government. Knowledge Economy and its main component, Knowledge Management, are not taking benefit from this existing potential.

Consequently, two important general needs emerge:

- the need of an effective Regional Clustering e-governance strategy for implementing the European policy of Knowledge Society.

- the need for a real mental change, a change in mind-set, or an M-Change, accelerating into the European future of e.Government and Knowledge Economy.

Related to the existing situation and the needs, there are definitely differences between the MS, but there are (no doubt) huge differences between MS and AS, and even between AS. Additionally, for AS there is a double challenge of M-Change: the one due to the transition from the old communist mentality to the open market based economy, to the freedom of expression and the need of continuing education. After this comes the second one, common with the partners from the MS, the one needed to the post-industrial transition. Not simply a smooth, moderate ratio climbing is required from the AS citizens here, but a quantum accelerated leap. Thus, the targets and the tools should be definitely different, as well; (To enable a comparison, the percentage of the graduates is at least 13-15% in the most of MS, but in Portugal is 9% and in AS is lower – e.g. in Romania and Bulgaria it is lower than 5%).

The new age, which the European Programs address, is the post-industrial one. It is obvious that we can not talk about a post-industrial stage in AS, or at least not in all of them. In this order, the M-Change approach must, once again, be adapted and particularised to fit local contextualities.

Additionally, the structure of the society and the education level of the citizens should be the first input when defining a M-Change strategy. Since in countries such as Romania or Bulgaria almost half of the population is living and working in the country side (in Poland a quarter), that means of that more than 35 mil. persons with a very particular way of living, mentality, culture and level of education must be particularly addressed.

In conclusion, to be effective in all the AS countries, to allow a real European partnership and to fill in the gaps, the M-Change must be a complex mass phenomenon, firstly involving huge cultural and educational changes. To achieve this, enormous infrastructural efforts must be also involved.

Summarising, the main issues/challenges for the RIGs from AS are:

- - infrastructure

- the access to information;

- - development of a continuing education and lifelong leaning culture;

- - the necessity to persuade the people to invest in information and culture (their time and other resources);

- - education in how to use the information as the most powerful democratic tool;

- - creating an entrepreneurial culture.

These, in may ways, signal the need to educate people as citizens in participative democracy in a European, free-market, social economic context:this is a real challenge and one that the M-Change Project is designed to address

Towards the above issues, the M-Change offers today a unique opportunity for developing a deeper understanding of the strategic role of knowledge dynamics in overcoming the crisis of representative democracy in relation to the effective needs of obtaining a prompt development of the European Knowledge Economy starting with the examination of specific patterns of change rooted at territorial level.

As a matter of fact, the Regional Interest Groupings empower democratic society playing its role more effectively and therefore it will be facilitating the performance of governments’ main function helping a more direct participation of the people who elected the policy makers and Governmental Institutions.

The envisaged Change of Mentality oriented to favour the way where Information Society affects knowledge dynamics patterns and practices linking the development of Knowledge Economy at both the European and Local levels in relation to change the inadequate policies that maintain invariable the old economic concepts. Nowadays these are useful only to maintain the often obsolete criteria of efficiency of the industrial society based on the classical division of social labour, because the maintenance of the development criteria will simply increase the overall development gap with the global competition for the development of the Knowledge Economy.

Another responsibility of all contemporary governments is to respond to globalisation challenges and establish conditions under which their citizens can benefit from globally available information and knowledge to generate developmental dynamics of the Knowledge Society in their own local regions.

An European Partnership of RIGs (E.RIGs) can develop an ICT system for sharing the best practices at the European level in a way to improve an efficient integrity of the overall process of developing the Knowledge Society and at the same time to allow for overcoming the risks to damage the development dynamics of knowledge economy, by the conformist resistances against the deep needs of the M-Change in the knowledge dynamics evolution.

## SWOT Analysis of the Objectives of the M-Change proposal

The SWOT analysis is useful because it includes a clear description of how the project will generate significant new knowledge, beyond the state-of-the-art and a sufficient account of the methodologies to be pursued, so that a good assessment can be made of its innovativeness and the quality of the research to be undertaken. The SWOT analysis will be also periodically performed to evaluate the progress of the M-Change project evolution during its developmental activities.

### STRENGTS – Citizen understands BUSINESS MANAGEMENT SKILLS INNOVATION in the development of a European Knowledge Economy

M-Change is a contribution to the European Knowledge Economy sustaining and stimulating the creation of the Innovation Driven Knowledge Communities at the level of regions, sectors, social groups, institutions and organisations, aiming throughout these groupings at the Clusters of Science and Business. These virtual or shaped institutions give an effective contribution to the Citizen’s understanding of Knowledge dynamics and economic development in Europe through a sharing methodology of collaborative promotion of best practices that will also oriented to develop an innovative knowledge management for strengthening ERA among University and SMEs and Governmental Regional Institutions.

The M-Change program is oriented to developing Research Action Areas concerning the advancement of the managing human  resources (HRM) component by the aggregation of multidisciplinary teams in genuinely comparative research across Europe in the context of the European Extension.

The key challenges in advancing the management of human resources will develop managerial skills for the Integration (Enlargement of Europe - Accession), that will be able to favour the citizen’s understanding of knowledge dynamics changes that need for improving European Knowledge Economy in relation to issues concerning competitiveness, regional development and economic and social cohesion.

Certainly can be considered as a strength of the M-Change project, the preliminary fact that the proposal was able to reunite in a Consortium a critical mass of resources in Europe, to integrate research efforts and existing knowledge, by pulling them together and to make this research and development application into a more coherent conceptual schema.

Hence the M-Change can move and will be implemented towards rigorous comparative research & development in terms of methodology, data, and coverage of significant and truly representative numbers of MS and AS, but also is open not exclusively at EU level for responding to demands for support the EU open process of co-ordinating the European Knowledge Society.

The M-Change consortium will also operate for improving economic performance of learning and competence-building in Business Networking Management Skills in a way that will be necessary for managing the future Knowledge Economy. Fitting this goal is strongly depending by a method to share innovative knowledge management based on a deep knowledge of powerful indicators of Regional Development that will assess the significant socio-economic policy fields particularly concerning the advances agreements between SMEs and the Research & Development of the University and other public or private centres of research.

One of the powerful indicators moving towards the future Knowledge Economy, a fundamental endeavour of the economic growth, will be the knowledge work-creation in each regional context of Europe; therefore the M-Change project will contribute to develop models of methodologies and actions for a continuing education for citizen understanding of the European Knowledge Economy growth aiming at the same time to overcome the difficulties of job-insecurity of business managers.

To provide a fundamental contribution to this goal it will be necessary a M-Change that permits an inversion of the traditional way to see the job-creation as a factor depending from the labour-market needs. Simplifying this concept, it is easy to recognize that without improving work-force productive employment in knowledge management it will be not new possibility of the expansion of the market in the networking socio-economic environment of the European post-industrial society.

Hence one of the main efforts of the M-Change is to analyse the possibilities for an appropriated commitment of the intellectual work force management in a new path of development of Knowledge economy, aiming to change the individual and organisational informal learning cultures and improving a digital interactive and pro-active access to a bottom-up e.Governmental methodology for developing a very advanced Knowledge-based Economy.

This means essentially developing a knowledge management strategy for developing Innovation-Driven Knowledge Communities aiming to meet local with global challenges and encouraging the debate in Science & Society developmental priorities, oriented to the intellectual job-creation. They will also develop a large European comparison about the most important socio-economic developmental indicators and to diffuse and disseminate such results for an open debate to the general public and also to policy makers and business managers in Europe. Another contribution can be added to significant socio-economic policy fields particularly, but not exclusively, at the EU level, including the development, analysis and assessment of relevant Regional needs.

### WEAKNESSES - criteria for contributing to the enhancement of co-operative knowledge management innovation developing the project M-Change

It is necessary to add some considerations about the need overcome the weaknesses of the M-Change project because they mainly are a consequence of the cultural resistances and the difficulties of a practical understanding of developmental change.

It is easy to understand that in the contemporary years all over the world we are living near to a socio-economic crisis, due to the deep changes requested by the transformation of the old industrial society. The high rates of unemployment in most of EU member and associated countries especially in the sector of graduated youth, remains a vital policy problem that undoubtedly is in need of a Regional adjustment strategies in the context of European Integration.

As a matter of fact the accelerating process of EU integration in accompanying Regional differences in employment and in different sectors of development, has exposed all European Citizen to a powerful change of mentality in terms of the criteria and methods to develop and utilise Science and Technology (S&T), Open and Distance Learning and Permanent Education (Net-E) and research and development (R&D).

Therefore, without acting consciously in terms of the needs in business management in relation to S&T innovation, Net-E and R&D, that need to be well oriented to improve the Knowledge Economy, the European competitiveness will be declined as a result of the structural changes in the world global economical trends.

At the present time in the initial situation of the development of Knowledge Economy, the working roles in society is changing again, and people need to understand the big shift that require to be assured to transform the traditional forms of the social division of labour, in a large spectrum new job activities related to Knowledge Management innovation, where it will be required an higher skill levels in networking business innovation and in problem solving or problem saving capacities of all e.Workers.

Human capital is the foundation of Intellectual Capital, therefore, the big issue of the labour force change represents the more important weaknesses of the Knowledge Dynamics. Thus, its understanding must be focused into the need of favouring a strategy for overcoming both digital divide and skill shortage problems, in a way that will be possible to drive Regional competitiveness in the context of advancing of European Knowledge Economy.

So that we need to be able to emphasise qualitative Regional best practices in the context of development of ICT applications, looking to exchange information about the developmental patterns of e.Working employment.

Underlining the weaknesses of the M-Change research activities, it will be necessary to consider that because of the conservative attitudes and feelings of some older workers, especially in relation to the changes related to e.Work employment. this requires that we open also  collaborative studies of the social alienation and related mental disorders threaten the possible troubles of future e.Work development in the context of an advanced Knowledge Economy globalisation.

Democracy is by definition inclusive, so that the current level of understanding of knowledge dynamics of changes between the industrial society and the post industrial society, generate a Citizen exclusion that is a fundamental constrain of the necessary spreading of a more direct e.Democracy in Europe, with a consequence that it will become difficult to develop a large consent and a deep knowledge of citizen for improving new e.Work creation, and innovative knowledge management as well it will be useful in a new globalisation context determining the new international division of the labour.

In conclusion, the M-Change project, taking in account the effective weaknesses fundamentally consequent to the aforementioned difficulties and also from the complexity of the proposal, will contribute to a gradual but remarkable transformation in the culture of Universities’ collaboration with Industry-especially SMEs, in a way that will be possible to give a make a direct contribution to accelerate the Knowledge Economy development, and providing a crucial insights into a matter of fundamental concern to a range of interdisciplinary oriented research in Knowledge management innovation, including economics, economic history, political economy, the history of technology, and the history and epistemology of science.

### OPPORTUNITIES AND THREATS

One of the fundamental opportunities of the economic growth and social change for improving the knowledge as the basis of European Economy will be rethinking science policy into a new international system of more open cultural democracy.

Therefore the M-Change project will concerns also with ICT models for managing science policy more effectively from bottom-up decision making of the citizen, aiming to innovate performance in the ability of science and technology to address the priority of socio-economic issues.

These issues (related to the strategy of developing Knowledge Economy in Science & Innovation) are too important to leave them only in the decision making of academic scientists or politicians - policy makers.

The future European Knowledge Economy lies on an effective growing of the ERA that will be an expression of large networks including Governmental regional bodies and public and private research institution that will get some complementary roles in the development of the highest competitiveness of the European Knowledge Society.

Thus, the M-Change Integrated Project will give the opportunity to develop a good contribute building up ICT models and dissemination strategies on S&T implementation planning for ameliorate science & technology social-development, favouring a bottom-up cultural-democratic approach of decision making, founded on the Citizen’s understanding of science & technology developmental problematic, that will be an essential democratic attribute of the future knowledge driven Society.

In fact ICT applied to permanent education of the Citizen can give an extraordinary opportunity for growing up a modelling, simulation and forecasts in the S&T perspectives and therefore can allow a rapid social-advancement of the S&T, based on the sharing knowledge and on advancing a collaborative efforts in science policy performance, developed in agreement through networks aggregation among University’s, Regional Governmental Institutions and Industry (including SMEs).

Certainly, towards the existing state-of-the-art, the M-Change proposal may also feature some threats due to the old academic tradition of the Universities and also to the traditional Industry’s behaviour, in particular of the SMEs, that are not accustomed to share business information. Therefore the critical threats include essentially the difficulties related to develop a knowledge management strategy of networking enterprises. Hence the main expected result of the M-Change will be to find operative solutions that transform ICT in a powerful engine for the Business Management of the Networked Economy.

In particular it will be important knowing very well those threats generated by a conservative mentality, for overcoming them and considering the importance of the benchmarking of best practices organised in ICT collaboration by the M-Change project, in a way to help the growing up of the productivity by means of a well structured information on line oriented to the Knowledge Management innovation. On this aspect about the level of the utilisation of ICT for improving the Knowledge management innovation in various world wide countries is useful to get a look to the Status of the Art of Global Competitiveness Programme, that reports a recent classification of world countries about the level of developing networking business and managerial skills in relation to the need to accelerate the Knowledge Economy growth [10].

## M-CHANGE R&D detailed studies and sector-targeted programs

In view of the growing importance of knowledge dynamics in organisations in the knowledge based economic and international order, the program M-Change will focus strongly on organisational knowledge dynamics and management.

Contributes will be developed by the M-Change project to significant socio-economic policy fields particularly in Sociology and Economy of Knowledge Dynamics, not exclusively focused at the EU level, but including the world wide development of those fields of research, developing an analysis and assessment of relevant strategies of knowledge dynamics all over the world and aiming to grow up advanced strategies of net-learning and competence-building at the level of regions, sectors, social groups, institutions and organisations, and to relate this to issues of competitiveness, regional development and economic and social cohesion.

In this way that will become possible to respond to demands of the European Citizen and for support governmental initiatives able to involve, as appropriate, users and stakeholders and contribute to the analysis and assessment of relevant governmental innovation policies especially in relation to the creation of new e.Work application, and an to the improvement of networking -economy management; of the European SMEs.

As a consequence the scientific program in sociology and economy of knowledge dynamics will be focused on the problems and the related fields of Information Management and Knowledge Management in networked organisations.

In detail, the principal topics of the R&D will be the following:

- information policy in knowledge dynamics, law and ethics Information management, methods and practice, lessons of the past and visions of the future;

- knowledge dynamics information and organisational design, options and choices for the development of a knowledge-based society in a multi-dimensional economic context;

- forecasting of the impact of knowledge dynamics on economic and social development; topics for specific targeted research projects and co-ordination actions;

- team e.Work in human-media interfaces criteria and methodology, and systems development, and intellectual property issues in a distribution and use of knowledge dynamics information;

- competitive intelligence in knowledge management network economy, decision making and decision support systems in grouping aggregation, social trends in the knowledge-based society and their implications for quality of life;

- innovation strategies and complexity management, knowledge management concepts, methods and practice; Knowledge dynamics and organisational design for SMEs / University, aggregation oriented to favour capital investment attraction;

- economy of science; marketing and market infrastructure of science innovation; production potential efficiency of regional economy in a developmental knowledge driven economy;

- investigation of social structure dynamics, social-psychological and ethno/international processes into a sociological provision of governmental system transformation;

- democratisation of public life, Regional and National governmental renewal in correlation of international relations in Europe, obtained by means of public opinion poll, interviewing, testing, monitoring, probability methods and social processes prognostication;

- sociology of science and technology, sociology of innovation, intellectual property and the commercialisation of research and innovation, technology foresight and social science - the dynamics of knowledge flow, acquisition and use;

- organisational and intellectual capital issues in relation to alignment of the networking extended enterprises around financial dynamics in a knowledge based changing patterns and assets in Europe.

## Scientometric Exploration of the Indicators for a Knowledge-Based Economy

The progress of the project work will be measured against its goals in later reviews and assessments, aiming the success of developing a citizen understanding of the role of European Best Practices in generating business competition by networking model of Regional Aggregations, and by measuring the management skills advancement for integrating Intangible assets of Research activities with Tangible productive development of European Development in Knowledge Economy. It is intended to draw, and build on, previous research from the MERITUM, PRISM and other projects.

The knowledge-based approach of an economy generates dynamics different from that of the traditional policy in economy. This is due to the process of Knowledge Accumulation and Dissemination, in the changing the structure and function of the University as Regional Pole of Knowledge and the role of the social structure in constructing the processes of Knowledge Society.

The change in emphasis of the future Knowledge Economy that places the University in a new alignment with the productive sector generates new integrated systems where the knowledge dynamics cannot be considered as given or immediately available for observation by means of quantitative indicators. For this specification, the quantitative analysis of the Mental Change project outcomes remains thoroughly dependent on the qualitative hypotheses, based on a verification of the co-evolution paths of a spiral model of the proposed innovation.

This requires capturing multiple reciprocal linkages at different stages of the capitalization and marketing of knowledge, creating systematically effective and dynamic interdependencies, into a matrix that in horizontal line connects the parameters of University, Governmental Institutions and Industry, and in the vertical line connects the factors that are in relation to Science, ICT, Innovation. The analysis of this matrix oriented to the goals of driving the performance of the integration between market and research will give the indicators for the dynamics of socio-economic changes (see Fig.1 at page 37).

In synthesis, a matrix-model of co-organization among University-Industry-Government for measuring the science & economy integration can be taken in account as an indicator of new modes of production in the Knowledge Economy. This model can be related to some special field on local dynamics of technological change/innovation in the context of the European strategy of Knowledge Society.

This matrix-model approach that will give the measures about the new production of integrated knowledge can be considered a good fuzzy indicator for an evaluation of the dynamics of science and research in contemporary societies. Additionally, it has the advantage of generating an opening of a pre-competitive incubator strategy that permits to identify new networking business Regional plans in the global world wide competition.

Specific IST indicators, according to e.Europe 2005 will be also considered when assessing and investigating the Regional levels of development on the Knowledge Economy topic related to the Mental Change project.

## State-of-the-art

### General considerations

The M-CHANGE project is promoted by the TUSCANY REGION [1], by the LRE-EGO-CreaNET of the University of Florence [2] in collaboration with ICIE [3] member of LegaCoop (www.legacoop.it) and other partners and stakeholders, to meet the challenge to develop a Regional clustering approach to the Knowledge Economy Networking, to exchange ideas and to share best practices in Europe; a crucial objective of the project will be also to found the scientific bases for developing of a comprehensive e.Educational infrastructure based on knowledge management innovation.

The S&T objectives of the M-Change are the consequence of the following general considerations (see also the state-of-the-art on the M-CHANGE website [4]).

The Networking organisation among Regional groupings, composed by Governmental local Institutions, Universities, Centres of Research and SMEs, offers today a unique opportunity for developing a deep understanding of the strategic role of knowledge dynamics to overcome the crisis of representative democracy in relation to the effective needs of obtaining a prompt development of the European Knowledge Economy starting of the examination of specific patterns of change rooted at territorial level. In spite of these very important inter-Regional strategies, Governmental Public Administrations of the Europe’s Regions, in many cases and in large extent delimit conventional policy of innovation and political responsibility to the proper local territory. They are utilizing ICT especially for increasing transparency in State services and not too much oriented forward getting better an efficient networking economy among University, Industry and SMEs for strengthening the European Research Area, which is the base of the new development of the European Knowledge Economy. As a matter of fact, the Regional public administration very often shows too much conservatism in their process of policy innovation development, by a rigid adherence to the classic definition, according to that the Regions’ Governmental actions belong only to a departmental localised territory.

This related to Knowledge Management obsolete mentality of the Governmental Regional authorities, dealing with a well defined territory district, do not fit so much the exigency of the Future Competitive Knowledge based Society of an enlarged Europe, based on an effective development of an European co-operation activities of Universities and SMEs. Therefore the project M-Change will be co-organise in each partnership’s Region, certainly with strong co-operation of Regional or National Governmental authorities, an efficient collaboration among sectors, social groups, University Institutions and Enterprise organisations, for accelerating a dynamic knowledge development including Citizen in a more direct participation to the definition of the need and solution of the more advanced European Knowledge Economy. Thus, the citizen will become not a part of the problem, but a part of the solution. Further, the M-Change consortiuum includes a diversity of regions, from MS to AS, from highly technologically developed to under-developed, from infrasturcture rich to infrastructrue poor, which should lead to useful comparitive indicators.

Therefore the above goal is the major challenge that the proposal M-Change project that will strengthening the European Research Area participating to the call - CITIZEN 3 and improving processes of learning and competence-building. The M-Change project will develop an informal education on line strategy, by means of sharing ICT Tools and platforms, the fruits of Knowledge Economy, built up by the RIGs grouping and disseminated by the trans-European partnership.

### Relation with previous initiatives, programs and projects

Europe’s innovation related policies are oriented to reinforce the ERA and therefore Regional Governmental activities across Europe are particularly exposed to such transformational economical and productive pressures, focused on the creation and utilisation of scientific knowledge to develop the Knowledge Driven Economy, especially for helping the growing competitiveness of the SMEs in the Global Market, and also for giving new opportunities to the intellectual employment, and enhancing a sustainable development of EUROPE looking to give a contribute to enrich geographical and historical extension of the future borders European Union.

The project M-Change is well conscious of the European initiatives oriented to growing the European Knowledge Economy, a concept established in LISBON in 2000, and therefore did take previous in contacts for opening a collaboration with all the important efforts and challenges produced by the Innovating Regions Network [5] in Innovation Strategies (RIS) and transfer strategies infrastructures (RITTS), as well as in Thematic Networks; e.g..STRINNOP - Strengthening the Regional Innovation Profile [6]; VERITE - Virtual environment for regional innovation technologies [7]; PAXIS - Region of Excellence of business creativity [8]; and also the ERIK - European Based Innovation Network [9] realised with the DG REGIO, which keeps in strong contact with the M-Change proposal.

### References

1. *** - http://www.regione.toscana.it

2. *** - http://www.chim1.unifi.it/group/education/index.html

3. *** - http://www.icie.it

4. *** - http://www.edscuola.it/archivio/lre/mental/index.html

5. *** - http://www.innovating-regions.org

6. *** - http://www.innovating-regions.org/network/presentation/displaytn.cfm?tnid=12

7. *** - http://www.innovating-regions.org/network/presentation/displaytn.cfm?tnid=13

8. *** - http://www.cordis.lu/paxis/

9. *** - http://www.eriknetwork.net

# Relevance to the objectives of Priority 7

The relevance of the M-Change proposal objectives for giving an essential contribute to the scientific & technological, wider societal and policy objectives of Priority 7 in the Area of research:1.1.2, will be to develop a multidisciplinary R&D approach as well as it is necessary for an effective improvement of the Socio-economic Knowledge Base in Europe in direct collaboration with trans-European partners that are able to involve in the M-Change project of large amount of Citizen’s stakeholders representatives.

Therefore the project M-Change is driven by a strategy oriented to analysing the following topics:

- Improving the generation, distribution and use of knowledge and its impact on economic and social development by means of the definition of a “branching developmental approach” on sharing Regional best practices the effective European Citizen to develop a down-top “e.governmental methodology” for growing up future Knowledge Society in the contemporary context of knowledge driven economy;

- Searching for options and choices for the development of a variety of paths towards knowledge-based society examining the effective key-forces behind the knowledge driven economy and developing a synergies for enhancing social cohesion through opening the project system of growing up new knowledge to a large number of relevant stakeholders;

- Consider the opportunities of renewing “e.govern policy” and new forms of economic governance at Regional level, just beginning a comparative European perspective oriented to developing a system for a co-operative understanding the best relationships between technology, employment and society that are vital to find new development strategies to achieve growth without impairing employment, social cohesion or the environmental and economical sustainability.

- Identify and testing and a system oriented to examine how different arenas for learning and competence building are inter-connected in specific patterns for shaping different national systems, as well as the implications for the EU open process of co-ordination. The above system can be obtained of through an on line information co-organized by the M-Change Partnership getting the better Knowledge Dynamics comparative possibility to grow up a continuous innovation moving towards on Research and key-Actions for enhancing European Knowledge Economy for all the duration of the project and its successive exploitation.

We are living in a time of major societal changes affecting, patterns of work, education and training and social security and safety systems. As a consequence the M-Change key actions aim to clarify these and other complex interactions between societal trends, changing lifestyles, economic evolution, labour market institutions and cultural patterns, taking Europe’s regional diversity into account. It will cover the high-profile analysis of the issues that the impact of Knowledge Economy on Social change is having on economic development, social integration and different social identity protection in the economical globalisation.

One focus M-Change key actions is following the consideration that today’s trend towards globalisation means that an important way to build competitiveness is constantly to increase innovation in productivity of the so called “Weightless Economy <W.E.> ” based on the marketing of knowledge innovation.

The name Weightless Economy is taken in reference to economic activity whose value does not lie in a physical end-product—in other words, it is intangible. Hence <W.E.> represent an important feature of the Knowledge based Economy.(KbE) In fact KbE might be taken to be nothing more than the proposition that knowledge matters for economic performance of goods production. Hence the “Weightless Economy”, is a more advanced sector of the KbE because it is dealing with the factors that generate an added value of production, mainly as a consequence of the innovation of Knowledge Management ; in this view, comprises various elements concerning the better use of the potentiality of Information and Communications Technology (ICT), for instance on Intellectual assets into e.working organisation for improving networking economy and business for extended enterprises co-organisation, broadly, name-brands, trademarks, advertising, financial and consulting partnership, and also e. education innovation, electronic libraries and databases including new media, video entertainment, and broadcasting. As a matter of facts the <W.E.> is the new R&D field of the Knowledge Economy Research, concerning the failure of central planning of any single enterprise based only on the cash flow of business.

To contribute to a new strategic goal for the European Union in order to strengthen employment, economic reform and social cohesion as part of a knowledge-based economy, the M-Change project will aim to respond to the needs of innovative knowledge management, that will be able to take in consideration the evolution of the “Quality of Products and Processes” enhancing the <W.E.> that is become the fundamental focal point of the global market and marketing competitiveness.

Hence the M-CHANGE key actions will develop a comprehensive study and reports of best practices about the recent restructuring of the centrally planned economies, towards decentralised networking economies based on the <W.E> advancement. In recent times many “Extended Enterprises” are becoming today successful “multi-enterprises and Institution corporations” adding an advanced <W.E > knowledge management, locating themselves around centres of RTD excellence in different countries in Europe. On this particular application the M- CHANGE project will promote an innovative research to realise how Information Communication Technology in conjunction with the <W.E.> are altering the whole nature of the labour market, making life-long learning a vital necessity for all of us and changing the balance between the genders in the workforce, and also at how they are drastically changing the economic relationship of cities and the countryside as locations in which to work and do business.

Taking in account of those preliminary considerations the manner how the proposed M- CHANGE strategy to give a contribute to the scientific, technical, wider societal and policy objectives CITIZEN 3 Call of Priority 7 will be focused in four areas:

- Encouraging citizen understanding on societal trends and structural changes in the advancement of knowledge Society in a way that KbE can be considered a driving force of an evolutionary achievement of European socio –economic contemporary development

- Promoting a new understanding of knowledge dynamics, also addressing to citizen “Science and Society “ priorities and facilitating e.Work employment through favouring innovative skills in knowledge management of Intangible capital based on the “research and society” advancements.

- Disseminating the key trends and new performances of innovative grouping approach for the Regional Economic growth by explaining all possible implications of developing a comparison the best practices on this collaborative grouping’s approach, as a method to transfer in agreement to the local needs and demands an advanced e.governance system, that it will be useful for advancing in the European Information Society Citizenship

- Improving the knowledge of European Citizen about the importance of brain –wave <Weightless Economy> models in Knowledge Economy order to build up employment skills for developing the dynamic of knowledge production, throughout strengthening “the European Research Areas especially in favour to grow up the SMEs competitiveness in the global market.

# Potential impact

Constructive dynamic methodology of Knowledge based growing in the M-Change proposal operates by codifying the innovative meaning of the information within a system of interactive communication technology where citizen and the most relevant stakeholders are included in a grouping territorial co-organization of the partnership’s groupings belonging to the M-Change Consortium.

This inclusion of citizen’s synergic presence permits to progress in the M-Change project by means of a constant co-operation in evaluating the development of the proposal in a way that will be synchronized by a interactive communication system, with the local demands and developmental needs. Citizens’ groups such as their local organisational configurations affecting the potential for innovation and economic development, represent the Social Capital able to recognize the effective of the M-Change proposal. Therefore in other worlds the step by step “strategic impact” it is seen as indispensable and fundamental negotiating element of the constructive dynamic of an evolving communication system that will use a sharing innovative methodology for the M-Change program implementation. Thus, a knowledge-based system of M-Change proposal constantly will operate in recursive loops with citizen ; in fact the project M-Change is increasingly open to the growth of stakeholders contributions, including external Regional or National Institutions, and /or similar unlocked relationships with other networking program of innovation, agencies, small and large firms or commercial associations, e.g. with a large interactive impact of human and social capital.

European development of Knowledge Economy is determined to progressing its internal political and economic integration and to play a global role, but this strategy of European expansion needs to look in detail at the richness of the cultural differences and cultural effects that can generate an effective development of European knowledge economy, in a way to overcome resistances to the change that can be a deterrent to the acceleration of the process of European Integration based on a clear democratic dimension able to ensure that the fertility of the cultural diversity and people identities is not decreasing.

The Key Action of the strategic impact of M-Change project, for example in reinforcing competitiveness or on solving societal problems will therefore understand how the dynamic role that the various levels of governance (local, regional, national and EU), is playing in the European expansion, and will look at best correct ways in which their interaction and accountability can be improved.

The vitality of Knowledge Economy innovation tend to upset the market mechanism and the mass media approaches to homogenization of people behaviour and customs, therefore the M-Change key activities will also get a large feedback impact, by examining the constituents the traditions and ethnicity of Regional or Local civil society in relation to the effective public interest of overcoming the resistances to change. In this manner the project M-Change implementation will give a particular consideration about the future possible citizen’s contributions to the effective advancements of knowledge economy in relation to the different cultures and popular traditions across Europe.

Hence the studies and reports of the M-Change proposal will be explore operatively how different cultures can be responsible to generate or not a resistance of change to the innovation of new developmental socio-economic models that now a days are considered some times only as well “a priori” hypothesis to be able in reinforcing competitiveness or on solving societal problems by an Knowledge Economy European strategy that certainly cannot become possible without a punctual democratic management of a citizen’ consensual domain based on the study and dissemination activities of knowledge dynamics of change.

## Innovation-related activities

The above strategy of the M-Change proposal aiming to relate the impact of the project proposal into the feedback of the same project implementation, if it is considered from the perspective of Economic growth, means also that the effective development of European Knowledge Economy need to create “innovative knowledge management” in the working knowledge society. Therefore this developmental approach will tend to understand how it will be possible to change the traditional hierarchies that are a traditional consuetude of the working function in the obsolete manual labour intensive organization of the industrial society. In fact knowledge production and economic exchange relation in knowledge economy advancements creates many new opportunities of independent “e.work” and management consultancy; this process of growing a new “e.working” structure in the “e.Europe” development, it will successfully able to meet the changing needs in the European information society. But considering that this on line working structure is growing up by a system of self-organization entrepreneurhip, it is possible to comprehend that the new “e.workers” have a strong need to improve a regeneration of the obsolete hierarchies of the industrial working division of labour, and transforming them into a auto-organizing dynamic networking interactive information architecture that will be a fundamental characteristic of the future knowledge society, The change of the division of labour in Knowledge Society that will progressively emerge making a great impact on innovative “e. governmental” systems, that need to become more appropriated to the Knowledge Economy scenario of the world wide information society.

The Key Activities of M-Change Project will therefore investigate the dynamics of employment creation in the e.working dimension in a European Expansion and also some related aspects of the global economy competitiveness where intangible factors predominate. Hence the Project M-Change will explore new sustainable development models which will “square the circle” by simultaneously fostering, intangible business organizations, social capital growth, “e.working” job creation, especially in relation to intellectual property, environmental protection, equal opportunities, the reduction of inequalities and improvement of the quality of life.

To back this up, the M-Change project will develop dynamic indicators of sustainable knowledge economy development, which take into account not only ‘hard’ evidence of prosperity, but also less easily quantifiable factors in the “niche-economy” helping the quality of life of European citizens. Important subjects for this analysis will be how social capital adding-values can be measured, how knowledge management innovative skills and human resources contribute to competitiveness of Europe, how networking work can be organised differently in a context of changing the industrial division of labour, and the role of not-profit enterprises and mutual programmed activity can improve efficient contribution for growing up the Knowledge Society in Europe. The result will give some policy advice on the future e.Europe competitiveness in the global Knowledge Economy development, respecting cultural diversity of European people.

## Exploitation and/or dissemination plans to ensure use of the project results

The M-Change exploitation will based on studies that will contribute to investigate the continuous progresses of the development of knowledge Economy especially regarding social dynamics and self – organizing networking systems of “knowledge management innovation”.

The dissemination plan will be diffused building up an M-Change “KNOWLEDGE ECONOMY PORTAL” that now is in a preliminary phase organized by the LRE-EGO-CreaNET of the University of Florence, for the partnership collaboration. In future the “Knowledge Economy Portal”, where running work plan activities of the projects will be diffused, will be built up with a clarity: language, in the discussion list, newsletters and forums oriented to find a coherence and better cohesion though “portal mirrors” that will be realized in all the partnership’s languages.

See: http://www.edscuola.it/archivio/lre/mental/index.html

The implementation plan will be realised by means of various multidisciplinary approaches to social and economical sciences oriented to better understanding the socio-economic development, based on theories of complexity and evolutionary dynamics. On the basis of such theoretical approach the knowledge dynamics will be explored, through research studies and readings (many online) and from the best practices data, received by the partner’ groups, that will be collected by an apposite Wireless structure of Educational Research Laboratory (“ERWL”), that will be co-organised by the M-Change Partnership. http://www.edscuola.it/archivio/lre/mental/interna7it.htm

The functional activity of such “ERWL” will be to act to implement a “Distributed Knowledge” that follows the “ERWL” editorial work to transform the received information into Knowledge Economy on line publications, in a new ordering perspective, oriented to facilitate the understanding of citizen through a great diffusion and dissemination.

Preliminary issues of such Editorial Work of the “ERWL” co-operative ICT infrastructure will be oriented to understand the potential role that ICT technology applied to the grouping context of basic information will play in the processes of growing up European Knowledge Economy.

In fact as well as other research of the M-Change program will be realised by a multi-disciplinary approach to the study of the socio-economical information coming from integrated alliances between research centres, governmental institutions and industry.

The elaboration in publication on line of those information will represent a way in which the knowledge dynamics flows into new sources and methods to utilise ICT innovation for helping citizen understanding about the effective needs of change in reinforcing European competitiveness or on solving socio-economic problems.

The above elaboration of information data in knowledge Economy on line publications has become an innovative activity’s task of M-Change proposal, that deeply change the previous emphasis limited to the diffusion of information about the technology transfer from Centres of Research to Industry, this because the spiral model of knowledge dynamics innovation, proposed by the M-Change project, requires to capture multiple reciprocal linkages at different stages of the capitalisation of Knowledge Economy and to assess them with the direct participative contribution of Citizen to the progressive distributed knowledge activities.

To ensure use of the project results, in turn the M-Change Consortium will produce a strategic dissemination plan of the publication realized by the ERW Laboratory for all the following categories of citizen:

- enterprise managers - who have to think far more about realising advantage through knowledge, intellectual capital, and knowledge management;

- employees - who need to change the skills and to learn for adjusting the their working ability;

- investors and financiers - who need to recognise and to assess the value of “intangible assets”;

- policy makers - who must create a climate conducive to success to the competitive new challenges created by the ICT –business application to a wider exploitation of new products and processes.

## Added Value at the European Level of M-Change strategic Activities

Focusing those categories of citizen the effective contributions of the M-Change Working Plan will be disseminated both at Regional and at European level and will be concentrated on the following specific actions will make:

Promoting “Net learning Programs” to identify and disseminate creative opportunities of innovative Knowledge Management for a closer and efficient European inter-regional co-operation.

Spreading M-Change educational programme on “collaborative intelligence management” which ensures that the knowledge based capabilities, including innovative management practices, are disseminated to a European and Trans-national level.

Provide a systematic exchange of information and best practices concerning significant social and economic changes that are being driven by the European Knowledge Economy.

- Favour the knowledge diffusion on Intellectual Property Rights arrangements, in a way that Regional Industry can profit from the knowledge or from licensing and patenting opportunities of science and technology innovation.

- Develop and diffuse an advanced knowledge and best practices about running programs in the development of campus or spin out companies or joint ventures between the science base RTD Centres and University’s and SME’s Associations or Grouping.

- Exchange and elaborate evaluation practices and financial procedures for an achievement of common and complemented networking programs

- Assist innovation and enterprise stimulation networking programmes, through organising Regional Congress and local workshops and also short term meetings of managers supporting them with the knowledge of “science & business” opportunities emerging European and Trans European levels.

- Developing and experimenting collaborative on line methods for sharing experiences and promoting best practices for joining and integrating programs between University and SME’s at the European level.

- Delivering on line case studies/ benchmarks materials, mutual opening initiatives and position papers, based on disseminating for instance innovative experiences on a number of specific problems and successful demonstration on Knowledge Dynamics, through a range of media/multimedia routes and could include short company visits, seminars, brief staff exchanges, etc.

In order to realise these M-Change strategic activities successfully, a mutual partnership’ recognition based on the International Steering Committee sharing evaluation will enable the dissemination to reduce the conceptual complexity by means of a preliminary discussion made for searching to escape from problems of ambiguity in the conceptual interpretation. Furthermore the validity of innovative indicators, and easier monitoring and evaluation procedures and program management approaches will be organised to ensure that they are comparable throughout the Europe, and to favour an effective European Integration.

## Contribution to standards

To lay the foundations for the future development of EUROPEAN KNOWLEDGE SOCIETY, the contribute of M-CHANGE PROJECT will be to evaluate standard ICT platforms to access to a large WEB-Information and Portals construction through management of knowledge and networking e.Learning. Modelling of very-large, scaleable and interoperable knowledge spaces, including GLOB technology tools supporting contextualisation and visualisation, and intuitive personalised interfacing with the user, will be validated by the M-Change Consortium Activities, as expected in challenging applications in various business and societal contexts; in particular, e-book, and more in general e.ediction infrastructures will be assessed , with emphasis on the context regarding  their utilisation on a great diffusion and a high impact of emerging fields of Knowledge Economy.

The contribution to ICT of the project M-Change is to consolidate ongoing research efforts in especially advanced methods of sharing of knowledge and the use of interface technologies , to aggregate cross-disciplinary know-how and to develop exploitable software components that can contribute to the development of the objectives of the eEurope and eEurope+ initiative; especially the validation of standard based software components will be a contribute to standards of the M-Change Project, that can be useful in areas of networking e-learning, cultural resources, digital content and cultural and linguistic diversity.

# Outline implementation plan

## Research, technological development and innovation activities

The Research activities of the M-Change project will be realised by the method of Goal Oriented Project Planning (GOPP) of self-management of the partnership oriented by the common goals and objectives of the M-Change Project.

This is an important research Method for understanding in a “bottom to top” approach the process of the KNOWLEDGE DYNAMICS in process of Networking e.learning and skills and competence building, coming from the effective thinking processes of European citizen and the most representative stakeholders belonging to SME’s and Governmental Regional Institutions in co-operation with public and private Research and Development Centres.

The above means that the M-Change project will develop a co-ordinated activity with other Interregional Proposal like the ERIK project that is also co-ordinated by the Regione Toscana (see: http://www.eriknetwork.net) to stimulate the creation of innovation driven dynamics for understanding the effective dimension of growing of Knowledge Society based on the creation by the M-Change Consortium partners of clusters before described as well Regional Interest Grouping (RIG) or National Interest Grouping (NIG) and also as Thematic Interest Groupings (TIG).

Therefore an auto-organisation an auto-organisation of the project partners, is necessary where develop an unified system TASKS in a way that it will be possible to obtain a down to top understanding of the evolution of the dynamics of change of the European Knowledge.

This not hierarchic character constitutes the fundamental GOPP – Research and ICT methods that constitute the basic logic of project M-Change. As a matter of facts this kind of GOPP planning, is improved for increasing and experimenting a participative democracy in the construction of integrated business networks and to measure with appropriated indicators the social capital dimension of future development of the European Knowledge Economy.

This GOPP approach in Research & development of the dynamics of change it will be clearly important to follow a line of investigation able to safeguard the richness of the different European Identities and at the same time to find together the best practices to change by means of sharing knowledge by e.work as an international e.society team, interpreting the territorial needs and managing ICT skill profiles and competencies for understanding the down-to top ability to drive the dynamics of change in the future evolution of European Knowledge Economy.

The M-CHANGE project will integrate the results of the Work-Packages at different level of complex elaboration of the creative knowledge construction. In the first start up (this section will take a duration of about one year) the Work will be done by each single partner at Regional Level. In a consecutive approach the partners and the stakeholders belonging to the same country will develop a National Model of Knowledge Dynamics in a dimension related to a National sub-Project, (this second section will take place in the second year of M-Change results integration). The third year of the M-Change Project duration will be includes an integration of results in three diverse models belonging to member Country’s model, associated Country’s Model, and new entry country’ model, in a way to obtain three dimension approach of the dynamics articulation of the GOPP supporting the evolution of the European strategy to develop the most important knowledge economy in the competitive Global World Society.

## Training activities

The training activities of the M-Change Project will be developed by all partners enjoining in the collaborative organisation of  the E.R.W.L.The Education Research Wireless Laboratory will be co-organised among the M-Change Consortium as well as a Centre of Cognitive Dynamics.

ERWL carries out the elaboration of research into the knowledge dynamics in the social and cultural changes in society in the direction of a European Knowledge Economy. The ERWL will develop two main functions:

- Target citizen and policy makers:  for this target will be elaborated Web-Training activities Science and technology aspects and impacts on changing the division of labour in society, with a particular focus on the dynamic relations between new technologies, new knowledge and social, cultural and organisational change.

- target SME’s management: the ERWL aims to enrich the Knowledge Management by means a Web-Log  (BLOG) system for permanent on line education understanding of knowledge Dynamics by drawing on a wide range of perspectives and styles from across a multidisciplinary aspect of sciences and humanities, and to use the insights gained from this research to contribute to favour the development of an integration between academic and business arenas.

Our current and recent research focuses on the following areas:

- best Practices on NET/ learning and impact of new technologies focus on their ability to improve the knowledge based society in a context of European enlargement;

- specific themes of  EWRL research will focus on the questions raised by new technologies for developing knowledge Economy  and by the different influences in different regions produces the development of an appropriated utilisation of ICT tools;

- strategic planning on internet  knowledge management;

- corporate Strategic Planning between University and SME’s;

- cognitive management profiles of net-workers;

- emotional style of on line management staff co-operation;

- clusters aggregation for regional knowledge innovation.

Answering the questions described above requires a detailed and intensive approach to strengthening an European Research Area in Education Research in a broadly constructive multidisciplinary approach of cognitive innovation in a way that is able to link directly advanced research and an innovative permanent system of e.education.

This method is based on the knowledge sharing system rather than aligning with a subdivision of disciplinary labour made by particular scientific or technical expertise. From a constructive perspective, the strength of the analysis comes through treating all contributors symmetrically and from being willing to question taken-for-granted perspectives.

As a matter of facts ERWL research is characterised in the project M-Change  by a focus on qualitative sociological and historical and scientific research, employing multidisciplinary approaches for NET –LEARNING such as, discourse analysis and conversation analysis in some virtual on line “blog” system. These approaches are particularly suited to exploring the detail of social and cultural dynamics in the complete deference of different educational identities among various people in a Trans European level of co-operative on line working.

Current topics concerning the training of research results therefore include environmental risk, new genetics, and the Internet application to the permanent education. More specifically the training activities will also include activities on:

- intercultural analysis of the impact dissemination activities of M-Change;

- research into the ideas that obtain more audience from the most relevant stakeholders;

- exploration of the use of BLOG technology in the net-leaning activities;

- studies of public perceptions of risk in relation to the needs of change in mentality;

- comparative research into the understanding of knowledge socio-economic dynamics.

## Management Activities

The project management activities in the phase of the start up of the proposal MENTAL CHANGE http://www.edscuola.it/archivio/lre/mental/ would be developed by LRE/EGO-CreaNET of the University of Florence http://www.chim1.unifi.it/group/education/index.html in collaboration with ICIE  -Bologna http://www.icie.it/frame.htm. Both of those Partners work in a open collaboration with the TUSCANY REGION http://www.regione.toscana.it for the Knowledge Management of the project proposal; moreover Prof. Danut Iordachescu working for UIJG also collaborates (dan_iord@yahoo.com <http://www.geocities.com/dan_iord/) with the role of internal evaluator. Also from the New Economy evaluation Strategy the Prof Enzo Rullani (Business Strategy Department of Business Economics and Management ,University of Venice; rull@unive.it.) will work with the partner EGO-CreaNET, and from the evaluation of the M-Change research from the Sociology point of view will act as an internal Evaluator Prof. Patrizio Di Nicola form Department of Sociology of the University La Sapienza in Rome (patrizio@dinicola.it, http://www.discuniroma1.it/).

The Laboratory of Education Research LRE/EGO-CreaNET is a University Research Public Institution for implementing knowledge managemenyt innovation through strategies of e.education and it is an expert on the following fields: distributed knowledge, knowledge sharing activities, knowledge dynamics, virtual community, and on line teaching and learning.

ICIE is a private research institute oriented to favour the increasing of the technical culture and the entrepreneurship knowledge management skills of SMEs and has competence on the following fields: Benchmarking and best practices diffusion, Business process analysis, Business transformation, communication skills, Management Information System, Organisational development, Supply chain management.

The Prof Danut Ioardechescu collaborates at the Knowledge Management activities as well and he is an expert in following fields: Knowledge representation, knowledge creation, project program management, quality management, strategic planning, strategy and forecasting, value based management.

As an external evaluator for an independent assessment of the quality assurance of the Knowledge management development system of the project the M-Change project has involved the Italian Ministry of Research and Education in the person of Dr. Fulvio Obici (fulvio.obici@murst.it, http://www.edscuola.it/archivio/lre/mental/interna7it.htm) who is responsible of the Communication on the EU funds.

The knowledge management model, will be definitely co-organised by the M-Change CONSORTIUM, during the implementation of the project, and will follow a methodology of research of KNOWLEDGE DYNAMICS based on a “comparative analysis of evolutionary trends of socio-economic changes”.

The main aspects of this approach request that all partners “e.works” with the same tasks through adaptive internal agreement  of producing results  and design knowledge dynamic characteristic and tools for analyse the improvement of innovation and changes,  in a way that it will be possible to realise a result of a differential comparative analysis in an evolutionary trends of the Knowledge Dynamics in a trans-European context of its regions.

The knowledge management model will begin by identification of crucial evolutionary characteristics useful as well dynamics uniform indicators of these models applied in the forecast of the future enlargement of the Europe. Consequently the method of comparative analysis of evolutionary trends will be focused on far-from-equilibrium analysis in diversity of cultural scenarios and in heterogeneity of economic agents favouring the goal of the development of Knowledge society. The product resulting by this model of comparative analysis of evolutionary trends of socio-economic changes will be useful for improving a WEB-Portal dissemination and demonstration activities, as well as for improving a flexible web-training education materials for presenting in occasion of open workshops and international congress.

# Description of the consortium

The M-CHANGE Consortium will be organised as a virtual community. On the other hand, the Mental Change proposal relays on these Groupings organized by Governmental and Public Institutions of Research and Private Companies in a way to grow up an effective knowledge potential that will be able to establish a down-to-top methodology to study the knowledge dynamics of the development of the European future Knowledge Society.

The M-CHANGE Project will be grounded on the analysis of the needs of understanding the dynamics of development of Knowledge Economy in a context of the European enlargement, incoming new countries belonging to the historical and geographical natural European environment.

The M-Change Consortium will be collectively working in a networked high quality dimension founded by the high complemented e.Working approach for producing a research on Knowledge Dynamics on the European strategy of development of Knowledge Society.

The M-CHANGE studies collectively investigate the uses of the Open and Distance Technologies to support collaborative research among groups of Regional clusters using ICT tools and infrastructures. Aiming to enhance their activity’s practices, the high skills in the field of ICT identified for each participant of the M-CHANGE Consortium play major role to guarantee the achieving of the project aims and objectives.

The partnership includes the following institutions (see for description Appendix A):

1 Regione Toscana (Italy) (coordinator)

2 UNIFI/LRE (Italy)

3 UOR (Italy)

4 ICIE

5 EBS (Estonia)

6 ULP (France)

7 TERRA (Hungary)

8 PLATO CORK (Ireland)

9 ICRI (Ireland)

10 SSI (Lituania)

11 SUC –Busines Adm. (Norway)

12 RKK (Norway)

13 PWR (Poland )

14 BYWEB ( Portugal)

15 IST (Portugal)

16 IPA (Romania)

17 UDJG (Romania)

18 ACD (Romania)

19 BIC GROUP (Slovak)

20 CSV (Slovenia)

21 IJS (Slovenia)

The gravity centre of the Dynamics of Social Change is the international work in knowledge dynamics achieved till now by the European Projects developed of the Tuscany Region  in co-operation with the Region Emilia Romagna, which has involved 20 different European Regions from Italy, Austria, Germany, France, Greece, Portugal, Spain, U.K, Belgium, Denmark, Netherlands, Sweden.

The Mental Change project works by declaring its strong relationship with the European Region Knowledge Based Innovation Network (ERIK) financed by the EU- D.D.REGIO. Thus, the Mental Change become more important, because can develop content of the Knowledge Dynamics that is growing up from down to top in a very strong contact with the citizen and the Developmental Economic forces of EUROPEAN, which are the SMEs and other stakeholders, representing the social democratic understanding of the complex change.

The Tuscany Region and ERIK Inter-regional consortium committed to promote the Mental Change proposal because the ERIK project (where the partnership can be only composed by Institutional Regions) is not able to develop the necessary clustering for stimulating the creation of the innovation-driven groupings. The Mental Change doesn’t need to spatially cover the whole Europe, but will have a wider enough coverage enabling the differentiated research approach, able to develop different Down Top Models for the MS and AS, as too.

The M-CHANGE Consortium, working as well as a Virtual Enterprise Research Network, aims to promote and foster research links between academic and industrial researchers and to disseminate the results to European Citizen co-operating all together at the convergence between the following Consortium collective tasks:

- Collaborative multidisciplinary Research and Developmental Applications concern the study of the new organisational practices and business models of Knowledge Economy Dynamics that arise from the availability of Internet and Web technology. They include favouring the establishment of University-SMEs research joint ventures in  e-Commerce, network economy and virtual communities co-organization and virtual teams co-operative applications. To co-ordinate more effectively Institutes and Centres with a Mental Change, the research will be focused on establish a more efficient processes in the joint management of research projects, including the regular monitoring of reporting requirements for funded research.

- Mutual learning co-operative strategies concern the processes, methods and tools for the development and maintenance of the collaborative applications in Networking e.Learning-based on the job permanent training strategies and also for on demand e.Education systems; they include for instance groupware workflow - Glob Technology for sharing knowledge; support the development of innovative and good e.Teaching practices, that enable to overcome the skill shortage in knowledge management of  the Research and Business Integration; encourage mutual learning through an open debate with the more representative stakeholders in each partner’s country about the importance of the European Knowledge Economy development oriented to the accession in the European Union,  web-seminars, electronic forums and innovative links between research and teaching programs.

- Developing strategic plans including an evaluation of the future research infrastructure and maintenance needs on a three-year basis. The plans will be annually reviewed to enable the possibility that before the end of the M-Change Program to open a new call to: enrol new partners; for opening new key areas of co-operative research on a comparative regional basis of  electronic 'talk networks' and net-learning activities; the developmental best practices used by means of the driven cognitive and educational kits designed to operate across trans-national geographic environment and organisational interdisciplinary boundaries, to obtain research flexible, portable and maintainable results that can be largely distributed.

In conclusion, the complexity of the proposed M-CHANGE research Consortium relays on that the progress can only be made through series of the previous analysed pre-competitive Research and Development goals and objectives, oriented to the understanding the Dynamics of Knowledge Society in Europe. This will be associated with a strategy of growing up virtual enterprises by means of an innovative management, bringing together in an integrated manner various Institutions, Companies and Governmental Regional Institutions. Thus, the organisation of the Regional Clusters (or Interest Groupings), can become able developing a distance-research, which will work as an infrastructure incubator concerning the Development, Implementation and Deployment of the KNOWLEDGE ECONOMY by means of a multidisciplinary project.

### Complementary working functions and tasks of the participants

Remembering that the Mental Change Consortium reunites a trans-European partnership community to contribute to enable the development of an ERA of understanding and disseminating the knowledge dynamics in terms of the new social trends and new net learning activities and, by networking business and looking at the following figure of the Operational Co-Organization Of Mental Change Consortium, the e.Working function of each partner is subdivided in the following three sections.

A - Research & Development Section.

All partners generate research and gives contribution to the main strategic objective, which is to understand the role of knowledge dynamics on the effective development of the Knowledge Society in processes of learning and competence-building within a clustering method to guarantee an industrial and commercial involvement at regional level and to relate the strategic objectives  to issues of competitiveness, regional development and economic and social cohesion.

The fundamental R&D activities of the M-Change Consortium will be co-ordinated by the project co-ordinator the Regione Toscana in collaboration with the LRE/EGO-CreaNET. The Regione Toscana is also the leader of the ERIK NETWORK Programme and it has the aim to establish a strong synergy between the two actions.

This fundamental A section will be open to other partners not identified by now, which can enjoy the Mental Change Consortium after 18 Months by participating to a new Call, oriented to obtain a more large exploitation of the Mental Change results applied to the European SMEs-University networking joint ventures. In particular, their tasks will be to open a great impact to the industrial and commercial involvement foreseen to ensure future sustainability of the M-Change Consortium.

B - Net learning open system.

The partners UNIFI/LRE, UOR, ICIE, EBS, SSI, SUC, UDJG and CSV will implement the Educational Research Wireless Laboratory. The co-operative task of this group of partners will be to develop a system of training activities in knowledge management innovation organised as a NET-Learning infrastructure especially in the “on the job” and “on demand” long distance web-learning educational material production in form of e.Books or hyper-texts and tool-kits useful for a large diffusion and exploitation of intermediate information and final results of the M-Change Research & Development.

C – Documentation.

It concerns the investigation and the preparation of a selected Documentation about the Best practices and policy studies of the advancements of knowledge dynamics. The E-Publishing Group of the M-CHANGE is a bold far-reaching collaborative project involving all consortium partners, but an especial task force will be composed by the following partners: UNIFI/LRE, ICIE, ULP, ICRI, PWR, IST, IPA, IJS.

The E-Publiscing Task Force has grown to encompass two main aims:

- to create an end-user  driven collection of  Best Practices of Knowledge Society advancements and Research & Development  co-operation among University and industrial and commercial enterprises at the level of regions ,sectors, social groups, and most important stakeholders;

- to review and redesign the Documentation production to yield more flexible formats that help contain costs and facilitate multiple output and use options of the Knowledge Contents dissemination through electronic publishing activities.

The M-Change Consortium partners proposes a detailed description of their involvement and action roles and tasks in the M-CHANGR Consortium for identify their proposals in the project activity participation (see Annex 1 – Role of the partners).

# Description of project management

- Starting from successful past experience of different national and international projects, we propose a lean but effective organisation of the management activities. The management structure envisaged for this project is based on four responsibilities: the Project Co-ordinator (PC), the Partners Board (PB), the Technical Committee (TC) and the Workpackage Co-ordinators (WPCs).

- The Partners Board (PB) is in charge of setting the broad project direction so as to ensure that project execution produces benefits for all the partners. It is constituted by one senior representative from each partner and is chaired by the PC. The PB members have the necessary authority within their organisation to make commitment of staff and other resources as required by the project. If a PB member is not present or represented at a management board meeting, that partner is bound to honour decisions taken and actions placed on it in its absence. The PB:

- Takes strategic decisions, resolves project-wide issues, agrees on project modifications whenever required, and generally supports the PC in guiding the project to a successful completion.

- Ensures that the project maintains technical and cost objectives, and resolves technical and administrative issues that are not resolved by other means within the project.

- Actively promotes consensus in case of conflict and, if no consensus can be found, the decision is taken by a 2/3 majority vote of the PB.

- The Technical Committee (TC) assists the other Project Management entities by supporting all their technical decisions. It is constituted of the TC Co-ordinator (TCC) and other members appointed and possibly revoked by the PB and selected within the most qualified specialists of the technical partners. The TC is chaired by the TC Co-ordinator who is chosen by the TC within its members. The TC:

- decides on documentation standards, quality control and acceptance procedures,

- ensures that the decisions taken by the PC and the PB (including changes to the workplan) are, from the technical viewpoint, inter-compatible and in line with the project objectives and future developments,

- revises every deliverable before submitting it to the EU Commission and, in case it is not satisfactory, manages its improvement by advising the WL in charge of it,

- establishes liaisons with related projects, both terminated and in progress, to exchange knowledge and results and reduce overlapping and redundancies.

- The project will be managed on the basis of a general plan, agreed with the partners, made of Workpackages and tasks, as described in Part B. The Project will have:

- Project Co-ordinator (PC). The role and task of PC is to co-ordinate and monitor the overall progress and state of the project. The PC will perform his task on a daily basis and will keep under permanent control the development of all activities (in terms of results, budget, time, as defined in the project plan), do its best to keep the group together, have a problem solving approach and attitude, avoid potential disputes, work for conflict solutions. The co-ordinator will also maintain permanent contact with the European Commission on both organisational and technical contractual questions (accounts, delivery of reports, etc.) and will co-ordinate relations with all the operating units of the partners. In addition, in order to guarantee homogeneity in terms of contents and of recognizability, the Co-ordinator will provide guidelines for the development of deliverables and will cooperage with the WP Co-ordinators;

- WorkPackage Coordinators (WPCs). Each WPC will be responsible of his WP specific activities and will guarantee the achievements of the objectives and good results of their WP in terms of technical contents quality, time, budget and EC contractual requests (i.e.: deliverables, peer reviews, etc. ).

- Project Management will also cover the following:

- COMMUNICATION FLOW

- Ensuring a good communication among project partners and towards the outside world represents an important ingredient for the success for the project. The communication strategy pursues two main objectives:

- keep all partners fully informed about planning, work in progress and problems;

- disseminate the project results to the interested audience. For the internal communication, technical and plenary meetings constitute the main events to ensure deep knowledge exchange. They are integrated by daily communications via e-mail and file transfer, the operation of a Project Office and the creation of a private Web site provided with a proper support like BSCW. For the outside communication and promotion of the project results, the envisaged means are publications, constitution of the Interest Group, organisation of workshops, and creation of a public project Web site.

- PROJECT CONTROL PLAN

- A PCP will be made available and it is supposed to function as an operational manual for the consortium, identifying an unambiguous and appropriate workflow between consortium partners and the various roles, designed for the project.

- The PCP will identify:

- rules for task execution and documentation, times and criteria for deliverable revision, procedures to manage deviations and unconformity

- a clear list of all review, audit and acceptance points in the lifecycle of the project

- all types of forms and other documents that must be prepared in the project course, in order to closely track the project progress and allow for early problem identification and solving

- a special communication flow diagram, depicting graphically the relationship between the critical points, the respective documents and the precise roles/ persons involved in their process (production, submission, acceptance, etc.).

- The Plan is inspired to a quality policy that must be kept light to cope with the RTD project nature, and nevertheless sufficiently strict to homogenise, in quality, the contributions brought by the different Consortium partners.

- PROJECT ASSESSMENT

- The project is subject to an independent assessment of its progress and results, which is in charge of a Project Evaluator, appointed by the co-ordinator, who is not involved in other project technical or managerial activities. To this purpose, a specific task is envisaged in the workplan, WP0/T0.2, which lasts the whole project life and produces, at the end of the project the Project assessment manual (Deliverable 17).

- RISK MANAGEMENT

- Many Consortium partners already participated in European RTD projects, then they are aware that an innovative and prototypal work like this is subject to a number of risks. Such risks have already been identified and presented, in section B6.6, in terms of causes, consequences and contingency plans. This constitutes a good reference point for the Project Management structure, by which the project will be kept in line with its objective and scope.

- PROCEDURES FOR CONFLICT RESOLUTION

- Two main types of conflict have been envisaged as potentially damaging:

- diverging views regarding the project roll-out strategy, encompassing issues such as medium-term objectives and longer-term exploitation policies; these will be handled and solved within the PSC, pragmatic negotiation being the base of the conflict resolution approach. Should the consensus being not achievable as above stated, a majority vote will resolve the conflict, each of the members holding one vote;

- as above, referring to technical assessments, choices and implementation routes; possible conflicts of this nature will be handled and solved within the technical responsibility of the WP Co-ordinator by means of a thorough technical evaluation that will exploit to its maximum both skill and experience availability within the Consortium itself. Should an agreement prove impossible, the Project Co-ordinator will appoint an independent referee whose judgement will be considered conclusive.

- The principal conflict resolution procedure will clearly be proactive by creating an open, consenting and coherent working climate between the partners. In case this proves unfeasible, the conflict will be dealt with by the PB by approval of a relative majority. In case of even number of the members of the organisation co-ordinating the project will be entitled to a double vote.

- The Consortium will use Project Management tools and techniques to keep the project progress under control (schedule chart, PERT, Gantt, etc.).

# Project resources

The following table summarises the costs that the M-CHANGE Consortium partners intend to bear for the execution of the project. Note that labour rates are per person-month and include overheads, while other costs include travel and costs (local service providers, purchasing and installation of other technical equipment) necessary to carry out the envisaged activities.

| Nr. | Partner | Country | Cost model | Labour rate | Effort (mm) | Labour cost | Other costs | Total costs |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Regione Toscana | Italy | FC | 7.000 | 70,0 | 490.000 | 25.000 | 515.000 |
| 2 | LRE | Italy | AC | 7.000 | 33,0 | 231.000 | 6.000 | 237.000 |
| 3 | UOR | Italy | AC | 7.500 | 20,2 | 151.500 | 6.000 | 157.500 |
| 4 | ICIE | Italy | FC | 7.000 | 53,5 | 374.500 | 15.000 | 389.500 |
| 5 | EBS | Estonia | FC | 7.000 | 48,7 | 340.900 | 10.000 | 350.900 |
| 6 | ULP | France | AC | 7.200 | 38,2 | 275.040 | 15.000 | 290.040 |
| 7 | TERRA | Hungary | FCF | 3.600 | 50,7 | 182.520 | 20.000 | 202.520 |
| 8 | PLATO CORK | Ireland | FC | 5.600 | 48,7 | 272.720 | 10.000 | 282.720 |
| 9 | ICRI | Ireland | AC | 4.800 | 29,2 | 140.160 | 6.000 | 146.160 |
| 10 | SSI | Lithuania | FC | 2.700 | 57,2 | 154.440 | 10.000 | 164.440 |
| 11 | SUC | Norway | AC | 6.000 | 29,2 | 175.200 | 6.000 | 181.200 |
| 12 | RKK | Norway | FCF | 6.000 | 41,7 | 250.200 | 10.000 | 260.200 |
| 13 | PWR | Poland | AC | 1.680 | 56,2 | 94.416 | 10.000 | 104.416 |
| 14 | BYWEB | Portugal | FC | 7.000 | 42,5 | 297.500 | 10.000 | 307.500 |
| 15 | IST | Portugal | AC | 2.800 | 49,7 | 139.160 | 6.000 | 145.160 |
| 16 | IPA CIFATT | Romania | FC | 2.400 | 55,7 | 133.680 | 10.000 | 143.680 |
| 17 | UDJG | Romania | AC | 2.400 | 67,5 | 162.000 | 6.000 | 168.000 |
| 18 | ADC | Romania | FC | 1.800 | 53,7 | 96.660 | 10.000 | 106.660 |
| 19 | BIC GROUP | Slovakia | FCF | 5.544 | 56,7 | 314.345 | 10.000 | 324.345 |
| 20 | CSV | Slovenia | FC | 2.100 | 54,7 | 114.870 | 10.000 | 124.870 |
| 21 | IJS | Slovenia | AC | 5.376 | 27,9 | 149.990 | 6.000 | 155.990 |
| 22 | New Partner 1 | ? | FC/FCF | 5.000 | 19,2 | 96.000 | 4.000 | 100.000 |
| 23 | New Partner 2 | ? | FC/FCF | 5.000 | 19,2 | 96.000 | 4.000 | 100.000 |
| 24 | New Partner 3 | ? | FC/FCF | 5.000 | 19,2 | 96.000 | 4.000 | 100.000 |
| 25 | New Partner 4 | ? | FC/FCF | 5.000 | 19,2 | 96.000 | 4.000 | 100.000 |
| 26 | New Partner 5 | ? | FC/FCF | 5.000 | 19,2 | 96.000 | 4.000 | 100.000 |
|  |  |  |  | TOTAL | 1.080,90 | 4.540.801 | 237.000 | 4.757.801 |

## IP Project Effort Form

### MANAGEMENT ACTIVITIES

| ID | Start month | End month | 1-Regione Toscana | 2-LRE | 3-UOR | 4-ICIE | 5-EBS | 6-ULP | 7-TERRA | 8-PLATO CORK | 9-ICRI | 10-SSI | 11-SUC | 12-RKK | 13-PWR | 14-BYWEB | 15-IST | 16-IPA | 17-UDJG | 18-ADC | 19-BIC GROUP | 20-CSV | 21-IJS | 22-New Part. 1 | 23-New Part. 2 | 24-New Part 3 | 25-New Part 4 | 26-New Part 5 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP0 | 1 | 36 | 15,0 | 5,0 | 3,0 | 5,0 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,5 | 0,2 | 0,2 | 8,0 | 0,2 | 0,2 | 0,2 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 39,5 |
| T0.1 | 1 | 36 | 11,0 | 3,0 | 0,0 | 3,0 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,5 | 0,2 | 0,2 | 5,0 | 0,2 | 0,2 | 0,2 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 25,5 |
| T0.2 | 6 | 36 | 4,0 | 2,0 | 3,0 | 2,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 3,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 14,0 |
|  |  |  | 15,0 | 5,0 | 3,0 | 5,0 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,5 | 0,2 | 0,2 | 8,0 | 0,2 | 0,2 | 0,2 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 39,5 |

### RTD/INNOVATION ACTIVITIES (1/2)

| ID | Start month | End month | 1-Regione Toscana | 2-LRE | 3-UOR | 4-ICIE | 5-EBS | 6-ULP | 7-TERRA | 8-PLATO CORK | 9-ICRI | 10-SSI | 11-SUC | 12-RKK | 13-PWR | 14-BYWEB | 15-IST | 16-IPA | 17-UDJG | 18-ADC | 19-BIC GROUP | 20-CSV | 21-IJS | 22-New Part.1 | 23-New Part. 2 | 24-New Part. 3 | 25-New Part. 4 | 26-New Part. 5 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP1 | 1 | 3 | 6,0 | 3,0 | 2,0 | 5,0 | 5,0 | 2,5 | 4,0 | 3,0 | 2,0 | 3,5 | 1,5 | 3,0 | 3,5 | 2,5 | 3,0 | 4,0 | 6,0 | 4,0 | 4,0 | 4,0 | 0,6 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 72,1 |
| T1.1 | 1 | 2 | 3,0 | 1,0 | 1,0 | 2,0 | 2,0 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 0,5 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 31,7 |
| T1.2 | 2 | 3 | 2,0 | 1,0 | 0,0 | 2,0 | 2,0 | 1,0 | 1,0 | 1,0 | 0,5 | 0,5 | 0,5 | 1,0 | 0,5 | 0,5 | 1,0 | 1,0 | 3,0 | 1,0 | 1,0 | 1,0 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 21,7 |
| T1.4 | 2 | 3 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,5 | 1,0 | 1,0 | 0,5 | 1,0 | 0,5 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 18,7 |
| WP2 | 3 | 6 | 3,0 | 3,0 | 1,0 | 5,0 | 5,0 | 2,5 | 5,0 | 3,0 | 3,0 | 6,0 | 1,5 | 3,0 | 6,0 | 3,0 | 5,0 | 5,0 | 7,0 | 3,0 | 5,0 | 4,0 | 0,6 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 79,6 |
| T2.1 | 3 | 4 | 1,0 | 0,5 | 0,0 | 2,0 | 2,0 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 0,5 | 1,0 | 2,0 | 1,0 | 2,0 | 1,0 | 3,0 | 1,0 | 1,0 | 1,0 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 26,2 |
| T2.2 | 3 | 6 | 1,0 | 0,5 | 0,0 | 2,0 | 2,0 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 0,5 | 1,0 | 2,0 | 1,0 | 2,0 | 2,0 | 2,0 | 1,0 | 2,0 | 1,5 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 27,7 |
| T2.3 | 4 | 6 | 1,0 | 2,0 | 1,0 | 1,0 | 1,0 | 0,5 | 1,0 | 1,0 | 1,0 | 2,0 | 0,5 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 2,0 | 1,0 | 2,0 | 1,5 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 25,7 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP3 | 6 | 9 | 5,0 | 1,5 | 1,0 | 3,0 | 6,0 | 2,5 | 3,0 | 6,0 | 2,5 | 5,0 | 1,5 | 3,0 | 5,0 | 3,0 | 3,0 | 6,0 | 5,0 | 4,0 | 5,0 | 5,0 | 5,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 81,0 |
| T3.1 | 6 | 8 | 2,0 | 0,5 | 1,0 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 0,5 | 1,0 | 0,5 | 1,0 | 1,0 | 1,0 | 1,0 | 2,0 | 1,0 | 0,0 | 1,0 | 1,0 | 1,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 22,5 |
| T3.2 | 7 | 8 | 2,0 | 0,5 | 0,0 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 1,0 | 2,0 | 0,5 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 30,0 |
| T3.3 | 7 | 9 | 1,0 | 0,5 | 0,0 | 1,0 | 2,0 | 0,5 | 1,0 | 2,0 | 1,0 | 2,0 | 0,5 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 28,5 |

### RTD/INNOVATION ACTIVITIES (2/2)

| ID | Start month | End month | 1-Regione Toscana | 2-LRE | 3-UOR | 4-ICIE | 5-EBS | 6-ULP | 7-TERRA | 8-PLATO CORK | 9-ICRI | 10-SSI | 11-SUC | 12-RKK | 13-PWR | 14-BYWEB | 15-IST | 16-IPA | 17-UDJG | 18-ADC | 19-BIC GROUP | 20-CSV | 21-IJS | 22-New Part.1 | 23-New Part. 2 | 24-New Part. 3 | 25-New Part. 4 | 26-New Part. 5 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP4 | 9 | 12 | 4,0 | 3,0 | 1,0 | 3,5 | 4,0 | 3,0 | 4,0 | 3,0 | 2,0 | 4,0 | 6,0 | 3,0 | 4,0 | 3,0 | 4,0 | 6,0 | 4,0 | 4,0 | 4,0 | 4,0 | 4,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 77,5 |
| T4.1 | 9 | 10 | 2,0 | 1,0 | 0,0 | 2,0 | 2,0 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 33,0 |
| T4.2 | 10 | 11 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,5 | 1,0 | 3,0 | 1,0 | 1,0 | 1,0 | 1,0 | 2,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 23,5 |
| T4.3 | 10 | 12 | 1,0 | 1,0 | 0,0 | 0,5 | 1,0 | 1,0 | 1,0 | 1,0 | 0,5 | 1,0 | 2,0 | 1,0 | 1,0 | 1,0 | 1,0 | 2,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 21,0 |
| WP5 | 12 | 16 | 5,0 | 7,0 | 2,0 | 4,0 | 4,0 | 4,0 | 6,0 | 4,0 | 3,0 | 6,0 | 3,0 | 4,0 | 6,0 | 3,0 | 6,0 | 6,0 | 6,0 | 6,0 | 6,0 | 6,0 | 5,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 102,0 |
| T5.1 | 12 | 13 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 1,0 | 1,0 | 2,0 | 1,0 | 2,0 | 2,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 38,0 |
| T5.2 | 13 | 15 | 1,0 | 2,0 | 0,0 | 1,0 | 1,0 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 31,0 |
| T5.3 | 14 | 16 | 2,0 | 3,0 | 0,0 | 1,0 | 1,0 | 1,0 | 2,0 | 2,0 | 1,0 | 2,0 | 1,0 | 1,0 | 2,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 1,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 33,0 |
| WP6 | 14 | 18 | 7,0 | 5,5 | 4,0 | 5,5 | 6,0 | 8,0 | 6,0 | 8,0 | 4,0 | 8,0 | 4,0 | 8,0 | 8,0 | 5,0 | 8,0 | 8,0 | 8,0 | 8,0 | 8,0 | 8,0 | 3,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 138,0 |
| T6.1 | 14 | 15 | 2,0 | 1,0 | 1,0 | 1,0 | 1,0 | 2,0 | 1,0 | 2,0 | 1,0 | 2,0 | 1,0 | 2,0 | 2,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 0,5 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 32,5 |
| T6.2 | 14 | 16 | 1,0 | 2,0 | 2,0 | 1,0 | 1,0 | 2,0 | 1,0 | 1,0 | 0,5 | 1,0 | 0,5 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,5 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 22,5 |
| T6.3 | 15 | 17 | 1,0 | 1,0 | 0,0 | 0,5 | 1,0 | 1,0 | 1,0 | 2,0 | 1,0 | 2,0 | 1,0 | 2,0 | 2,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 0,5 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 29,0 |
| T6.4 | 15 | 18 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,5 | 1,0 | 0,5 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,5 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 19,5 |
| T6.5 | 16 | 18 | 2,0 | 0,5 | 0,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 1,0 | 2,0 | 1,0 | 2,0 | 2,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 1,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 34,5 |
| WP7 | 2 | 36 | 9,0 | 0,7 | 1,2 | 7,5 | 3,5 | 4,5 | 4,5 | 6,5 | 3,5 | 6,5 | 2,5 | 5,5 | 5,5 | 5,5 | 6,5 | 6,5 | 6,5 | 6,5 | 6,5 | 5,5 | 1,5 | 3,2 | 3,2 | 3,2 | 3,2 | 3,2 | 121,9 |
| T7.1 | 2 | 36 | 2,0 | 0,5 | 0,0 | 2,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 2,0 | 1,0 | 1,0 | 1,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 2,0 | 0,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 32,5 |
| T7.2 | 4 | 36 | 3,0 | 0,0 | 0,0 | 2,0 | 1,0 | 1,0 | 1,0 | 2,0 | 1,0 | 1,0 | 0,5 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 24,5 |
| T7.3 | 6 | 36 | 3,0 | 0,0 | 1,0 | 3,0 | 1,0 | 2,0 | 2,0 | 3,0 | 1,0 | 3,0 | 1,0 | 3,0 | 3,0 | 3,0 | 3,0 | 3,0 | 3,0 | 3,0 | 3,0 | 2,0 | 0,5 | 1,5 | 1,5 | 1,5 | 1,5 | 1,5 | 54,0 |
| T6.6 | 17 | 36 | 1,0 | 0,2 | 0,2 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 0,0 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 0,5 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 10,9 |
| WP9 | 18 | 24 | 4,0 | 1,0 | 2,0 | 4,0 | 4,0 | 3,0 | 5,0 | 4,0 | 3,0 | 5,0 | 3,0 | 3,0 | 5,0 | 4,0 | 4,0 | 4,0 | 5,0 | 5,0 | 5,0 | 5,0 | 2,0 | 5,0 | 5,0 | 5,0 | 5,0 | 5,0 | 105,0 |
| WP10 | 24 | 30 | 4,0 | 1,0 | 2,0 | 4,0 | 4,0 | 3,0 | 5,0 | 4,0 | 3,0 | 5,0 | 3,0 | 3,0 | 5,0 | 4,0 | 4,0 | 4,0 | 5,0 | 5,0 | 5,0 | 5,0 | 2,0 | 5,0 | 5,0 | 5,0 | 5,0 | 5,0 | 105,0 |
| WP11 | 30 | 36 | 4,0 | 0,3 | 1,0 | 4,0 | 4,0 | 3,0 | 5,0 | 4,0 | 3,0 | 5,0 | 3,0 | 3,0 | 5,0 | 4,0 | 4,0 | 4,0 | 5,0 | 5,0 | 5,0 | 5,0 | 2,0 | 5,0 | 5,0 | 5,0 | 5,0 | 5,0 | 103,3 |
|  |  |  | 51,0 | 26,0 | 17,2 | 45,5 | 45,5 | 36,0 | 47,5 | 45,5 | 29,0 | 54,0 | 29,0 | 38,5 | 53,0 | 37,0 | 47,5 | 53,5 | 57,5 | 50,5 | 53,5 | 51,5 | 25,7 | 18,2 | 18,2 | 18,2 | 18,2 | 18,2 | 985,4 |

### TRAINING ACTIVITIES

| ID | Start month | End month | 1-Regione Toscana | 2-LRE | 3-UOR | 4-ICIE | 5-EBS | 6-ULP | 7-TERRA | 8-PLATO CORK | 9-ICRI | 10-SSI | 11-SUC | 12-RKK | 13-PWR | 14-BYWEB | 15-IST | 16-IPA | 17-UDJG | 18-ADC | 19-BIC GROUP | 20-CSV | 21-IJS | 22-New Part. 1 | 23-New Part. 2 | 24-New Part 3 | 25-New Part 4 | 26-New Part 5 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP8 | 14 | 36 | 4,0 | 2,0 | 0,0 | 3,0 | 3,0 | 2,0 | 3,0 | 3,0 | 0,0 | 3,0 | 0,0 | 3,0 | 3,0 | 5,0 | 2,0 | 2,0 | 2,0 | 3,0 | 3,0 | 3,0 | 2,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 56,0 |
| T8.1 | 14 | 24 | 2,0 | 2,0 | 0,0 | 2,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,0 | 1,0 | 0,0 | 1,0 | 1,0 | 3,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 22,0 |
| T8.2 | 16 | 36 | 2,0 | 0,0 | 0,0 | 1,0 | 2,0 | 1,0 | 2,0 | 2,0 | 0,0 | 2,0 | 0,0 | 2,0 | 2,0 | 2,0 | 1,0 | 1,0 | 1,0 | 2,0 | 2,0 | 2,0 | 2,0 | 1,0 | 1,0 | 1,0 | 1,0 | 1,0 | 34,0 |

| TOTAL ACTIVITIES | 70,0 | 33,0 | 20,2 | 53,5 | 48,7 | 38,2 | 50,7 | 48,7 | 29,2 | 57,2 | 29,2 | 41,7 | 56,2 | 42,5 | 49,7 | 55,7 | 67,5 | 53,7 | 56,7 | 54,7 | 27,9 | 19,2 | 19,2 | 19,2 | 19,2 | 19,2 | 1080,9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

# Detailed implementation plan – first 18 months

## Technical content & framework structure of dissemination

The Mental Change project will involve clearly targeted dissemination and valorisation strategies, addressing not only scientific audiences, but also policy-makers and the general public. Therefore the Mental Change working plan will be focused on the development of an e.Editor co-organisation that will be the basic practical element of the framework-structure of the dissemination. A Knowledge Economy Portal (KEP) will work as well as a wireless framework structure where the Mental Change Consortium will organise a system of on line publications. In this way the information received will be assembled in appropriated formats by the Education Research Wireless Laboratory (ERWL). That will also be organised by the partners clustering a Virtual Editorial Staff. The KEP editions and dissemination on Knowledge Economy Dynamics will work for facilitating the understanding of Citizen by diffusing on line advanced information, which will be developed as well as an educational permanent training system, oriented to a wide range of subjects on Knowledge Economy. Hence the multi-objectives endeavor will be organized through interactive net-learning sequences of hyper-texts and e.book that can be downloaded from the KEP. Therefore the KEP will follow the evolution of the European Knowledge dynamics issues related to the working plan of the Mental Change development. Thus, the diffusion and the dissemination on line of the Mental Change activities will exploit an INDUCATOR action (i.e. incubator plus educator) based on the methodology of sharing knowledge. This approach for the construction and utilization of the KEP is important for helping the conceptual innovation growing up an extended Inducator net-.learning community. The Inducator meaning is equivalent to incubator for improving a networking learning interactive plan and delineate a strategy very useful for promoting innovative Knowledge Management (KM) entrepreneurship’s skills for strengthening University and Enterprises business relationships, and diffusing the best practices of those results to European Citizen. The Inducator is a new creative strategy for avoiding the failings of typical methods of traditional distance teaching finalised to the transfer of standardised knowledge. The innovation of the Inducator sharing knowledge based system consists in programming an effective answered interaction inside of a networking learning community, in order to develop on demand educational replies and improving a collective know-how for a wide net.Learning managing, finalised to prepare innovative web-educational materials. Therefore the focus of the Mental Change organisational program will be centred in the R&D collaborative structure of the virtual international ERWL (Fig. 1) organised as well as an innovative e.Editor that will grow up an user centred strategy of innovative Knowledge Management design, in the contest of the development of European Knowledge Economy. Fig.1 draws the EWRL and its relation with the KNOWLEDGE ECONOMY PORTAL, which will contain a regularly updated set of articles describing selected themes methods and specific topics.

Fig.1: M-CHANGE architecture

The organisation - functions of ERWL described in the figure (Fig. 2) are subdivided in four basic elements of the Mental Change Inducator dissemination strategy by ICT tools:

A) Inducator networked function co-organized by partners for setting together cognitive Knowledge Economy priority problems.

B) e.Editor networked function for setting up the tools and editing the Knowledge Management net-learning materials.

C) Front Office function co-organised by partners for setting advisors and stakeholders Meetings with SMEs entrepreneurs and developing innovative networking business model, collaborative marketing and commercial plans.

D) Knowledge Economy Portal is a function co-organized by partners for setting the ICT-based interactive implementation & dissemination process.

Fig.2: E.R.W.L. structure

## Activities of the Mental Change project

The M-Change program in the will be developed throughout the following issues:

1) Identification of the networking Regional structures and processes that enable to develop an organizational Knowledge dynamics leading to the conversion of intangible grouping assets into socio-economic developmental value, oriented to improve European Knowledge Economy in a world wide competitive environment. The nodal question of this R&D activity will concerns three fundamental aspects of Citizen advanced understanding of issues regarding the  Technological and Financial Change in the deployment of knowledge driven economy through an analysis around the growing relationship between ICT and Financial synergic processes of ‘Organizational Capital”.

2) Contribute to overcoming the lack of an Innovative Knowledge Management in relation to the advancing patterns of the economic change of management of the intangible networking organisational assets in a knowledge driven economy. M-Change program will favour the organisation of clustering of stakeholders enjoining the M-Change project to support possible joint/common foresight activities in the following developmental priority areas:

- Research addressing the major societal and economic challenges of the Knowledge-driven Economy, especially regarding the large branch of priorities in RDT innovation that will be especially addressed to favour University SMEs integration. (e.g. improving start up, spin of, spin out, Business to Business Agency etc.)

- Development of Coordination/Cooperation Objectives of the M-Change project activities may also lead to fostering ERA strengthening by combining business relationships between RTD Centres and SMEs aiming to contributing to the general goal: Europe becoming the most competitive and dynamic knowledge-based economy until 2010

- To follow Knowledge Dynamics of the above general dimension of the M-Change planning, the principal actions of the project activities will be subdivided in short, medium and long term actions.

### Short-Term Actions

Achievable within the first 18 months, short terms actions consist of measurable and verifiable form through the Work Packages described in section B8.3

These actions will intend to stimulate partnership between the State, the private sector and civil society in order to secure the involvement of more social stakeholders in management. Improving Citizen Information

Identifying and sustaining territorial pilot programmes in a way that they will encourage grassroots communities to design community coordinated M-Change actions; those activities will be devoted to:

- working to ameliorate the information system between European and National policies and to contribute to avoid short term duplication of similar key initiatives

- optimising co-operative infrastructure/equipment investments for understanding Knowledge dynamics

- preparation of mutual opening of facilities and ICT laboratories favouring the Knowledge Economy R&D

- co-ordinating actions to avoid cultural and/or digital barriers for researchers and citizens understanding

- stimulating cultural and scientific innovation and economic growth through Knowledge management innovative strategies

### B Medium-Term Actions

They represent the subsequent development of the 18 months to 3 years of the M-CHANGE. Below the main directions continuing the activities in the frame of the activities of the first 18 months:

- helping the creation of sustainable growing of new skilled intellectual knowledge management for the SMEs inclusion into a strategy of collaborative European Knowledge Economy;

- favouring the reorganisation of work, from low skill level of the labour-intensive sectors to a more productive knowledge team - e.Work management more addressed to the networking Knowledge Economy European development.

- supporting the increase of the co-ordination/co-operation of National/Regional/ European RDT programs.

- exploring and taking in advanced account the ethical, environmental and gender issues of the future Knowledge society in relation to the Implications of European integration and enlargement for governance and new advances in citizen direct participation on e. Governmental activities.

### Long term actions

Implementation and Follow-Up Dynamic strategies (project’s sustainability after ending the EU funding): subsequent development for the longer-term evaluation of citizen participation in European governance innovation.

The M-CHANGE Consortium would like to realize a proper sustainability after the end of the EC funding, becoming a co-operative trans-national Agency for training and competence building in Knowledge Management co-organization,able to explore critical success factors for enabling Intelligent ICT to be used as well as a fundamental tool for redesigning co-ordination process and to support a durable co-operation for the European e.Governance in all the fields of RDT Driven Economy. In the last phase of the three years program a Strategic Knowledge Management Action Plan and a joint database of experts/advisors and committees boards, will be provided and implemented, utilizing the latest trends of intelligent techniques and semantic software and creative ideas, that will be included in a Knowledge Economy Portal.

At that stage, the Knowledge Economy Portal will be optimized to contain corporate case studies and special cases based reports, new reasoning reports; also will be organized a mutual learning on demand system with a special attention to the field of business & RDT integration process, to benefit mutual understanding of the re-engineering procedures of RDT/SMEs integration, which will be able to satisfy the users requirements.

The Expanded Project Focus of this phase will reply to some asking questions probably remained open in the knowledge dynamics developmental approach of the M-Change project, as well the following:

How sustainable are the various models of citizen centred governance? How can they be made more inclusive of ‘hard to reach’ world wide R&D Interested groups? How successful they are in developing terms of European Knowledge Economy engagement, which result in them having real influence on the advancement of Regional government? What do these Regional initiatives mean at trans- National level for citizen that can be able to contribute to a delocalized e.Governance and, in particular how can we learn from the positive response to engaging young and older people all over the world?

For these reasoning questions, the future implementation and follow up dynamic strategies will be decided by means of a profound assessment that will be made in reference to the performance indicators provided for in the matrix of actions and will be useful not only in measuring the progress made, but also in identifying shortcomings and the corrective measures to be taken to reinforce the sustainability of knowledge dynamics strategy in relation to improving world wide relationship on knowledge Economy, and aiming to give a contribute on bettering the European Leadership in the use of ICT Infrastructure for sharing different cultures and values, skills and competencies, processes and systems improving the World Wide Knowledge Society.

Finally, the prevalent relevance of the Mental Change project it will meant to develop coordination activities based on the integration between University and Centres of Research with the SMEs’ innovation, into an higher level of agreement in a wide European ICT framework improving network management roles and responsibilities, common understanding and standardized methods for reward and evaluation procedures.

### Cluster activities

1st Cluster

1) Multidisciplinary Studies on the development of models for an efficient optimization of strategic alliances and model predictive control within strengthening alliances among Governmental Local Institution SME’S and Universities and other Public or Private centres of research & development, aiming to work in partnership for the integration of local models of development and macro economical optimization.

2) Research on different levels on e-Governance in Europe, on economic and social regulation within Europe; analysis of the role of regional public authorities in the partnership’s countries on economic and social development within Europe including the evolution of e.work systems; and the dynamics of European integration and enlargement.

During these studies and researchers, will be developed seven tasks and actions as well as: dissemination of intermediate reports towards improved management of societal change; diffusion of new perspectives and realization of training courses of Net-learning strategies in a changing society and social cohesion obtained by means of a lifelong competence-building for improving intellectual employment in e.Working co-operative systems; diffusion of Information on e.Governance advancement, citizenship understanding on the dynamics of the European integration and EU enlargement in the development of the global competition on Knowledge Society.

### 2nd Cluster

1) Multidisciplinary Studies of new development models fostering growth and employment oriented to overcoming the lack of an Creative Knowledge Management, to ameliorate the SMEs’ quality of production and processes and to exploit results through the preparation of a mutual opening e.Learning on demand platforms and methods to favour a common understanding of RTD strategies for improving the European Development of Knowledge Economy.

2) Research into new sustainable models to foster growth, job creation, equal opportunities, reduction of inequities - exploring and taking in account ethical and gender issues and favoring the improvement of quality of life, helping the creation of sustainable growing by the training of skilled staffs and helping the reorganization of work, from low skill level of the labour-intensive sectors to a more productive knowledge team-e.Work management.

During these studies and researchers the Mental Change programme is intended to offer and disseminate a series of specific tasks and activities, focused on the following issue: how the Knowledge Economy development should be carried out preparing a durable cooperation activity favoring the development of clustering for Regional projects and for possible joint/common foresight activities in the following developmental priority areas:

- coordinating actions oriented to avoid cultural and/or digital barriers for researchers and citizens;

- stimulating cultural and scientific innovation and economic growth through Knowledge management innovative strategies;

- collaborating with other social and policy actors for improving actions addressing the major societal and economic challenges of Knowledge driven Economy for instance: dissemination on Regional research innovations about developmental priorities on agro-food quality and food traceability process all along the production chains, food frauds prevention; impact of food on health and so on; multifunctional materials, applied to new products and processes etc. and to all other RTD fields and all scientific and technological advancements especially addressed to favour University SMEs’ integration (e.g improving start up, spin of, spin out, Business to Business Agency, and so on) and all other factors aiming to contributing to the general goal: Europe becoming the most competitive and dynamic knowledge-based economy until 2010.

### 3rd Cluster

1) Multidisciplinary Studies oriented to further optimise the M-CHANGE project for favouring co-ordinated response of Regional Groupings towards common European challenge’s development by growing up a conscious understanding of citizen and implementing human and social policies in Europe.

2) Comparative research across Europe of the possible end sustainable relevance of M-CHANGE programme focused about the strategic contribution to realise supporting long-term perspectives in European research and developmental policies, addressed to improve territorial and organisational co-operative configurations affecting the potential for innovation and economic development by growing up a conscious understanding of citizen and implementing human and social in Europe.

During these studies and researchers the Mental Change programme will support effective contributions to the specific working planning activities addressed on various co-ordination and supporting actions oriented to realise a large market of Priority-Driven Research that can be realised throughout the effort developed for achieving a creative change of strategic knowledge management co-organisation.

### Project milestones

In order to make the progress of the project work measurable at a regular pace, it was decided to position milestones on a six-month basis:

- Milestone M1 after 6 months. It corresponds to the project stage surveys and analysis on existing data and ERWL laboratory design and development have been carried. The project Web site is also set up, preliminary dissemination plans are issued and first event realised.

- Milestone M2 after 12 months. It corresponds to the project stage when the dynamical indicators have been set up and the GAP analysis can start.

- Milestone M3 after 18 months. It corresponds to the project stage when the conceptual and organisational model is ready a second set of dissemination actions have been performed. After this milestone, the searching of new partners who can join the M-CHANGE project can start.

## Detailed work description

- This section is devoted to present details on work packages and deliverables. For the sake of readability, the partners are identified by their identification numbers (according to form A3), as shown in the following table:

| - ID | - Partner short name | - Country |
| --- | --- | --- |
| - 1 | Regione Toscana | - Italy |
| - 2 | LRE - EgoCreanet | - Italy |
| - 3 | UOR | - Italy |
| - 4 | ICIE | - Italy |
| - 5 | EBS | - Estonia |
| - 6 | ULP | - France |
| - 7 | TERRA | - Hungary |
| - 8 | PLATO CORK | - Ireland |
| - 9 | ICRI | - Ireland |
| - 10 | SSI | - Lithuania |
| - 11 | SUC | - Norway |
| - 12 | RKK | - Norway |
| - 13 | PWR | - Poland |
| - 14 | BYWEB | - Portugal |
| - 15 | IST | - Portugal |
| - 16 | IPA | - Romania |
| - 17 | UDJG | - Romania |
| - 18 | ADC | - Romania |
| - 19 | BIC GROUP | - Slovakia |
| - 20 | CSV | - Slovenia |
| - 21 | IJS | - Slovenia |

- Workpackage list (18 month plan)

| - Work-package No | - Workpackage title | - Lead contractor No | - Person-months | - Start month | - End month | - Deliv-erable No |
| --- | --- | --- | --- | --- | --- | --- |
| - WP0 | - Project Management | - 1 | - 20,3 | - 1 | - 18 | - D01; D17 + Progress Reports |
| - WP1 | - Platforms for knowledge dynamics | - 1 | - 72,1 | - 1 | - 3 | - D02 |
| - WP2 | - Shared methodology for knowledge management issue’s approach | - 17 | - 79,6 | - 3 | - 6 | - D03 |
| - WP3 | - Learning and competence building for network economy: Investigation and Demonstration | - 8 | - 81 | - 6 | - 10 | - D06 |
| - WP4 | - Set up Dynamical Indicators for the knowledge economy | - 11 | - 77,5 | - 9 | - 12 | - D07 |
| - WP5 | - GAP Analysis (SWOT) | - 2 | - 102 | - 12 | - 16 | - D09; D10 |
| - WP6 | - Conceptual and organisational model for a centred e-Governmental European strategy | - 6 | - 138 | - 14 | - 18 | - D12; D13 |
| - WP7 | - Dissemination and exploitation | - 1 | - 51,9 | - 2 | - 18 | - D04; D05; D08; D14; D16 |
| - WP8 | - Training for net-learning | - 14 | - 11 | - 14 | - 18 | - D11; D15 |
|  |  |  | - 633,4 |  |  |  |

- Deliverables list (18 month plan)

| - Deliverable No | - Deliverable title | - Delivery date | - Nature | - Dissemination level |
| --- | --- | --- | --- | --- |
| - D01 | - Project Management tool and Quality assurance plan | - 4 | - R | - RE |
| - D02 | - M-CHANGE platforms | - 4 | - R | - CO |
| - D03 | - Knowledge dynamics understanding | - 7 | - R | - CO |
| - D04 | - Dissemination and exploitation plans | - 7 | - R | - CO |
| - D05 | - Proceedings. International Congress Knowledge Dynamics and Mental Change | - 7 | - R | - PU |
| - D06 | - Learning organisations | - 13 | - R | - CO |
| - D07 | - M-Change hyper-text | - 13 | - R | - CO |
| - D08 | - First report on dissemination activities | - 14 | - R | - PU |
| - D09 | - Gap Analysis (SWOT Analysis | - 16 | - R | - CO |
| - D10 | - Booklets and Guides for the Net-learning Inducator ? | - 16 | - R | - CO |
| - D11 | - Refined training material | - 16 | - R | - CO |
| - D12 | - Conceptual and organizational model for a citizen-centred e-governmental European strategy | - 18 | - R | - CO |
| - D13 | - Knowledge-based economy dynamics indicators | - 18 | - R | - CO |
| - D14 | - Proceedings. International Congress Human, Intellectual and Social Capital key components of value in a European knowledge-based economy | - 18 | - R | - PU |
| - D15 | - Report on training activities | - 18 | - R | - PP |
| - D16 | - First exploitation agreement | - 18 | - R | - CO |
| - D17 | - Assessment of project results | - 18 | - R | - CO |

Work breakdown and timing (Gantt chart – first 18 months)

- The attached Gantt chart shows the planned timing of work packages and their component tasks.

Interdependencies of tasks (PERT diagram – first 18 months)

- The attached PERT diagram shows the interdependencies between work plan tasks.

## M-Change Gantt chart (first 18 months)

## M-Change Pert Diagram (first 18 months)

- Work package 0 – Project Management (18 month plan)

| - Work package number | - WP0 |  |  | - Start date or starting event: |  |  |  |  |  |  | - month 1 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Participant id |  | - 1 | - 2 |  | - 3 | - 4 | - 5 | - 6 | - 7 | - 8 |  | - 9 | - 10 | - 11 |  |
| - Person-months per participant: |  | - 8 | - 2,5 |  | - 1,5 | - 2,5 | - 0,1 | - 0,1 | - 0,1 | - 0,1 |  | - 0,1 | - 0,1 | - 0,1 |  |
| - Participant id |  | - 12 | - 13 |  | - 14 | - 15 | - 16 | - 17 | - 18 | - 19 |  | - 20 | - 21 | - - |  |
| - Person-months per participant: |  | - 0,1 | - 0,1 |  | - 0,3 | - 0,1 | - 0,1 | - 4,0 | - 0,1 | - 0,1 |  | - 0,1 | - 0,1 | - - |  |

- Objectives - The WP0 Project Management aims at ensuring that the co-ordination and work between interacting parties and the Commission proceeds smoothly, at the administrative, organisational and technical levels. It will deal with detailed planning and objectives for the long term period – 3-year projects’ Handbook; co-ordination of the projects and network activities, in order to assure the achievement in 100% and under previewed quality requirements of the WPs activities and outcomes; establishment and follow-up of special procedures for Quality Management and Assurance; assuring correct financial activities, according to the EU rules; assuring the project development sustainability after the end of funding.

- Description of work - The work ito be carried out in the following tasks that covers the whole project duration: T01 – Management of the project. This task intends to ensure a correct execution of work and maintain all the relationships within and outside the Consortium. In particular, it must: establish the management organisation, define project policies and procedures; organise and prepare plenary internal meetings and the foreseen review meetings; create and maintain the project office; monitor the work activities and, if needed, re-schedule them; prepare the progress reports and collect other due documentation. All partners will participate in this task and the project co-ordinator will take the overall responsibility. The work is divided into two sub activities: Administrative and technical management. The administrative management includes general responsibility for the organisation, planning and control of the project; contacts with the project officer; formulation of propositions for possible modifications of the work plan; monitoring of the project cash flow; management of conflicts by application of the foreseen procedures and especially, a constant co-operation with the Partner Board (PB). The technical management includes technical co-ordination and assistance of the Work Package leaders; initiatives to undertake certain specific political initiatives, to propose technical solutions and to fine tune the technical orientation whenever necessary; control of technical and policy build up activities carried out in specific tasks and subtasks; proposition to the PB of technical modifications and reallocation of resources according to the aims of the project as well as reporting to the PB about deviations from the technical plan; constant co-operation with the administrative management. The starting point is the organisation of the M-Change Kick-off 2 days meeting to be held in Florence (Italy) at the venue of the Congress Hall of Regione Toscana. It aims at defining the operational details for the first 6 months and signing the official documents. After about six-seven months the project starting a second 1 day plenary meeting will be organised in Craiova (Romania). It aims at evaluating the of the project management strategy, analyzing the structuring integration effect into a coherent set of strategic elements of the M-Change e.Working and financial co-organisation, (e.g. vertical integration of stakeholders; horizontal integration of multidisciplinary activities; activity integration across the full research spectrum and promotion of demonstration activities). The first International congress will be held in successive days. A third consortium meeting is foreseen approximately at month 12. It aims at verifying the consortium level advancements and financial and administrative management; planning proposals for competitive calls for the enlargement of the M-Change Consortium; revising the previous long term planning and objectives for the 3-year period; criteria and evaluation for opening of a new call at the end of the 18 months, aiming to implement the partnership especially coming from SMEs and Industry. At month 18 a new partnership’s recognition (M-Change fourth Consortium Meeting - 2 days) will be organised by the responsibility of the International Steering Committee of the M-Change Project that would like to describe also the Guideline and the conditions to participate to the open call for implementing the partnership of the M-Change Proposal. T0.2 – Assessment of project results. This task provides an independent evaluation of the project progress and results with respect to the Technical Annex. The work is in charge of a person, the Project Evaluator, who is not involved in project execution.

- Deliverables - Progress Reports (1 every six month) and Annual Reports - D01 – Project Management tool and Quality assurance plan (web based); - Final report (at the end of the project) and also all administrative documents required by the Commission, internal-working documents etc. - D17 – Assessment of project results. The document qualifies the project objectives with respect to key evaluation criteria agreed among the partners, maps the objectives into operational goals and identifies how to achieve them, establishes measurement criteria and parameters of project progress and success.

- Milestones and expected result - The result expected from workpackage WP0 is managing the project activities so as to ensure the respect of the time schedule and the quality of the intermediate and final project outcomes. The early development and use of a Quality Assurance Plan will be the instrument that will support the management activities.

- Work package 1 Platforms for Knowledge Dynamics

- (18 month plan)

| - Work package number | - WP1 |  |  | - Start date or starting event: |  |  |  |  |  |  | - month 1 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Participant id |  | - 1 | - 2 |  | - 3 | - 4 | - 5 | - 6 | - 7 | - 8 |  | - 9 | - 10 | - 11 |  |
| - Person-months per participant: |  | - 6,0 | - 3,0 |  | - 2,0 | - 5,0 | - 5,0 | - 2,5 | - 4,0 | - 3,0 |  | - 2,0 | - 3,5 | - 1,5 |  |
| - Participant id |  | - 12 | - 13 |  | - 14 | - 15 | - 16 | - 17 | - 18 | - 19 |  | - 20 | - 21 |  |  |
| - Person-months per participant: |  | - 3,0 | - 3,5 |  | - 2,5 | - 3,0 | - 4,0 | - 6,0 | - 4,0 | - 4,0 |  | - 4,0 | - 0,6 |  |  |

- Objectives Development of EU Platform for knowledge dynamics and promotion of regional platforms open to stakeholders. Strengthening the organisation of clustering of stakeholders enjoining the M-Change project to support possible joint/common foresight activities in the Research addressing the major societal and economic challenges of Knowledge driven Economy.

- Description of work Developing and experimenting with a system of Forum and Electronic Conferences for exchanging data and sharing knowledge to manage the M-Change project and the first approach for the realisation of the structure of the Knowledge Economy Portal. T1.1 – Analysis of existing relevant data. Identifying and assessing the existing information at Regional, National and European levels; decision on organisation of pools in the project’s regions, results’ interpretation T1.2- Assessment of the state-of-the-art. Achievement and / or revision of existing questionnaires/research instruments to assess the state-of-the-art of the partnership between the State, the University, the private productive sector (especially SMEs) and civil society; T1.3 – Harmonisation of knowledge. Generation of an harmonisation of knowledge required by partners to implement the priority themes on knowledge dynamics and citizen understanding of change in mentality between Industrial Society and Knowledge Society.

- Deliverables D02 –M-CHANGE platforms. It aims at sharing knowledge and Knowledge Economy Portal co-organisation and training and dissemination activities proposals in a collaborative organisation.

- Milestones and expected result The report will emphasise the Intellectual Job Creation change dimension by the impact of technological change in the European strategy of Knowledge Economy and the need to develop a system of training for overcoming skill shortage in the long term prospects of the development of the European Knowledge Society. It will draw the specific activities to be developed by each RIG and partner, in order to fulfil the project’s tasks based on the specific conditions and the common M-Change approach.

- Work package 2 Shared Methodology for Knowledge Management Issues Approach

- (18 month plan)

| - Work package number | - WP2 |  |  | - Start date or starting event: |  |  |  |  |  |  | - month 3 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Participant id |  | - 1 | - 2 |  | - 3 | - 4 | - 5 | - 6 | - 7 | - 8 |  | - 9 | - 10 | - 11 |  |
| - Person-months per participant: |  | - 3,0 | - 3,0 |  | - 1,0 | - 5,0 | - 5,0 | - 2,5 | - 5,0 | - 3,0 |  | - 3,0 | - 6,0 | - 1,5 |  |
| - Participant id |  | - 12 | - 13 |  | - 14 | - 15 | - 16 | - 17 | - 18 | - 19 |  | - 20 | - 21 |  |  |
| - Person-months per participant: |  | - 3,0 | - 6,0 |  | - 3,0 | - 5,0 | - 5,0 | - 7,0 | - 3,0 | - 5,0 |  | - 4,0 | - 0,6 |  |  |

- Objectives Development of a shared methodology for driving the regional economic competitiveness by co-organising the innovative knowledge dynamics information on Knowledge management issues and permanent training activities. This methodology will be used for improving actions oriented to stimulate partnership between the State and the private sector and civil society in order to secure the involvement of more social stakeholders in the M-Change project management.

- Description of work T2.1 - Education Research Wireless Laboratory design. Integrating the critical mass of activities and resources needed to develop R&D innovation and the diffusion of Science & Business best practices, through the M.Change Platform. Operational agreement for designing the co-operative “Education Research Wireless Laboratory”. T2.2 – ERWL development and implementation. Increasing the implementation of “Knowledge Dynamics” of the future Knowledge Society by means of some demonstration of the usefulness of the M-Change ICT framework for all actors and relevant stakeholders (e.g. definitive structure of the Knowledge Economy Portal, Global-technology, Newsletter, e.Magazine, annotated on line Bibliography). The task deals also with the operational agreement for developing the co-operative Education Research Wireless Laboratory. T2.3 - Innovation strategies and complexity management. Knowledge management concepts, methods and practice; Knowledge dynamics and organisational design for SMEs / University, aggregation oriented to favour capital investment attraction.

- Deliverables D03 - Knowledge dynamics understanding. Study report on the implementation of “knowledge dynamics understanding” in a long term prospective of CITIZEN ( especially policy makers) and for Knowledge Management innovation (especially foe SME’s management) located in the set of the partnership’s Regions.

- Milestones and expected result The report will emphasise the methodological and scientific achievements for improving and measuring an qualitative regional impact of the M-Change Strategies, for developing a better understanding in each partnership’s country of contemporary “Knowledge Dynamics” especially in relation to both the target groups: a) Citizen and b) SME’s Manager and Policy Makers.

- Work package 3 Learning and Competence Building for Network Economy: Investigation and Demonstration (18 month plan)

| - Work package number | - WP3 |  |  | - Start date or starting event: |  |  |  |  |  |  | - month 6 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Participant id |  | - 1 | - 2 |  | - 3 | - 4 | - 5 | - 6 | - 7 | - 8 |  | - 9 | - 10 | - 11 |  |
| - Person-months per participant: |  | - 5,0 | - 1,5 |  | - 1,0 | - 3,0 | - 6,0 | - 2,5 | - 3,0 | - 6,0 |  | - 2,5 | - 5,0 | - 1,5 |  |
| - Participant id |  | - 12 | - 13 |  | - 14 | - 15 | - 16 | - 17 | - 18 | - 19 |  | - 20 | - 21 |  |  |
| - Person-months per participant: |  | - 3,0 | - 5,0 |  | - 3,0 | - 3,0 | - 6,0 | - 5,0 | - 4,0 | - 5,0 |  | - 5,0 | - 5,0 |  |  |

- Objectives Investigate learning and competence building for network economy organised in multidisciplinary teams of NET-learning (or Mutual Learning) organisations. Assessment and design of the requested conditions for preparation of mutual opening of facilities and ICT laboratories favouring the Knowledge Economy R&D: co-ordinating actions to avoid cultural and/or digital barriers for researchers and citizens understanding; stimulating cultural and scientific innovation and economic growth through the realisation of courses in Knowledge management innovative strategies especially oriented to SMEs international networking activities. Preparation and start of the demonstration phase.

- Description of work T3.1 – Building the strategic drivers of M-CHANGE approach. It aims at structuring integration effects into a coherent set of strategic elements of the M-Change e.Working and financial co-organisation, e.g. vertical integration of stakeholders; horizontal integration of multidisciplinary activities; activity integration from across the full research spectrum and promotion of training activities. T3.2 – Promoting developmental dynamics. Driven research and open discussion on Learning and competence building for network economy with policy makers and researchers at level of regions, social groups, institution and organisations. Knowledge sharing and dialogue methodology as major deliverable of the e.Governamental M-Change project development; perspectives and primary results T3.3 – Demonstrate the M-CHANGE approach. The demonstrating activities on Learning and competence building for network economy in the partners Regions or Countries for improving University /SMEs forms of integration are addressed to the major socio-economic needs of citizen understanding of developmental dynamics to the European Knowledge Economy.

- Deliverables D06 –Learning organisations. Study report on learning and competence building of the CITIZEN (mainly policy makers and SME managers) on issues related to the competitiveness of Regional Development European Knowledge Economy Strategy.

- Milestones and expected result The report and the activities carried out in this period will emphasise the methodological and educational achievements, the co-operative and comparative multidisciplinary NET- Learning in competence building innovation.

- Work package 4 – Set up Dynamical Indicators for the Knowledge Economy

- (18 month plan)

| - Work package number | - WP4 |  |  | - Start date or starting event: |  |  |  |  |  |  | - month 9 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Participant id |  | - 1 | - 2 |  | - 3 | - 4 | - 5 | - 6 | - 7 | - 8 |  | - 9 | - 10 | - 11 |  |
| - Person-months per participant: |  | - 4,0 | - 3,0 |  | - 1,0 | - 3,5 | - 4,0 | - 3,0 | - 4,0 | - 3,0 |  | - 2,0 | - 4,0 | - 6,0 |  |
| - Participant id |  | - 12 | - 13 |  | - 14 | - 15 | - 16 | - 17 | - 18 | - 19 |  | - 20 | - 21 |  |  |
| - Person-months per participant: |  | - 3,0 | - 4,0 |  | - 3,0 | - 4,0 | - 6,0 | - 4,0 | - 4,0 | - 4,0 |  | - 4,0 | - 4,0 |  |  |

- Objectives The WP4 aims at establishing the dynamical indicators to measure and understand the advances of Knowledge economy by means of the public-private e.Governmental partnerships; encouraging the establishment and promoting Regional or National Mirrors of the KNOWLEDGE PORTAL in the Different languages of the Country partners on Knowledge Dynamics as appropriate; stimulating the increasing of the information exchange on experiences best practices and Regional strategies of Knowledge Economy development and discussing and monitoring; fostering synergies between different approaches, thematic issues and dynamic indicators.

- Description of work T4.1 – Survey and assessing Dynamical indicators. The task investigates and assesses the existing dynamical indicators to measure and understand the advances of Knowledge economy by means of the public-private e.Governmental partnerships. T4.2 – Introducing new/improved dynamical indicators. The task proposes new and/or improved indicators to measure and understand the advances of Knowledge economy by means of the public-private e.Governmental partnerships. T4.3 – Creation of innovation driven grouping. The task aims at stimulating the strengthening and the creation of innovation driven grouping or clusters in Research and Business networks in each participant Region; assessment of the results.

Deliverables D07 – M-Change hyper-text. Iper-text and e.Book on knowledge dynamics diffused on line on the knowledge Portal. CD-ROM and Iper-Texts on line related to the Net-learning Courses.

- Milestones and expected result Main tasks will be: to strengthening the European and the Regional policies and strategic objectives in the field of knowledge dynamics understanding trough the production and dissemination of information online organised by hyper-text and CD-ROM written for improving a permanent Education by means of the co-organisation of special Courses on line and in presence in the Country of the partners. Co-organise at the same time the communication and the interaction between researchers and policy makers and between researchers and SMEs managers and between researchers and end-users. Facilitate the accessibility to scientific results produced by the M-Change Consortium and stimulating a large involvement of all actors and stakeholders concerned about development of the Knowledge Economy at the International and Regional scale.

- Work package 5 – GAP Analysis (SWOT)

- (18 month plan)

| - Work package number | - WP5 |  |  | - Start date or starting event: |  |  |  |  |  |  | - month 12 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Participant id |  | - 1 | - 2 |  | - 3 | - 4 | - 5 | - 6 | - 7 | - 8 |  | - 9 | - 10 | - 11 |  |
| - Person-months per participant: |  | - 5,0 | - 7,0 |  | - 2,0 | - 4,0 | - 4,0 | - 4,0 | - 6,0 | - 4,0 |  | - 3,0 | - 6,0 | - 3,0 |  |
| - Participant id |  | - 12 | - 13 |  | - 14 | - 15 | - 16 | - 17 | - 18 | - 19 |  | - 20 | - 21 |  |  |
| - Person-months per participant: |  | - 4,0 | - 6,0 |  | - 3,0 | - 6,0 | - 6,0 | - 6,0 | - 6,0 | - 6,0 |  | - 6,0 | - 5,0 |  |  |

- Objectives The WP6 aims at assessing the socio-economic relevance of the M-Change project achievements in the first year based on a comparative European perspective of specific clusters of key qualification on knowledge economy advancements, organised by the partners; demonstrating the policy implications in innovation of e.Work patterns and labour market on the advancements of the European strategy of Knowledge Economy and in the Permanent Education activities targeted (investigated and demonstrated) by the M-Change Consortium on the basis of an INDUCATOR Strategy; revising the previous long term planning and objectives for the 3-year period; setting up criteria and evaluation for opening a new call at the end of the 18 months in order to improve extend the partnership especially coming from SMEs and Industry.

- Description of work T5.2 – Gap Analysis. Development of the Gap Analysis (SWOT analysis) on the research activities and best practices in the field of all themes related to the M-Change proposal. T5.2 - Co-operative and Mutual Learning Courses design. The courses are on issues related to the knowledge-based economy demands, focusing the acquisition of new skills and adaptability through life-long training in a way that will be developed an open networking approach to e.learning as well as it is required by an integration among local and national cultures and the promotion of a mutual understanding of Knowledge Society advancements between all people in Europe. T5.3 – Promoting networking activities. It aims at assisting innovation and enterprise stimulation networking programmes. Regional Congress and local workshops will be organised together with short term meetings of managers supporting them with the knowledge of “science & business” opportunities emerging at European and Trans European levels.

- Deliverables - D09 - Gap Analysis (SWOT Analysis). Analysis on research activities and best practices in the field of all themes related to the M-Change proposal. Booklets and Guides for the Net-learning Inducator- Courses: introduction, contents and basical information of participation. - D10 - Booklets and Guides for the Net-learning Inducator. Planning of courses: introduction, contents and basic information of participation.

- Milestones and expected result The main goal is to improve the networking mutual permanent Education in the Inducator strategy approach; this should better respond on global challenges of forming Knowledge Economy skills in providing necessary background for successful people living in this new knowledge based configuration: forming base knowledge and motivation for constant improvement of knowledge and skills and setting up of life-long learning initiatives.

- Work package 6 – Conceptual and Organisational Model for a Centred e-Governmental European Strategy (18 month plan)

| - Work package number | - WP6 |  |  | - Start date or starting event: |  |  |  |  |  |  | - month 14 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Participant id |  | - 1 | - 2 |  | - 3 | - 4 | - 5 | - 6 | - 7 | - 8 |  | - 9 | - 10 | - 11 |  |
| - Person-months per participant: |  | - 7,0 | - 5,5 |  | - 4,0 | - 5,5 | - 6,0 | - 8,0 | - 6,0 | - 8,0 |  | - 4,0 | - 8,0 | - 4,0 |  |
| - Participant id |  | - 12 | - 13 |  | - 14 | - 15 | - 16 | - 17 | - 18 | - 19 |  | - 20 | - 21 |  |  |
| - Person-months per participant: |  | - 8,0 | - 8,0 |  | - 5,0 | - 8,0 | - 8,0 | - 8,0 | - 8,0 | - 8,0 |  | - 8,0 | - 3,0 |  |  |

- Objectives The WP6 starts the formulation of an enhanced conceptual and organisational model for a citizen centred e-Governmental European strategy, founded on supporting participatory democracy, that will offer at the European Citizen the opportunity to access and to share information by means of an interactive e.Editorial system, both within European Regions and across Regional and National borders. The aims are to: - Implement a verifiable additional value at the European Level on the Regional contributions to development of Knowledge Society by means of new experience and best practices on value based management; - Provide a systematic exchange of information and best practices concerning significant social and economic changes that are being driven by the European Knowledge Economy; - Favour the knowledge diffusion on Intellectual Property Rights arrangements, in a way that Regional Industry can profit from the knowledge or from licensing and patenting opportunities of science and technology innovation. The WP6 will also give continuity to the M-Change strategic activities by opening a new call to aggregate a collaborative partnership especially coming from SMEs, Industry or Industrial Associations; moreover it will assess the validity of innovative indicators; an easier monitoring and evaluation procedures and programme management approaches will be organised and designed to ensure that the M-Change results are comparable throughout Europe, and that they can be optimised to favour an effective European Integration.

- Description of work T6.1 – Modelling M-Change development and diffusion. The task aims at Modelling the development and diffusion of the advanced knowledge and best practices about running programs in the development of campus or spin out companies or joint ventures between the science base RTD Centres and University’s and SMEs Associations or Groupings. T6.2 – Indicators and procedures. The task aims at elaborating evaluation indicators, guide for practices and financial procedures for the achievement of common and complemented networking programmes for implementing the European knowledge-based economy. T6.3 – Networking programmes. The task aims assisting innovation and enterprise stimulation networking programmes, through organising Regional Congress and local workshops and also short term meetings of managers supporting them with the knowledge of science & business opportunities emerging European and Trans European levels. T6.4 – M-Change online methods. The task aims at developing and experimenting collaborative on line methods for sharing experiences and promoting best practices for joining and integrating programs between University and SME’s at the European level. T6.5 – Diffusion of case studies and benchmarking. The task aims at delivering on line case studies/benchmarks materials, mutual opening initiatives and position papers, based on disseminating for instance innovative experiences on a number of specific problems and successful demonstrations on Knowledge Dynamics, through a range of media/multimedia routes and could include short company visits, seminars, brief staff exchanges, and so on.

- Deliverables D12 – Conceptual and organizational model for a citizen centred e-governmental European strategy D13 - Knowledge-based economy dynamics indicators. The document assesses the networking programs in relation to the development of human and social capital

- Milestones and expected result The main expected result of the M-Change activities is to generate a deep understanding on the knowledge dynamics and characteristic in networking Business and Education framework system that permits differentiation in several key aspects of future knowledge economy from the traditional industrial economy (considering that Knowledge when locked into transformation systems or processes has higher inherent value than when it can ‘walk out of the door’ in people’s heads). Another purpose is to set up the dynamics indicators in relation to the development of human and social capital will be introduced to measure the effect of de-localisation of the Economy in a Knowledge Society advancement and in particular in relation to the management skill changes, that are necessary for using appropriate technology and methods, able to develop virtual organisations in mutual–networking learning and business, in a way that can offer benefits of speed and agility, of round the clock operation and of global-research in word wide Knowledge Economy competition.

- Work package 7 – Dissemination and Exploitation (18 month plan)

| - Work package number | - WP7 |  |  | - Start date or starting event: |  |  |  |  |  |  | - month 2 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Participant id |  | - 1 | - 2 |  | - 3 | - 4 | - 5 | - 6 | - 7 | - 8 |  | - 9 | - 10 | - 11 |  |
| - Person-months per participant: |  | - 4,5 | - 0,3 |  | - 0,6 | - 3,5 | - 2 | - 2,5 | - 2,5 | - 3,5 |  | - 1,5 | - 3 | - 1,5 |  |
| - Participant id |  | - 12 | - 13 |  | - 14 | - 15 | - 16 | - 17 | - 18 | - 19 |  | - 20 | - 21 |  |  |
| - Person-months per participant: |  | - 2,5 | - 2,5 |  | - 2,5 | - 3 | - 3 | - 3 | - 3 | - 3 |  | - 3 | - 1 |  |  |

- Objectives WP7includes two complementary and parallel lines of action. Dissemination groups the activities aimed at widely informing about the M-Change approach and results, as a condition for their adoption and exploitation in different contexts. In particular, an Interest Group is constituted to verify time by time the project results. IG components are first of all organisations and companies which present similarities with the Consortium partners. The Consortium partners act as regional co-ordinators of the IG members they can directly contact. Also, a Web site is realised to inform on the project, events are organised in accordance with the project results and other dissemination activities are studied and performed. All the partners are somehow engaged in dissemination activities. Exploitation groups the activities aimed at establishing the conditions under which the M-Change partners will participate, in conjunction and separately, in the exploitation of the project results. In particular, plans are made to consolidate the use of the M-Change platform and approach and to promote its diffusion through the provision of the relative Internet-based service. All the partners are involved, with different roles, in these activities.

Description of work The work is split into the following main tasks: T7.1 – Dissemination & exploitation policy and plans. The Consortium goes deeper in defining how to promote and M-Change approach and results over Europe. Dissemination plans include initiatives to involve new companies and organisations both private and public in different European countries. T7.2– Dissemination material and channels. Dissemination material and generic communication channels are indeed necessary to transfer knowledge elements to the widest audience through a free access to informative, learning and training materials. In addition to opening a public section in the project Web site, the broadcast of project objectives as well as intermediate and final results calls for production of leaflets and brochures in different languages, and publication of informative and technical papers. In addition, the dissemination structure based on first- and second-level associations provides further dissemination opportunities. This task aims at promoting and co-ordinating this work. T7.3– Dissemination events. A first International Congress (2 days) is planned after the first six month. it relates on the topic: Knowledge Dynamics and M-Change. Debate on the Study Report on the implementation of Knowledge Dynamics Understanding will be included. This Congress will be held in ROMANIA, Craiova and will be organised by IPACIFATT. A second International Congress (held in the Congress Palace in Florence Italy) is planned after 18 months on the topic: Human and social capital key components of value in a European knowledge-based economy. Some seminars and other debates will focusing also on the emergence and development of gender mainstreaming strategies and their truly impact at economic social, public and private sector. T7.4 – Exploitation agreement. The task aim is defining a general agreement on project result exploitation, with identification of roles, rights and obligations of each Consortium partner with respect to industrialisation and sale of the project outcome.

Deliverables D04 – Dissemination and exploitation plans. The document presents the results of task T7.1, in terms of M-CHANGE approach characterisation, preliminary market analysis and target audience description, plans for dissemination and exploitation activities for the whole project duration. D05 – Proceedings. International Congress Knowledge Dynamics and Mental Change. D08 – First report on dissemination activities. The document summarises the work (referred to tasks T7.2 and T7.3) done by all the Consortium members in the first year of the project (in particular, Web site set-up and first events), including an update of the dissemination and exploitation plans. D14 – Proceedings. International Congress Human and social capital key components of value in a European knowledge-based economy. D16 – First exploitation agreement.

- Milestones and expected result - The work done in this WP produces the deliverables D04, D08 and D16 and by the first 18 months two international events will be carries out.

- Work package 8 – Training for Net-Learning (18 month plan)

| - Work package number | - WP8 |  |  | - Start date or starting event: |  |  |  |  |  |  | - month 14 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Participant id |  | - 1 | - 2 |  | - 3 | - 4 | - 5 | - 6 | - 7 | - 8 |  | - 9 | - 10 | - 11 |  |
| - Person-months per participant: |  | - 1,0 | - 1,0 |  | - 0,0 | - 1,0 | - 0,5 | - 0,5 | - 0,5 | - 0,5 |  | - 0 | - 0,5 | - 0,0 |  |
| - Participant id |  | - 12 | - 13 |  | - 14 | - 15 | - 16 | - 17 | - 18 | - 19 |  | - 20 | - 21 |  |  |
| - Person-months per participant: |  | - 0,5 | - 0,5 |  | - 1,5 | - 0,5 | - 0,5 | - 0,5 | - 0,5 | - 0,5 |  | - 0,5 | - 0,0 |  |  |

- Objectives WP8 groups the activities aimed at putting the system users (target citizens, policy makers, private and public enterprises) in the best condition to use the M-CHANGE approach. Training is based on a wide material derived from the project documentation (above all organisational models and indicators), and an important outcome is the realisation of localised versions of this material taking advantage of the real user experience.

The work is split into the following main tasks: T8.1 – Preparation of draft training material. Starting from the results of WP3 this task produces basic training materials in English, to be adapted to local conditions in the next task of the same WP. Different user profiles are identified. T8.2 – Localisation and training in the different Countries. The task includes organisation and execution of the needed training sessions, for each target user profile. User opinions and recommendations on the effectiveness of the lesson structure and training material are collected for workpackage WP8.

Deliverables D11 – Refined training material. The document summarises the work done in task 8.1, and produces the training material suitable for use by newcomers of the M-CHANGE approach. D15 – Report on training activities. The document presents the work done in task T8.2, and is split into two parts: (i) description of training activities execution, in terms of course structure, involved persons and achieved results, (ii) suggestions for further improvement of training material and methods.

- Milestones and expected result - The Workpackage produces the first result with D11 on delivering of training materials. Lessons learnt and recommendations to fasten and improve knowledge transfer to other stakeholders are obtained by the end of the project, and constitute a fundamental step towards an effective and cheap diffusion of the project results.

## WORKPLAN - AFTER 18 /MONTH

General Topic: Starting from the consideration of the principal forces driving the knowledge based economy are focused on the Intellectual Capital management as well as a key source of innovation, the program M-Change will continuing the research and the activities following the objective to understand the role of knowledge dynamics in processes of learning and competence-building and to relate this to issues of competitiveness, regional development and economic and social cohesion.

The strategic issue of the development included in the of the Working plan between <18- to 36> months will be able to develop a set of key factors that can be used by citizen to make decision or take actions that are important for developing a conscious change of mentality in a developmental world wide context opening up local economies to global competition through greater interdependency of business and research.

Therefore the M-Change project aims at suggesting innovative solutions to these developmental endeavours by developing suitable methodologies of research and dissemination actions that include activities in the following fields:

The Working plan will be divided in three phases looking at a progressive differentiation of the working activities made by the original partners and by new partners and stakeholders joining the project M-Change; as a matter of fact, in a successive 18 months perspective the project will support the integration of other partners belonging to candidate and third countries regions.

### First Phase - Six months Month 18-24

### WP9 - Development of models for strategic alliances

1) – Multidisciplinary Studies on the development of models for an efficient optimisation of strategic alliances and model predictive control within strengthening alliances among Governmental Local Institution SME’S and Universities and other Public or Private centres of research & development, aiming to work in partnership for the integration local models of development and macro economical optimisation.

2) - Research on different levels of e-Governance in Europe, on economic and social regulation within Europe; analysis of the role of regional public authorities in the partnership’s countries on economic and social development within Europe including the evolution of e.work systems; and the dynamics of European integration and enlargement.

During those studies and researchers will be developed seven tasks and actions as well as: dissemination of intermediate reports towards improved management of societal change; diffusion of new perspectives and realization of training courses of Net-learning strategies in a changing society and social cohesion obtained by means of a life long competence-building for improving intellectual employment in e.working co-operative systems. Diffusion of Information on e.Governance advancement, citizenship understanding on the dynamics of European integration and in EU enlargement in the development of the global competition on Knowledge Society.

### Second Phase - Six months Month 24-30

### WP10 - Creation of e-learning on demand platforms

1) Multidisciplinary Studies of new development models fostering growth and employment oriented to overcoming the lack of an “Creative Knowledge Management”, to ameliorate the SME’s quality of production and processes and to exploit results through the preparation of a mutual opening "e. learning on demand" platforms and methods to favour a common understanding of RTD strategies for improving the European Development of Knowledge Economy.

2) Research into new sustainable models to foster growth, job creation, equal opportunities, reduction of inequalities - exploring and taking in account ethical and gender issues and favouring the improvement of quality of life, helping the creation of sustainable growing by the training of “skilled staffs” and helping the reorganisation of work, from low skill level of the labour-intensive sectors to a more productive knowledge “team-e.work” management.

- During those studies and researchers the M-Change programme is intended to offer and disseminate a series of specific tasks and activities, focused on the following issue: how the Knowledge Economy development should be carried out preparing a durable co-operation activity favouring the growing up of clustering for Regional projects and for possible

- co-ordinating actions oriented to avoid cultural and/or digital barriers for researchers and citizens

-stimulating cultural and scientific innovation and economic growth through Knowledge management innovative strategies

- collaborating with other social and policy actors for improving actions addressing the major societal and economic challenges of Knowledge driven Economy for instance: dissemination on Regional research innovations about developmental priorities on agro-food quality and food tractability process all along the production chains, food frauds prevention ; impact of food on health and so on; multifunctional materials, applied to new products and processes etc. and to all other RTD fields and all scientific and technological advancements especially addressed to favour University SME’s integration (e.g improving start up, spin of, spin out, Business to Business Agency, and so on) and all other factors aiming to contributing to the general goal: “Europe becoming the most competitive and dynamic knowledge-based economy until 2010”

### Third Phase - Six months Month 30-36

### WP11 -Consolidating the M-Change approach

1) Multidisciplinary Studies oriented to further optimise the M-Change project for favouring co-ordinated response of Regional Groupings towards common European challenge’s development by growing up a conscious understanding of citizen and implementing human and social in Europe.

2) Comparative research across Europe of the possible end sustainable relevance of M-Change program focused about the strategic contribution to realise supporting long-term perspectives in European research and developmental policies, addressed to improve territorial and organisational co-operative configurations affecting the potential for innovation and economic development.

During those studies and researchers the M-Change programme will support effective contributions to the specific working planning activities addressed on various co-ordination and supporting actions oriented to realize a large market of “Priority Driven Research” that can be realised throughout the effort developed for achieving a creative change of strategic knowledge management co-organisation

As a matter of facts the <M-CHANGE > CONSOTIUM would like to realise a proper sustainability after the end of the European Commission Contribution, becoming an co-operative trans –national Agency for training skill and competence building in Knowledge Management co-organisation, able to explore critical success factors for enabling Intelligent Information Technology Communication to be used as well as a fundamental tool for redesigning co-ordination process and to support a durable co-operation for the European e.Governance in all the fields of RDT Driven Economy. In the last phase of the three years program a Strategic Knowledge Management Action Plan and a joint database of experts/advisors and committees boards, will be provided and implemented, utilising the latest trends of intelligent techniques and semantic software and creative ideas, that will be included in a KNOWLEDGE- ECONOMY PORTAL.

The Knowledge Economy Portal at that stage, will optimised to contain corporate case studies and special case based reports, new reasoning report; also will be organised a mutual learning on demand system with an special attention to the field of business & RDT integration process, to benefit mutual understanding of the re-engineering procedures of RDT/SMEs integration that will be able to satisfy the users requirements.

Finally the prevalent relevance of <M-Change> project it will meant to valorise the interface to develop a large proposal of co-ordination activities based on the integration between University and Centres of Research with the SME’s innovation, into an higher level of agreement in a wide European ICT framework improving network management roles and responsibilities, common understanding and standardised methods for reward and evaluation procedures.

# B.9 Other issues

## Contributions to European Governance

The European Governance White Paper (2001) has proposed an “opening up the policy-making process to get more people and organisations involved in shaping and delivering EU policy. It promotes greater openness, accountability and responsibility for all those involved”. Paradox is the fact that For the moment more than 75% of social laws have a EC origin and yet it widely accepted that the first starting point for public policies must be developed on a territorial basis, as a result of dialogue, concertation and negotiation between all the stake-holders in join agreement of end beneficiaries.

M-Change Project results will foster good citizens-centred governance initiatives by improving the capacity to develop a trans-national framework of an open information system made for a knowledge dynamics understanding.

These results will foster some of the main points, proposed by the Commission, to strength the European Governance, namely:

- stronger interaction with regional and local governments and civil society;

- greater flexibility into how Community legislation taking in consideration regional and local conditions;

- establishing a more systematic dialogue with representatives of regional and local governments through national and European associations;

- improve the dialogue with governmental and non-governmental actors of third countries.

In fact the two basic concepts beyond M-Change Project (“down-top decision making” and “meet local with global challenges”) are the key-points to establishing more democratic society by follow the principles of good governance: openness, participation, accountability, effectiveness and coherence.

## Contributions to European Governance

“Democracy depends on people being able to take part in public debate”.

Providing more information and more effective communication are a pre-condition for generating European Knowledge Society. In this field, information and communication technologies have an important role. The inter-active web platforms of M-Change Project will provide and provide up-to-date on-line information and look after feedback and debate, where different actors from different countries can discuss what they perceive as being the important challenges and determinants towards a knowledge based Society.

M-Change Project intent to produce specific research over the democratization of public life, Regional and National governmental renewal in correlation of international relations in Europe, obtained by means of public opinion poll, interviewing, testing, monitoring, probability methods and social processes prognostication. More specifically the work package 6 intends to starts the formulation of an enhanced conceptual and organisational model for a citizen centred e-Governmental European strategy, founded on supporting participatory democracy, that will offer at the European Citizen the opportunity to access and to share information by means of an interactive e.Editorial system, both within European Regions and across Regional and National borders.

## Empowerment

M-Change Project is based on the aggregation of Regional (RIG) and/or National (NIG) Interest Groups - horizontal networks, but also of Thematic Interest Groups (TIG) vertical networks. Beyond this, the Project will build knowledge communities allowing adequate interaction in a multi-level partnership. Furthermore, exchange of information and joint research and training between partner and sub-partners at various levels would contribute to a better knowledge of each other’s policy objectives, working methods and instruments.

This empowering philosophy are constantly present since the Project Planning, will be deeper during the implementation and will continue till the results’ exploitation (work package 7): Exploitation groups the activities aimed at establishing the conditions under which the M-Change partners will participate, in conjunction and separately, in the exploitation of the project results. In particular, plans are made to consolidate the use of the M-Change platform and approach and to promote its diffusion through the provision of the relative Internet-based service. All the partners are involved, with different roles, in these activities.

# Gender issues

## Gender action plan

One of the M-CHANGE goal is also promoting the gender equality on the Project through the following actions:

- encouraging women’s participation in research, evaluation, consultation and it’s implementation;

- using local, national and European networks of Women in Science (such as Development-gender Group, UWiSe, BeWiSe, Amazon, IReen, IEEE-Women-In-Engineering, ...) to advertise any vacant positions and perform a fair selection and human Resources recruitment;

- ensuring that human resources involved on it’s development are either men and women in an egalitarian proportion;

- treating women participating into the project equitably, given equal resources, payment and included in decision-making;

- allowing at least one gender expert to take part on the Planning and monitoring team of the Project;

- ensuring equal opportunities to end beneficiaries of the project;

- guaranteeing a good gender balance in the program of scientific meetings, organized (e.g. take care of a good female representation in the speakers' list and chairpersons' list).

Moreover project will focus on themes, direct or indirectly, related with gender issues; documents produced under the Project development will be written in gender neutral language; advertising and marketing plan and it’s products (web-site, lefts and others) will use non discriminating photos, images or language; it will produce statistics taking account on women and men preferences, choices and needs and will include specific activities (see above “B.10.2. Gender issues” ) to promote attitudes changes towards gender equality; the project will take in serious consideration equality policy and norms in the EU and will disseminate results, products and good practices produced under gender equality framework and link them with networks of women scientists in the field of the project.

## Gender issues

Many Policies and guidelines engendered by the European Commission advocate a gender mainstreaming approach, the tackling of gender gaps and the reconciliation of work and family life. This issues are strength tied not only to personal, social and familiar life, but also so with the quality of the jobs and the success of the companies.

To follow policies and research orientations and make over activities to achieve tangible results depends crucially on the active support of the social partners in the various territorial and sectoral spheres. The strategy under Mental Change Project, by aggregating Regional (RIG) and National (NIG) horizontal networks and also of Thematic (TIG) vertical networks, will provide the required inputs that guarantee an added value over issues such as the above mentioned.

To favour the building of the European Knowledge Society the project will start from widely accepted concepts and practices of the Knowledge Economy development. In fact It is widely accepted that Human Capital is a major capital of the company (especially SME) and highly effective investments in the Human Resources are among most important conditions, which provide a difference between competitive innovative company and non-productive one. It all so clear that in Human Resources terms, companies are looking for highly skilled staff with strong social-relational abilities, who can constantly adjust their existing skills to new working situations.

New business practices and management techniques such as Total Quality Management or other allows the full involvement of all Human Resources and the full use of their skills and abilities in the project of enhancing organisational performance for competitive advantage. This implies that women’s and men’s skills are equally utilised, and that they are equally drawn into organisational projects for quality improvement. In practice, however, changes in organisational structure or new forms of work organisation are rarely implemented in an equality-conscious way and women tend to remain marginal to most total quality management initiatives.

M-CHANGE aims to understand the role of knowledge dynamics in processes of learning and competence-building and to relate this to of competitiveness, regional development and economic and social cohesion. In this context it will be highly important to assess, analyse and identify key factor to “mental change” and achieve gender equality at social and economic level.

Along the Project Development 3 main steps will consider, some factors related with equal opportunities, specially those related with gender dimensions:

- building a clear reference framework, to launch the practical work, in order to link territorial, Sectoral and Thematic approaches;

- conceiving grid to assess inputs to Mental Change Project and relevance of the expected outcomes of the Project;

- defining a model of dynamic knowledge at micro, medium and macro level.

The gender Plan, of Mental Change Project, will take in consideration the following documents and statements:

- Lisbon European (March 2000) - underlined the need for investment in human resources and for every citizen to be equipped with the skills needed to live and work in the information society and the need to further all aspects of equal opportunities.

- European Council in Brussels (March 2003) - underlined the importance of investment in human capital and lifelong learning as a prerequisite for the promotion of European competitiveness, for achieving high rates in growth and employment and moving to a knowledge-based economy.

- Council Resolution on "e-Inclusion" (October 2001) - underlined the importance to provide Information and Communication Technologies (ICT) training and other learning to disadvantaged people, promote digital literacy, encourage partnerships of all stakeholders and mainstream a gender equality approach in e-Inclusion policies.

- Conclusions of the Conference "Social and human capital in the knowledge society: policy implications" (October 2002), which highlighted the mutually reinforcing role of social and human capital for economic growth [...] and social cohesion [...].

- Ministerial conference on "Gender and ICT" . Athens (May 2003) - devoted to the risks and opportunities of the knowledge society for gender equality.

- Commission Staff Working Paper, developed with the support of the High Level Group on the Employment and Social Dimension of the Information Society (ESDIS), on "Building Social and Human Capital in the Knowledge Society".

### Commission

RECOGNISES the key role that knowledge embodied in individual capabilities and social networks [...] plays in the context of the Lisbon strategy for ensuring that the European Union becomes the most competitive and dynamic knowledge-based economy in the world, capable of sustainable economic growth with more and better jobs and greater social cohesion.

UNDERLINES the need of developing the positive interactions of social and human capital [...] in three areas in particular: learning, working and social cohesion, while integrating the gender dimension into all these areas.

## Ethical issues form

A. Proposers are requested to fill in the following table

| Does your proposed research raise sensitive ethical questions related to: | YES | NO |
| --- | --- | --- |
| - Human beings | - X |  |
| - Human biological samples |  | - X |
| - Personal data (whether identified by name or not) | - X |  |
| - Genetic information |  | - X |
| - Animals |  | - X |

- B. Applicants are requested to confirm that the proposed research does not involve:

- Research activity aimed at human cloning for reproductive purposes,

- Research activity intended to modify the genetic heritage of human beings which could make such changes heritable

- Research activity intended to create human embryos solely for the purpose of research or for the purpose of stem cell procurement, including by means of somatic cell nuclear transfer;

- Research involving the use of human embryos or embryonic stem cells with the exception of banked or isolated human embryonic stem cells in culture

Further information on ethics requirements and rules are given at the science and ethics website at http://europa.eu.int/comm/research/science-society/ethics/ethics_en.html.

# Appendix A - Profiles of the M-Change Consortium partners

## 1 - Regione Toscana – Italy

Tuscany is located at the center of Italy, it is bordered by the Tirrenian sea at west and south, and the Appenini mountains chain north and east. The region is 22.992 squared kilometers wide, 66,5 % hills, 25,1 % mountains, 8,4 % plains. It has 3.528.225 inhabitants with a 153 in./sqkm. density - lower than the national average. Natality is very low, i.e., demoghraphic growth is –0,3 / 1000.

Tuscany’s economic system features a high number of small and medium enterprises (SMEs). 35,2 % of tuscany employees is in firms with less than 10 employees, 39,3 % is in enterprises with 10 to 50 employees, and only 25,5 % is in firms with more than 50 workers. Therefore the SMEs phenomenon refers in Tuscany to very small firms, many more than in similar regional economic systems (e.g., Emilia Romagna, Veneto).The small size of firms is strictly related to prevailing productive sectors: about 14% of workers are in clothing and footwear (6,5% in Italy), 12 % in Investment Goods (23,6 % in Lombardia and 19,1 % in Emilia Romagna). SMEs in Tuscany do not cover light and traditional sectors only: small firms occur in every industrial sector, even in most advanced and dynamic ones (e.g., Mechanics and Electronics). However, the small size of firms in Tuscany is not as important as the fact that they tend to form integrated systems, i.e., clusters of a high number of firms, embedded in the local societies, forming industrial districts. These constitute a concentrated group of productive activities in a specific territorial context. Due to the small size of firms one finds a limited growth and diffusion of technologies, credit rationing, and limited scale and net economies. Local industrial systems feature various levels of diversification in Tuscany: some are strongly specialised (e.g., textile in Prato, leather in Santa Croce), whereas others show several productive typologies. On the other hand, one common character of such systems is the flexibility of the labour factor, together with its strong identity.

Regional Programme Of Innovative Actions focuses (IARP) on the first of the three strategic themes, i.e. knowledge-based regional economies and technological innovation, and specifically on the sub-theme cluster and business networks. The Programme is composed by 4 actions:

- Technological transfer and innovation technology diffusion in Western Tuscany;

- Technological transfer and the innovation technology diffusion in the fashion system;

- Industrial applications of the optoelectronic technologies;

- Industrial agro-alimentary applications of the biotechnology. There are also two more actions: Accompanying measure and Technical assistance.

CORINNA is the network of IARP Programme of Italians region and it was planned, promoted and managed by Regione Toscana. The structure and financial and administrative issues have been finalised within last months and the Consortium Agreement is being signed

The aims of the “Innovation and Research Policies Office” of Economical Development Department are:

- Study of the innovative processes of the regional economy to improve regional competitiveness and innovative capacity SMEs;

- Sharing of information, experiences and good practices among the partners to steer regional strategies and RDT&I efforts towards knowledge oriented society; (ERIK network management, CORINNA management)

- Promotion of feasibility projects in innovative clusters (Objective 2 funding programme, Innovative Actions Programme);

- Support of SMEs and promotion of technological transfer in the region (Objective 2 funding programme, Innovative Actions Programme under the theme Regional Economy based on knowledge society);

- Governance of the networking among SME, research bodies and services centres, public administrations, financing bodies in order to strengthen the cooperation among involved stakeholders at regional, national and European level and develop regional integrated policies;

- Development and Design of project in the field of innovative technological processes, in particular under National and European programmes (EU Framework Programmes, TenTelecom (IRENE project), ERDF Interreg Programme);

- Monitoring supporting of the regional and national operational organisations.

From the European Council in Lisbona (2000), Regione Toscana has decided to increase and focuse efforts to play its governance role in improving the definition of innovative integrated policies as better as it was requested. Main guidelines were to support new policies with the related knowledge sharing, to move towards integrated and territorial policies and to move from a centralised management to networking and governance activities. At thepresent, the Tuscan Region is the fourth Italian region for R&D related expenditure, followed by Lombardy, Piedmont and Latium respectively.

Region of Tuscany has created a set of instruments to insure the systematic participation of agents in economic and social development of Tuscany:

- the Pact for Development and Employment;

- Committee for arrangements with economic categories;

- The permanent Regional Conference along with the six academic Institutions of Tuscany and the two research Areas of the National Research Council.

The elaboration of the Programme was overlapped by the Forum on Innovation and on Regional Development Policies (ended December, 2001), and in particular in the thematic workshops in which all of the potential public partners of the Programme contributed to the proposal and in-depth study of the strategic themes and the specific sector initiatives for technological innovation and transfer in Tuscany.

The Programme aims to stimulate the dissemination process of technological and knowledge development within the regional economy through the creation of a set of co-operation networks among SMEs, research centres and universities, local public institutions, centres for technological innovation and transfer, business services, training centres and financial organisations.

These co-operation networks will promote the integration of scientific, technological and industrial skills in the more developed areas of the region with the resources present in the areas that will benefit from the ERDF financing (Objective 2 and transitory support) so as to facilitate the extension of technological innovation and transfer processes to these areas. This will allow for the piloting of innovative methods which was used subsequently in the interventions planned by Objective 2 programme, launched in 2001.

### Latest experiences of Co-ordination in European network or projects:

ERIK Network

The ERIK network has been founded by the Toscana and Emilia-Romagna regions, acting as leading regions, together with other 11 European regions. The main scope of a network should be the sharing of information and practices with the largest number of interested actors. It has been created to sustain and further develop inter-regional networking and to provide network support to regions with approved ERDF Innovative Actions programmes. The network aims at improving cohesion through the sharing of information, experience and good practices among partners and to steer regional strategies towards knowledge oriented policies. For this reason the enlargement of the ERIK network to other regions is our first objective. ERIK is still in its embryonic phase, but a number of regions have already expressed their interest in joining us. ERIK is the network of European Regions dealing with “Regional economies based on Knowledge and Technological Innovation”. Activities carried out within ERIK network and directly related to Mental Change are:

- the enhancement of innovation and knowledge oriented regional strategies

- the benchmarking of good practices relating to innovation and knowledge policies;

- the extension of collaboration at interregional level among the different actors of the regional knowledge systems;

- the increase of the know-how of main regional actors as far as innovation, technology transfer and the promotion of knowledge economy are concerned.

INTERREG IIC/IIIB (European Structural Funds)

Retelab, Transnational Network of Environmental Laboratories: InterregIIC Western Mediterranean and Latin Alps. Achievements of the project may be briefly stated as follows:

- creating a permanent network among regional centres and laboratories where data are collected and processed;

- starting a permanent updating process for lab-staff, in order to share acquired skills;

- exchanging skills and methodologies, both through workshops held by researchers and technicians from other labs and by exchanging materials etc.;

- fine tuning of methods and procedures to spread information and products to the public.

PAN, Mediterranean system of routes in natural and cultural parks: InterregIIC Western Mediterranean and Latin Alps. Achievements of the project are:

- To improve network marketing strategies to increase tourist demand;

- To promote the spread of multimedia skills and build a digital network of natural and cultural parks, in order to manage and control several promotional activities.

CV’s of Key Personnel

Simone Sorbi. Project Co-ordinator of the M-CHANGE project. Director of Innovation and Research Policy Office since October 2000.

| Present position | Director of Innovation and Research Policy Office since October 2000. The aims of the Office are: - Promotion of feasibility projects in innovative cluster - Relationship among advanced technology, tourism, and environmental and cultural heritage. - Relationship among SMEs and Hi-Tech - Study of the innovative processes of the regional economy - Development and Design of project in the field of innovative technological processes, in particular to National and European programmes. |
| --- | --- |
| 2000 | Co-ordinator for the regional law number 55 “06.04.2000” to give birth to the “LaMMA SKY MED” company by ASI, CNR and FMA |
| 1999 | Co-ordinator of joint activities with Finmeccanica, ESA and latin american countries to develop ground stations for reception and data processing in the framework of new satellite technologies for earth observation Co-ordinator of activity from NRC, National Air Force, ESA, Tuscany Region and EUMETSAT for the development of GOME (Global Ozone Monitoring Equipment) by Finmeccanica Appointed coordinator by the Transport Ministry for the new Interreg IIIB programme plan, with reference to environment |
| 1998 | Person in charge for the Agreement between Tuscany and the National Air Force, working together both in meteorology and climatology |
| 1997 | Project leader and transnational coordinator of two Interreg IIC projects: “Transnational Network of Multifunctional Environmental Laboratories” and “Parks, Environment and Nature – New Paths for a Sustainable Tourism” featuring italian, spanish, french and greek partners. |
| 1996 | Promotes, together with MURST, the TETRA project – a european standard for mobile wide band together with OTE-Marconi Communication; Appointed substitute member in the directive committee for the Interreg IIC programme by the regional council. |
| 1995 | Appointed in charge of the LaMMA regional project, managing its birth and development, makes for regional participation in the European Community Project “Cosmo Sky Med” |
| 1994 | Editor of the regional “Technological Research and Innovation” series, publishing some four issues per year on specific regional themes |
| 1993 | Member of the High Technology Network, appointed member of the executive board in Pisa Ricerche and Etruria Innovazione by the regional council |
| 1992 to 2000 | Responsible for developing the MAN Information Network together with the National Research Council and its related Project; Tuscany is the first region to deploy a wide band information network to connect three distinct universities |
| 1990 | Head secretary for the Regional Council – University Conference, in charge of related Agreements and the Regional Research Plan. |
| 1987 | Director of Regione Toscana Research activities. In cooperation with CNR a set up an innovative program concerning Information Society and Telecommunication projects in the region. Responsible of regional founds about post-graduate research contracts in co-operation with CNR and Universities. |
| 1983 to 1985 | In behalf of Tuscany Regional Government, responsible of the regional energetic plan and of the application of the relative law on the energy savings. Institutional relationships with CNR, ENEA, ENI and ENEL. |
| 1977 to 1983 | Responsible for the regional vocational training activities in the agricultural and forest science sector |
| 1972 to 1977 | Teacher at some vocational training schools of Regione Toscana |

Saverio Gini. Degree in Electronic Engineering with specialisation Biomedics, Università degli Studi of Firenze with Thesis title: “Processing of EEG signal through adaptive prediction and fuzzy logic”, Supervisor: Prof. Vito Cappellini, Prof. Guido Valli, Eng. Franco Bartolini, Eng. Vincenzo Roma, Eng. Simone Pola in collaboration with EBNeuro company of Firenze, vote: 105/110. The software tool implemented during the thesis period was developed in Visual C++ language in Windows environment. Engineering qualification from Università degli Studi of Firenze. He took part in Trastek project with the aim to form consultants in technological transfer in the health area. The course, funded by Tuscany Region, was organized in collaboration with Cesvit, high technology agency. He has experience in the development of research project at European and national level; in the analysis of interdisciplinary problems and in the identification of technological solutions adapted to the users needs and based on feasibility studies; in the Technological transfer, modules of finding regional, national and international financial sources and in tools for EEG processing.

## 2 - LRE-EGO-CreaNET – -FACULTY OF SCIENCE –University of Florence, Italy

LRE/EGO-CREANET LRE@UNIFI.IT is the acronym of the Laboratory of Educational Research - University of Florence ( http://www.chim1.unifi.it/group/education). The Laboratory of Educational Research (LRE) has been, since 1985, in charge of the Faculty of Sciences of the University of Florence (Italy) for developing partnerships between The University, the Schools and the Enterprises. Our mission is to promote the collaboration between education and enterprises, for the creation of new job opportunities in an contemporary economy driven by Knowledge.

In order to develop on-line innovative activities of e-learning/e-work, the LRE of the University of Florence has created the International Telematic non-Profit International Association EGO-CreaNET, a virtual community of "e-Brainworkers" dedicated to the improvement of the “Knowledge Society”, in Science and Art, Net-economy and Education.

Following this strategy, the LRE–EGO-CreaNET is a new public (LRE-UNIVERSITY of Florence Italy) and private institution (EGO-CreaNET – No Profit Telematic International Association), the last composed of members of a trans-national partnership, whose aim is to strengthen the development of life-long training in Internet, as a mean to create new professions and to increase the exchange of cultural and scientific initiatives on-line.

The activities of EGO-CreaNET/LRE  began in 1997. The Operational Research Group of EGO-CreaNET/LRE ("Global Extended Observatory on Creativity Networking), is made of voluntary researchers of the LRE/ of the University of Florence (Italy) and of a number of regional and/or international chapters of the EGO-CreaNET. Autonomous chapters exist in Italy, in Lombardia, Veneto, Romagna, Tuscany, Umbria, Campania and Puglia.  In 1999 the first international section was created in Lima, Peru and more recently in San Luis, Argentina. The EGO-CreaNET International Telematics Association is the Italian Representative of the following co-operative international bodies:

a) iEARN (International Education and Resource Network);

b) eXplora Europa- Schooling Prize: http://explora.eun.org

c) Think-Quest World Prize: Think Quest Italy http://www.thinkquest.it/ and http://www.thinkquest.it/egocreanet

d) The LRE-EGO-CreaNET strating fron 2002 is partner of the Following Euroean Projects

Lefo- Minerva European Project  http://www.miksike.com/

Forco-Precanet – Leonardo Eurpean Project: http://www.univ-tlse2.fr/leonardo/forco-precanet/

OGM – Leonardo Project: WWW.  ( in construction)

The main WEB-Sites of EGO-CreaNet/LRE are:

http://www.chim1.unifi.it/group/education;

http://www.edscuola.com/lre.html ; http://www.educazionevisiva.cjb.net

http://www.narnia.it/egocreanet ; http://www.hermeslab.net/ ; http://www.nove.firenze.it/

The role of LRE/EGOCreaNET will be enclosed in the following research issues:

Knowledgde dynamics and scenery  for innovation ; changes in mentality and impact in society; NET-leraning strategy, new paradigms and indicators for the evaluation of intangible gods as social and human skills, and other knowledge economy developmental issues.

CV’s of Key Personnel

Paolo Manzelli.

LRE –of University of Florence  SCIENTIFIC DIRECTOR- President and Legal Representative of of the EGO-CreaNET -International Telematics  (No for Profit) Association.

Membership of Professional Bodies: President International Telematics Association EGO-CreaNET.

Other Skills: 	Research on Education and economic development of Knowledge Society.

He has been working at the University of Florence for 35 years.

Key Qualifications: (relevant to the project) Brain e.work  for improving projects for knowledge management education and net-economy innovation.

Experience in Specific countries/territories :

Country : SOMALILAND –AFRICA Professor of Chemistry (Date :      1974 / 1981). In 1971-/73 Voluntary Co-operation for the Foundation of National Somaly University  - in Mogadisciu.

Co-Organisation staff of the National University in SOMALILAND AFRICA:

Location: MOGADISCIU

Organisation: Department of Science

Position: Professor of Agricultural Chemistry

Responsibilities: Coordinator of the Laboratory

He carried out More than 280 publication (27 Chemical Physics until 1974) after 1974 publication in Educational Research and Development in various Fields of Learning ( Chemistry, Pedagogy, Brain & Education).

Matteo Barbarulo. Graduated in arts and history, he has got a Master of E-learning Management at University of Florence (2002). He has a long experience in ICT with the Italian Public Administration. Since 2002, he is involved in the European projects with the LRE-EgoCreaNet R&D Group's.

## 3 - UOR – Dipartimento di Sociologia e Comunicazione dell’Università di Roma La Sapienza, Italy

http://www.discuniroma1.it/

The Department of Sociology and Communication was founded on January 1st 1983 with a rectors' Decree as of December 30, 1982.

The main location of the Department is in via Salaria, 113. Classrooms and other teaching facilities are also located in via Vicenza and Corso d’Italia. The Director of the Department is Professor Mario Morcellini. He is full Professor of Sociology of Communication. He has been reconfirmed as Director of the Department for the years 2001 to 2004. At present in the Department there are more than 55 professors, 20 administrative employees and technicians, and a number of contracting research staff and PhD students. The Department of Sociology and Communication promotes and coordinates research activity within the realm of the various areas of sociology, human sciences, media studies and e-learning methodology. The Department offers two PhD programs and 8 specialisation post-graduation courses.

In recent years the Department carried out research project together with the following public and private organizations: The Regione Lazio – Assessor ship for the Educational training and Cultural Policies; City of Narni; Ministry of Culture; Ministry of Labour; Ministry of University; Province of Rome; Co-operative Banks; Municipal Organization for the Environment; Telecom Italia; Informational Section of RAI -Italian National Television; SIAE (Italian Association of Authors and Publishers); WWF Association; European Commission (5FP projects BISER and EGAP); International Training Center of the ILO.

The main research activities carried out in the last four years by the Department are as follows.

Il gioco delle parti (The role playing)

In collaboration with the Province of Rome, the Department of Sociology carried out, in 1997,  the research Una Maestra in più in the schools of the roman area, monitoring the relationship between minor and television in order to create personal “diets of consumption”. The success of the experiment encouraged the two partners of the project to repeat the study experience (Il gioco delle parti – 2000), renewing and elaborating contents to verify the variety and characteristics of  the young multimedia uses. Some training activities, for teacher and parents, were implemented by the University during the collaboration with the Province of Rome in order to test and gain tools and methods of the Media Education. (Years: 2000/2001, Customer: Province of Rome (public)).

Benchmarking of e-learning platforms

This study has been conducted by the Department of Sociology and Communication for the Italian Foreign Affairs Ministry and ILO (International Labour Organization). The study is a benchmark of E-learning platforms available on the market, according to shared evaluation criteria in order to achieve an objective and effective measurement (Years: 2002/2003, Customer: CIF/OIL (private).

BISER-Benchmarking the Information Society: e-Europe Indicators for European Regions

BISER Project, approved under the Fifth Framework Program – IST (Information Society Technologies) includes the Department of Sociology and Communication together with five European partners. During its three years the BISER project will define, develop and pilot a set of statistical indicators for benchmarking the progress of European regions in respect of the e-Europe Initiative and the emerging Information Society (Year: 2002, Customer: European Union (public).

Media-Tv-Minori (Media-TV-Minors)

This theme is constantly central in the public debate. This is why the Department has regularly analysed the relationship between media and minors. The Department developed this study matching television audience ratings  (Iard data) with the data of the research “La TV fa bene ai bambini”,1999 (“TV is good for kids”). The Department is constantly investing in researching these fields, allowing researchers the possibility to define and study this important connection between media and minors (Years: 2002/2003, Customer: Autorità per la garanzia nelle comunicazioni (public).

Project EGAP - E-Society Gap Assessment Project

The EGAP Project, approved under the Fifth Framework Program – IST (Information Society Technologies) includes the Department of Sociology and Communication together with five European partners. The project intends to observe and compare several significant EU countries in order to bring out precisely the reasons and the ways that, within specific professional environments, telework and teleactivities in SMEs meet difficulties in implementation, or generate positive results (Years: 2002/2003, Customer: Futuribles sarl (private).

ITENETS

The ITENETs project - International Training and Employment Network – is part of a larger program: “Specific programmes for animation and promotion of stable networks between South Italy Regions and Italians abroad”, a program of the Foreign Affairs Ministry. The project intends to create a system of net services to promote, program, orient and sustain the southern Italian Regions in the creation of training and employment networks with Italian communities all over the world (Years: 2002/2003, Customer: Ministry of Foreign Affairs Minis, (public).

OPENFAD

The OpenFad project aims to develop the interrelations between the University of Bari and the State of Argentina. This relationship was born thanks to several project developed during the past with the National Universities of Rosario, Mar del Plata, Belgrano and the San Juan Bosco University of Patagonia. The main goal of the project is to innovate the net between Bari and the Argentine Universities through the creation of an innovative open source and free e-learning system. This system could be used by Universities, local public administrations trainers teaching in public offices.  The Department of Sociology and Communication will create the e-learning platform and develop the training contents (Year: 2003, Customer: University of Bari (public).

PPTIE (Territorial Partnership Program for Italians Abroad)

PPTIE project is promoted by Italian Foreign Affairs Ministry and Southern Italian Regions (OB1 Regions). The program is co-financed by European Community, International Training Centre of the  International Labour Organization (ICT-ILO) and Department of Sociology and Communication. The project intends to promote, facilitate and sustain the development of collaboration projects between Italian Southern Regions and Italians communities abroad, through the creation of territorial partnerships (Year: 2003, Customer: Ministry of Foreign Affairs (public).

CV of key personnel

Prof. Patrizio DI NICOLA, sociologist and expert of ICT, is professor of Sociology of Organisation at the Faculty of Communication Sciences and former Professor of Methodology and Techniques of the ICT at the Department of Information, Economy and Society - Faculty of Sociology - University of Rome "La Sapienza". Since 1985 he was scientific director for many researches on telework, virtual enterprises, e-learning and the post -industrial labour market, and was managing consultant of many enterprises and Government bodies. From 1996 to 1999 was National Co-ordinator for the European Telework Development Initiative, in 1999 was Advisor of the Minister of Regional Affairs and member of the Italian Forum for the Information Society. In 2000 was e-learning director at e-Work spa. He is author or contributor of many books and is editor of the Italian version of the TCA' Teleworking Handbook (1997 and 1999). Most recent publications include: Le@rning, with F. Comunello, Telework between Law and Contract  (1998)¸ Telework: Working on progress, 1998 (CD Rom); New International Perspectives on Telework, 1998; Internet 2000, (1997). He is contributor of the recent book Building the Knowledge Economy, IOS press, 2003.

Prof. Patrizia CINTI, sociologist, is professor of “Education and politics of the human resources“ and professor of “Master organisation and formation“ at the Faculty of Communication Sciences, University of Rome “La Sapienza”. She is the responsible for the e-learning activities for the Faculty of Communication Sciences.

Expert of organisation and education, knowledge management, organizational networks and e-learning, she worked in many public and private organisations.

Since 1989, she is senior consultant of “Butera and Partners“ and of “IRSO“ Institute, contributing to innovation and e-learning projects for the Italian schools. She is also visiting scholar at the J. Anderson Graduate School of management, UCLA, University of Los Angeles, California.

She is author or contributor of many books. Most recent publications include: “Il Knowledge Management nelle organizzazioni che apprendono”, in Le@rning, P. Nicola and F. Comunello, 2003; ”La flessibilità dell’orario di lavoro: una risorsa per le organizzazioni e per le persone“, with F. Ballone e A. Fasulo, in F.Butera, Tecnologia e organizzazione per l’uomo e per l’impresa; “Persone e organizzazione nella scuola che cambia”, in F.Butera, ibidem, 2003; “Modelli organizzativi per la scuola dell’autonomia”, Psicologia Scolastica, n° 2 2002; “Una Rete nella scuola”, in F. Butera, Il programma di cambiamento nella scuola italiana, 2002.

## 4 - ICIE S.c.r.l. - Istituto Cooperativo per l’InnovazionE, Italy

www.icie.it.

ICIE, the Co-operative Institute for Innovation, promotes and co-ordinates initiatives and activities in the fields of research, experimentation and technological transfer with regard to the building, energy and environment sectors.

The structure of ICIE takes account two fundamental factors: the business context in which it operates, and the need to develop close collaboration with research and development of other systems. Such a structure is based on a central organisation of strategic areas of interest (construction, industry, services) and is interwoven with the following fields: environment, energy, recycling, maintenance, quality, new technologies, new products and services.

ICIE relies on an expert and qualified structure, which is able to propose, plan, organise and administer complex programmes. It is composed of engineers, architects, experts in the communication field, economists, industry experts and an administrative staff.

The work that ICIE carries out can be summarised in the following points:

- consulting and technical assistance in complex projects for SMEs and municipalities,

- research projects and management of innovative programmes,

- consulting to firms regarding their entrepreneurial organisation and quality,

- multimedia services and editorial support for the marketing of SMEs.

- ICIE develops applied research activities aiming at promoting a closer relationship among the technological, scientific and production entrepreneurial sectors.

- What follows is a summary of some projects carried out by ICIE:

- DE 3207 FACILE – Support tools for housing design and management with telematics systems and services. The project aims at developing and realising two prototypes of Pre-Discharge Home unit in two hospitals in Italy and Sweden provided with information and communication devices. ICIE is the project co-ordinator of the FACILE Consortium

- DE 4102 NJORD-TIDE– Methods for User sensitive Evaluations of Domotic Environments. The project aims to realise a Guide to promote the use of evaluation methods of domotic solutions (telematics applications in the housing) including the point of view of the elderly and disabled people.

- LIFE 98 ENV/IT/000033 VAMP – An Internet-based support to manage C&D waste flows produced and consumed by individuals and organisation. ICIE is the project co-ordinator of the VAMP Consortium

- 0374/A2/M ADAPT Bis Programme - Promotion and development of an integrating system for access by SME to calls for tender in Europe. The project created a structured set of activities which will assist SMEs to access European markets through bidding in international tenders.

- IST 25125 – SOSS- The project is aimed at developing a methodology and an INTERNET-based ICT platform to support constitution, operation and dynamic adaptation of a new organisation for supply of small services at home, in particular provided for people.

Since 1991, ICIE has been part of a network of organisms called OPET (Organisations for the Promotion of Energy Technologies), selected in the THERMIE Programme by DGXVII and the INNOVATION Programme by DG XIII. In these fields ICIE carried out many significant initiatives:

- Promotion, realisation and management of conventions, thematic workshops and publications on subjects such as energy saving and financial instrument to create energy projects.

- Experimentation and monitoring of the procedure of Third Part Financing on a limited sample of real houses (hospitals and small and medium-sized firms).

- Studies for the formation of contract models for the Third Part Financing and a related strategy of dissemination.

CV’s of Key Personnel

Pietro Andreotti. Civil Engineer, chief of ICIE, expert in the technological transfer from RTD sector to the SMEs. He has a large experience in the industrial sector for what concerns new products, services and processes through the use of innovative technologies and new organisational methods. He is an active member of Legacoop, a big association of co-operatives in Italy grouping all industrial and service sectors. He has also competence for what concerns the certification procedures for the quality systems of the industrial companies particularly in the building sector.

Teresa Gallelli. She is an economist and got a Master of Contracts in Public Works at the University of Bologna. She operates in teams involved in designing and management of R&D projects and in the development of business ideas. She was involved in European projects, above all in R&D projects that aims to integrate ICT tools for new services, such as FACILE – Support Tools for housing and management integrated with telematic systems and services - and NJORD – Methods for user sensitive evaluations of domotic environment - in the 4th FP in the Telematics Application Programme. In the 5th FP she collaborated at designing and developing the project SOSS – Smart Organisation for Small Service- in the IST programme.

Mariella MELCHIORRI. She is project manager of European Projects: within DGXVII-THERMIE-Programme she operated as ICIE-OPET manager in Italy and as responsible for a project developed in the framework of the SAVE Programme; within DGXIII-Tide Programme she is co-ordinator of the FACILE Project.

## 5 – EBS - EBS Executive Training Centre, Estonia

http://etc.ebs.ee

The Estonian Business School (EBS) is the largest and oldest private business university in the Baltic States with over 4400 students of Estonian, Latvian, Lithuanian, Russian and Finnish origin, as well as over 1400 alumni. EBS provides programs in business and public administration, IT Management at undergraduate, graduate and doctorate levels.

The EBS Executive Training Centre, a leading training company in Estonia, belongs to the EBS Group and acts as a link between the business world and the Estonian Business School.

The vision of EBS Executive Training Centre is to become an efficient meeting place for the companies from East and West oriented to the growth and collaboration/networking. We create the development environment for executives to share the knowledge, skills and experiences.

International Cooperation

EBS Executive Training Centre is and has been a successful and good partner for international projects as we have effective project based team for international projects and we have large basis for experts for training and research being linked to the Estonian Business School. We have successfully written and managed a GST project Management training for local authorities; Management and strategy for life-long learning – financed by Flanders Foreign Ministry; a FEU project Preparing Estonian Civil servants for Working in EU policy-making Process, a 5th Framework project: EW ISME - Development of the innovative entrepreneurship potential of SME-s as knowledge-sharing trans-national technology transfer partners. IPS-2001-42012 – November 2002- June 2004 (EBS ETC is the coordinator).

Project where our expert is involved:

eForum

The purpose of the international non-governmental associaton e-Forum is to benefit for the European public services, that are targeted to both to citizens and businesses, to become trustable, up-to-date, accurate and cost-effective, on time and within budget. The e-Forum Association is open to both public and private sector members.

The objectives of the e-Forum are: to benefit for the adaption of the public service information infrastructure to the new challenges; developing a specific eGovernment model, as opposed to transplanting the private sector model; to generate synergies between European states, including EU Member States and EU candidate countries, in order to enrich eGovernment across Europe; and to determine selected priority areas that will be given high visibility, that will be measurable and will reinforce European cohesion and strengthen Europe´s ability to progress in the digital age.

Baltic Palette Information Society - eGovernance Network

The purpose of the network is to achieve the aims of interpreting and using the Information Society Indicators as a basis for regional development planning, both at regional, inter-regional and national levels. Another aim is to establish on-going, routine co-operation among web-masters and other technical staff to ensure that data will be regularly updated and easily shared among the BP partners and other actors with an interest in spatial planning in the Central Baltic Sea Region (a.k.a. Baltic Palette Region). This is planned to achieve by defining, collecting and publishing statistical indicators and other types of strategic information, and promoting the mainstreaming of the collection, analyzing and usage of regional Information Society Indicators. Scientific and Technological objectives for producing and disseminating new knowledge in the context of KNOWLEDGE ECONOMY European Development. The project capitalizes on rapid development of e-state, electronic banking and m-business in Estonia during recent years that creates platform for developing new advanced knowledge-based services for SME-s. The main scientific objective is to develop the concept of the SME-driven adaptable knowledge space that enables user-friendly integration of information services by e-state, domestic private service providers and internationally generated information that supports entrepreneurs in monitoring new entrepreneurship opportunities and empowers them as ambient participants of the knowledge economy development process in the European Union. Technological objectives focus on integrating new types of electronic information, related knowledge management tools and training technologies in the format that is easily accessible by SME-s.

Research at the Estonian Business School is closely linked to consulting and development projects that are conducted in co-operation with the business community, Estonian municipal and state authorities. EBS competencies for conducting the present project are based on several earlier research and development projects.

Research surveys conducted by the Estonian Business School staff in all major industry sectors of Estonia (agriculture was not included) indicated problems related to privatisation, company restructuring, introducing new products, technologies and other change management processes (Alas, 2001).

Research surveys on training and development needs of companies in the field of international business (Elenurm, 2001).

Studying the role of the knowledge transfer and learning in the process of economic transition (Elenurm, 2001).

Experience of developing executive tailor-made development programmes for companies and public offices introducing new technologies. Using WebCT-based distance learning environment in the process of preparing international student teams for learning community activities, international information monitoring and knowledge-sharing and introducing web-based learning technologies for organizational learning programmes.

Our contribution to Mental Change:

Mapping possibilities of eGovernment services for SMEs in all participating countries to find out basis for creating best combinations, solutions, develop recommendation for developing eGovernment services for SMEs, this would include workshops/focus group analysis of SMEs and eGovernment representatives. Developing and delivering training for two target groups about how to be able, improve efficiency etc to participate in the knowledge networks – state/local; SMEs to improve their understanding of each other’s knowledge needs and knowledge management in private-public co-operation networks; developing skills for using eGovernment services, for creating and using knowledge bases that are focused on SME needs, for data mining, business intelligence and knowledge sharing in the entrepreneurial context, for developing international learning communities of SME-s, for overcoming cross-cultural and East-West barriers to knowledge-sharing. Investigating the problems that raise about participating in such knowledge networks. Involving companies from Estonia that could help connect e-services with m-services in eGovernment. Dissemination of e-education and setting up SME's university networks.

CV’s of Key Personnel

Tiit Elenurm. He is head of the Entrepreneurship Department, and professor of entrepreneurship at EBS.  Tiit Elenurm obtained a PhD in economics in 1980 from the Plekhanov Institute of National Economy. The topic of his dissertation was managing organisational change processes and introducing new organisational structures. Tiit Elenurm has long-dated experience of managing and conducting training and consulting activities and participating in international comparative research and management development projects. He has in co-operation with foreign trainers and consultants representing expertise of EU countries accumulated versatile experience on transferring new management concepts to Estonia, has been engaged in a PHARE-ACE project studying privatisation in Baltic states and in a PHARE project for conducting survey of export-related training needs in Estonia. He has also participated as a local expert in EU-sponsored projects dealing with public communication development and related training programmes, reform and management of change projects in the field of medical services. Tiit Elenurm has participated in the team for assessing efficiency of UNDP projects in Estonia and coordinated development programme for export managers sponsored by the Nordic Council of Ministers. He has been visiting researcher at the London School of Economics. He is visiting professor of the Helsinki School

Arno Almann, EBS Chair of Law and Public Administration, professor. He has bachelor in law from Tartu State University from 1974 and MSc from. Academy of Social Sciences, Moscow (1989). His Doctor of Philosophy is in Social Sciences, Technical University,  Tallinn, 1999 .  He has been Director of Studies in the Estonian Institute of Public Administration, Acting Head of Chair of Law and Public Administration. Arno Almann has been and is actively involved in processes of Estonian laws and advising Estonian ministers in public administration and law issues.

Arno Almann has complied most of public sector trainings at EBS Executive Training Centre, and is a highly evaluated trainer by the participants.

Jaanus Tärnov, expert in public sectors, local administration, e-Government, innovation. He has a bachelor in engineering from Tallinn Technical University. He has been the lecturer of regional development and planning at EBS and Tallinn Technical University. He has worked for the Association of Estonian Cities as a manager of international relations for 5 years being involved in many projects as an project manager and expert. He is involved as an expert in eForum project in EU Framework 5 that is doing research and sharing knowledge about e-government in many European countries.

Külle Tärnov, the project manager. She is the director of international projects at EBS Executive Training Centre. She is managing international projects, and cooperation with international partners for EBS Executive Training Centre.

She has managed and is managing different international projects at EBS, e.g. Life-long learning and education management project with Lessius Hogeschool, The Baltic Business School project with Pan-European Institute, Vilnius University, and SSE in Riga, The Phare Multi-Country Program for Distance Education, Creating a European Forum for European Studies, EW ISME FP 5 innovation and SME project, etc.

She was the director of studies at EBS 1998-2001. She has got bachelor degree in philology from Tartu University, and has MBA from EBS.

## 6 – ULP - Céreq Alsace, Université Louis Pasteur, Strasbourg I, France

http://cournot2.u-strasbg.fr/index.eng.html http://cournot2.u-strasbg.fr/users/betacereq/

Founded in 1972 within the University Louis Pasteur of Strasbourg, BETA is a research laboratory associated to the French National Centre for Scientific Research (CNRS) since 1985. It is one of the major French academic team in economics (micro, macro and industrial organisation), management, innovation studies, science policy evaluation, technology foresight, VET and labour economics. It includes, on the average, 45 researchers and 55 PhD students and post-doctoral researchers. Many methodological methods are used: micro and macro-economic analysis, history of economic thought, modelling methods and field work.

BETA has a considerable experience in European research programmes. In the past decades, it performed the evaluation of the national and international space programmes (i.e. spinnoffs study of the European space policy for ESA, as well as some national policies in the field). For the European Community, BETA has, then, participated in the FAST-MUST programme and evaluated BRITE-EURAM. Recently, it has been working on several research and networking programmes: among others, Advanced Science and Technology Policy Planning (ASTPP), Strategies and Policies for Systemic Innovation and Convergence in Europe (CONVERGE), Technology and Infrastructures Policy in the Knowledge Based Economy (TIPIK), Socrates “LifeQual Project - Effective Process for Acquisition of Qualification for Lifelong Learning”, “FAME – Vocational Identity, Flexibility and Mobility in the European Labour Market” and “EURONE&T: Towards the European Society – Challenges for Education and Training Policies and Research arising from the European Integration and Enlargement”.

One of BETA’s teams, specialised in the study of relations between education, VET, skills, employment and social inclusion, is the Céreq Alsace. This team which includes 14 members from various disciplines (educational sciences, economics, sociology, philosophy, etc.) belongs to the French network of research centres associated to Céreq: The French Centre for Research on Employment and Qualifications. Besides these academic and scientific activities, BETA/Céreq Alsace has to fulfil a regional mission of assistance to the social partners and State administration in the field of training and employment.

CV’s of Key Personnel

Jean-Alain HERAUD (Prof. Dr.) is Director of BETA-Céreq, the regional associated centre to the “Centre d’Etudes et de Recherches sur les Qualifications” in Alsace (at the University Louis Pasteur of Strasbourg). He has been Director of BETA (joint research unit of ULP and CNRS)  from 1991 to 2000.

Since 1996 he directed BETA’s participation to several European research programmes or thematic networks: Advanced Science and Technology Policy Planning (ASTPP), Strategies and Policies of Systemic Innovation and Convergence in Europe (CONVERGE), Vocational Identity, Flexibility and Mobility in the European Labour Market (FAME), Towards the European Society – Challenges for Education and Training Policies and Research arising from the European Integration and Enlargement (EURONE&T) and Policies for Research and Innovation in the Move towards the European Research Area (PRIME).

On mission for various public institutions, he was in charge of several evaluation tasks and scientific contacts: foresight and planning projects in the area of science, technology and education (in particular the co-ordination of U3M procedure for Alsace in 1998-99); evaluation of the implementation of the South African innovation policy (2002); presentation of the European policy and the new French organisation of higher education and research (Toyo university, Tokyo, 2003); participation to several scientific or audit committees  (Institut Français de l'Energie, Institut Fraunhofer ISI à Karlsruhe, etc.).

His research areas are basically:

Economics of learning, technology and organisational change;

Regional economic and social development;

Evaluation of public research and innovation policies;

Evaluation and foresight techniques.

M'Hamed DIF (Dr.) is an Associate Senior Researcher in “Life Long Learning, VET & HRD” at BETA/Céreq Alsace (University Louis Pasteur of Strasbourg) working on various multidisciplinary (regional, national and European) research programmes. He is a member of “VET-NET” Board and reviewer at the ECER (European Conference on Educational Research) of EERA (European Educational Research Association, Scotland). He chaired VET-NET Programme for ECER 2001 Conference in France (Lille, 5-8 September 2001). He took in charge BETA’s recent scientific contribution to the following European research projects: “Effective Process for Acquisition of Qualification for Lifelong Learning” (LIFEQUAL: 1998-1999), “Vocational Identity, Flexibility and Mobility in the European labour market” (FAME: 2000-2003) and “Towards the European Society – Challenges for Education and Training Policies and Research arising from the European Integration and Enlargement” (EURONE&T: 2001-2004).

He participated and contributed to several  international  and European conferences, workshops and forums related to his expertise and research projects, namely:

European conference on « Lifelong Learning–Inside and Outside Schools » at the University of Bremen (25–27 February 1999).

European Workshop on continuing education : « Ability to meet future challenges through continuing education in Europe », 16–18 May 1999, Mainz, Germany.

JVET (Journal of Vocational Education and Training) Fourth International Conference, University of Wolverhampton, 16-18 July 2001, UK

European Conference on Educational Research (ECER), organised by « the European Educational Research Association (EERA) » : Finland (Lahti, 22–25 Sept. 1999), Scotland (Edinburgh 20–23 Sept. 2000), France (Lille, 5–8 Sept. 2001), Portugal (Lisbon, 11-14 Sept. 2002), Germany (Hamburg, 17-20 Sept. 2003).

He also worked outside France and Europe for 12 years as a Senior Lecturer & Researcher, Project Manager and Consultant.

His present research areas are basically:

Innovation, work identities,  organisational learning and change in  knowledge-driven society;

Lifelong learning, professional development and inclusion in active citizenship;

Flexibility, mobility, competence audit and accreditation of experiential learning;

Regional socio-economic development.

## 7 – TERRA - TERRA HUMANA Clean Technology Engineering Ltd., Hungary

http://www.terrenum.netl

Terra Humana Ltd. has been established in 1989 as Swedish - Hungarian joint venture company, whereas the Swedish part has been represented by the Swedish environmental scientist Edward Someus, while the Hungarian part was Central Europe’s largest machine manufacturer. The business activity of the company is to manufacturing of environmental equipment parts and components, and development and demonstration of innovative biomass recycling and carbonization technologies for manufacturing of activated carbon and Clean Coal. The Terra Humana is a united industrial and business organization for professional management of products & services for industry & agriculture on the rapidly developing E.U. & U.S. markets. The prime focuses on the Terra Humana business are:

Technical development and engineering of the patented innovative Thermal Desorption (US patent 5,707,592) waste management (Waste-to-Clean Energy, Clean Multi Fuel technology, soil treatment and hazardous waste management,) and Low Temperature Carbonization Technologies (Activated Carbon manufacturing from agro refuse and hard coal and).

Eco Agricultural Programs: design and engineering of biomass utilization systems and environmental friendly low input farming agricultural production systems. Development of agricultural by product based bio-impregnated activated carbon and recycling – reuse of agricultural by products.

Management of European Union & Central-East European Integrated Business Programs for renewable energy, environmental and agricultural projects. Participation in and/or promotion of industrial and agricultural projects and business programs with technical assistance, with special concern to the renewable energies, such as biomass.

CV’s of Key Personnel

Edward Someus is a senior Swedish environmental engineer, graduated at the University of Lund in Sweden in 1978. Soméus – combining high level of scientifically knowledge with industrial engineering and field applications, - specializing in the research, technical development, engineering and industrial applications of the 3R recycling, reduction and reuse of waste materials. The special focus is on the applications of Low Temperature Carbonization Technology for recycling of carboniferous materials and Thermal Desorption Technology for soil decontamination and revitalization. Speclizing in the technical development and engineering of the pyrolysis rotary kiln technique, post burners, venturi off-gas scrubbers, heat exhangers and auxiliary installation. Someus is participating in several international environmental projects, such as NATO and EUFP5 environmental projects. He is Coordinator and key technology engineer of EU FP5 NNE5/363/2001 Multi Fuels project (http://www.terrenum.net/cleancoal).

Recent major scientific and technology program worked out as follows:

Waste-to-Clean Energy by Thermal Desorption: Energy Globe 2000: March 8, 2000, Linz, Austria.

Intergrated Economical and Environmental Efficiency of the Thermal Desorption Technology: Federation of Technical and Scientific Societies of Hungary: April 14, 1999, MTESZ.

Environment and Sustainable Development: Creation of New Industrial Employment by Global Market Distribution of Advanced Waste Recycling and Treatment Technologies: Environment-orientated Sustainable Industrial Development in Central Europe During the European Union Integration Process: HUDEFO Expert Meeting and Workshop as a Preparatory Forum of Specific Project Development, January 21, 1999 Budapest, Hungary

Sensor - Batalas ISO 14000 1997, no.: 97/11/916. ISO 14001 environmental auditing the Hungarian Railway Real Estate Service, CEQUA 1999.

Hazardous Substance Management: ADPA, American Defence Preparedness Association, Environmental Restoration Opportunities Conference, Munich, Germany, October 25-27, 1994.

Thermal Desorption Technology and Integrated Bioremediation Application for Cost Efficient Treatment of Obsolete Pesticides Arising from Production, Storage and Use: 6th Int. HCH & Pesticides Forum, 13-15 March, 2001 in Poznan, Poland

Thermal Desorption Technology: Low Temperature Carbonisation of the Biomass for Manufacturing of Activated Carbon: 5th International Conference on Progress in Thermochemical Biomass Conversation, held in Tyrol Austria, 17-22 September 2000.

## 8 - Plato Cork, Ireland

www.plato.ie

PLATO-Cork is widely regarded as the most efficient and cost-effective support network for owner-managed SMEs in Ireland. An interesting aspect is that this SME development work is supported by over 100 large firms, who provide co-facilitators, and by a range of academic and other industry support institutions. PLATO Cork will support 12 small SMEs over the two years of the Building IC Awareness Initiative to test-bed Intellectual Capital and knowledge-production-function thinking and management. From this process, we hope that a blueprint will emerge that can then be used to introduce such IC thinking in other small firms both in Ireland and in Europe.

CV’s of Key Personnel

JJ O’Connell, Plato-Cork director, has built up very strong relationships with over 400 SMEs via the PLATO two-year SME development programme and has strong links within PLATO Europe and with similar initiatives in the United States.

## 9 - ICRI - The Intellectual Capital Research Institute of Ireland Limited, Ireland

http://www.intellectualcapitalireland.com/

ICRI operates on the principles of collaborative networking and communicative action and has strong links with leading Irish universities and with the international Intellectual Capital community. The broader Irish network exhibits a strong communitarian partnership between leading researchers, industry support networks and SMEs. In Partnership with Plato Cork on small owner-managed firms, and leveraging the expertise of our Irish academic network, we hope to both contribute to new knowledge creation in this area with our European colleagues, and to raise awareness of the economic and social importance of intangible values in both Irish and European SMEs.

CV’s of Key Personnel

David O’Donnell. ICRI director. Following over 20 years of international HRD practice, he entered research in the mid 1990s. He has been actively involved in research on intellectual capital in the Irish ICT sector since 1998 and has published in the Journal of Intellectual Capital, the Journal of Information Technology, MIT eCommerce Research Forum, and others, with both academic and practitioner colleagues. He has recently completed research reports, in collaboration with colleagues, on knowledge dynamics for both the Chartered Institute of Personnel and Development (CIPD) and the Chartered Institute of Management Accountants (CIMA). Recent research involvement includes the following:

- Intellectual Capital in Northern Ireland [2004]; ICRI, UU & IICR

- CIPD Project on e-Learning in Ireland [2003]

- CIMA Project on Intellectual Capital, e-Business and Organisational Dynamics in Irish ICT sector through lens of CFO. [2001 to date]

- Managerial Values; Ireland, Canada, Australia [2000 to date]

- Radical Organisational Change in Europe due to developments in ICT, Aalborg University, Denmark [2000 to date]

## 10 - SSI - Public Institution Strategic Self-Management Institute, Lithuania

www.eksponente.lt/ssi

Scientific consultation enterprise of Sociologist S.Paulauskas was created in February 13, 1991 as private enterprise. Registry Nr. IP91-682. Owner – Assoc. Prof. Dr. Stasys Paulauskas. Enterprise cod 4019915. VAT cod 4019915.

This enterprise was reregistered in Ministry of Education and Science of Lithuania with Nr. 104 mi as non-profit Public institution Strategic Self-Management institute in December 3, 2002. Registration address: Sausio 15 g. 11a-27. LT-5800 Klaipėda.

Together with Scientific innovation company “Eksponente” organising international scientific conferences “Energy decentralisation: Future of urban energy” (1999, 2002).

The international scientific journal “Strategic Self-Management” ((ISSN 1648-5815) is preparing now to start.

The main scientific profile of SSI related to Social sciences (S000) and Management (6G) according to official classification. During period from 1991 year SSI made more than 100 scientific works, related to own subject. The list of scientific publications consists of more than 70 books and articles.

CV’s of Key Personnel

Stasys Paulauskas. Director of Self Management Institute. Associated professor, Nostrified as doctor of social sciences. He carried out Post-graduate studios in Lithuanian Academy of sciences, Institute of philosophy, sociology and law, specialty - applied sociology. Membership of with the following professional bodies: Member of Lithuanian fishing council; President of Lithuanian wind energy association; Chef editor of international scientific journal “Strategic Self-Management”.

Kęstutis Biekša. Master Degree in Environmental Engineering and Sustainable Infrastructure (Major studies: sustainable infrastructure). Member of Lithuanian-Swedish society, member of Lithuanian wind energy association. Project manager of Strategic Self Management Institute. He has organizational skills of preparation of wind energy projects in Western Lithuania. Have knowledge of preparation of business plans and energy audits. Have good awareness with NGO sector and good experience with management of different projects. Management of civil engineering projects, including drawings and calculations. Management of building projects for small case waste water treatment facilities for dwelling houses.

## 11 – SUC - Stavanger University College (Norway)

www.his.no/

Stavanger University College/ Høgskolen i Stavanger was established on August 1, 1994 through a merger of seven formerly independent colleges. With more than 6000 students and over 700 members off staff the university college is one of the largest in the country with programmes and activities covering a wide range of study programmes.

Stavanger College consists from January 2004 of 3 faculties which offers a wide range of study programmes.  These are made up from the present 7 schools and 2 research centres.

- School of Health and Social Work Education

- School of Humanities

- School of Art Education

- School of Teachers´ Education

- School of Hotel Management Studies

- School of Science and Technology

- School of Economics, Cultural and Social Studies· Centre for Behavioural Research

- Centre for Reading Research

Most of these are located on the college campus at Ullandhaug about four kilometres from downtown.

The college has a special responsibility in Network Norway (a network comprising all Norwegian colleges and universities) for education in the fields of hotel management, tourism management, engineering education in petroleum technology and special education. 
Stavanger University College offers a wide range of study programmes from music performance to mathematics. Some of the study programmes are well suited for advanced training or as a basis for further studies, whereas other programmes provide training for particular professions. In academic fields where we have an especially high level of expertise we offer education up to both master and doctoral level.

Stavanger University College have in this structure  a “Centre for reading skills” with national financing and recognition. They make reading skills test for children all over Norway.

We have a department of media science that educates television producers for most of the  television companies in  Norway.  Our employees have  had a  major  report  or similar program  shown at national television every year the last years. Last week they had sent a program of 1,5 hour  documenting mismanagement  of  clients at social institutions.

10 different departments spread all over the institution have running e-learning programs of various types for both normal  distant students and for grownups in  various employment situations. Some of these are in close collaboration with RKK, Rogaland education and training centre, which specialize in  distant learning and videoconference based education for teachers and vocational training. The  e-learning programs have in many cases involved research projects with both regional , national and international funding.

CV’s of Key Personnel

Jan Frick. He Dr. is employed as Associate Professor and department manager at Department for Business Administration, Stavanger University College.

He holds a Master in Science in Operation Management and ICT from the Norwegian Institute of Technology in Trondheim, Norway, 1980, and a PhD in development of industrial collaboration network from Aalborg University, Aalborg, Denmark, 1992. Jan Frick has previous worked in various industrial projects at the research institutes SINTEF and Rogaland Research Institute and at the industrial collaboration institutions Jærtek at Bryne, and TESA at Sandnes. Before 1980 he worked at the companies “Statens Vegvesen Vest-Agder” Kristiansand, “Høivold Mekaniske Verksted” Kristiansand, “Tegle Mekaniske Verksted” Bryne, and “Flolo Electric Company” Franklin Park (US).

He has managed the Nordic PhD course “Managing International Research and Development Projects” 1998-2002, and the Norwegian research project on technology enhanced learning “NettLaeR” 1999-2002. He is since 1992 manager for the Norwegian part of the international research network "International Manufacturing Strategy Survey". Jan Frick is member of the IFIP workgroup 5.7 “Integration in Production Management” and the European network CI-net.

He has published at several international conferences, journals and book chapters. He is in Technical Program Committee for the conferences IRMA03 Philadelphia (US), Euroma/Poms03 Como (I), IFIP-wg5.7 Human Aspect in Production Management 03 Karlsruhe (De), BIS04 Poznan (Pl), and IRMA04 New Orleans (US). He was in 2003 the main author of the “NextLeap” Network of Excellence application for the IST program of 6FP where 32 European Organizations in 20 countries took part. He participates in the European programs Leonardo, InterReg3b, and R3L in collaboration with Rogaland Training and Education Centre, RKK. He is chairman of the board of the company “Sirdal Grunneierlag AS”, and member of the advisory council and board of “Centre for Maintenance and Asset Management”. He is also chairman of “Stavanger Macintosh User Group” which he established in 1985, and co-editor of the local community paper “Nordvesten” in Madla, Stavanger.

## 12 – RKK – Rogaland Training and Education Centre, Norway

RKK was established in 1989, and is a foundation set up by the County of Rogaland in conjunction with the regional branches of the Confederation of Norwegian Business and Industry (NHO) and the Norwegian Federation of Trade Unions (LO). Rogaland Training & Education Centre comprises the 32 upper secondary schools in the County of Rogaland.

Each school is itself a resource centre for further and continuing education focusing on the need for lifelong learning. Over 10.000 people of all ages took up the courses offered by RKK in 2002 and nearly 1500 teachers were involved. Over the last 10 years, RKK has had more than 30.000 course participants and has become the largest training and education institution in Rogaland.

The courses and education offered represent a variety of subjects from upper secondary school and university college level in addition to development of a number of tailor-made courses for the public and private sectors. Agriculture, aquaculture, health and social care, ICT for teachers, offshore related courses in oil well drilling technology and safety/ rescue operations are examples on various areas we already have well-established offers.

Common to all these offers, is the fact that they are all more or less available as net supported courses, and delivered across municipality, county, and national borders. Today RKK exports courses to other counties in Norway as well as Angola, Equatorial Guinea, Greece, Spain, the Baltic States and has also started to focus on the Russian petroleum industry. RKK emphasizes the teacher’s role in the blended learning-model and technical ease-of-use when it comes to choosing appropriate IC technology, and has therefore gained substantial experience in evaluating LMS’s and use of online video conferencing.

Experiences in regional development and some project partners

RKK has evolved to become an important actor in the area of regional development and learning regions. An increasing part of our activities is aimed at establishing long term relationships internationally, and contribute to strengthen and spread RKKs competence through interaction and cooperation with other regions in Europe. This is why we seek to be an active participant in regional development projects, such as e.g:

- ICT for SMEs within the Interreg III B North Sea programme, focusing on the ICT availability and usage for SMEs with partners from Germany, Denmark, Sweden, the Netherlands, Belgium and Scotland.

- Redmeis, part of the Leonardo programme focusing on regional development and the relation between vocational training institutions and local industry with partners from Spain, Greece and Latvia.

- R3L Learning Regions a Regional life Long Learning project with partners from Germany, France, Greece and Ireland.

- Etrainer in the Baltics, an Interreg III A project in cooperation with partners form Finland and the Baltic States.

- Train-the-Trainer in Angola with Ipedex and Intsok, an oil related programme between Angola, Norway and France.

- PETS, a Socrates project related to learning through sports

- TENT, Technology Supported Network Training for Adult Educators within the Socrates programme.

- Practical ICT for Teachers – a 60 credit study (1 year full study) developed together with Stavanger Univeristy College as continuing education for professional teachers at various school levels.

- 6-credit ICT-course for public information staff in various municipalities in Rogaland.

As an important basis for our regional and international work, we have developed close relations with regional business development associations such as the Stavanger Region Chamber of Commerce, Dalanerådet and Ryfylke IKS with whom we cooperate closely on several projects. We also have a good relation with the academic and scientific communities at Stavanger University College and Rogaland Reseach (RF).

Ryfylke IKS, represented by the municipalities Strand, Finnøy, Forsand, Suldal and Hjelmeland, is a regional development council. It is situated north east from Stavanger in Norway, in the middle of Rogaland County. The final part for installation broadband connections for the whole region is nearly finished. Ryfylke is a special area with lots of islands and we see the development of ICT for companies as a way of make live easier for those companies. They keep in touch with the region also trough their website: www.ryfylke.no. Among different regional projects Ryfylke IKS is also represented in an international project the Interreg III B “ICT for SMEs” for the North sea region.

Dalanerådet is a regional development council; the board is represented by all municipalities in this region, being Bjerkreim, Egersund, Sokndal and Lund.

The municipalities are situated in the south-east of Rogaland County.

Concerning eLearning they have established broadband in the whole region, under leadership of Dalanerådet.  They host a regional website, www.dalane.no, as a common information management tool. Use of ICT in education, within enterprises is one of the focus issues in their strategic business plan.

RKK is also a member of Innovasjon Rogaland, a top leader forum for exchange of experience and innovation in Rogaland, Deep Community SubSea, Fagforum for mat og drikke (Professional forum for Food and Drink), Finnova, Sauda Vekst and Haugaland Chamber of Commerce. All these partners are important co-actors to RKK in further development of the Rogaland area as a county-wide network.

CV’s of Key Personnel

Ole Imsland. He is the Managing Director of RKK, and has been so since 1993. He has a background from construction in the offshore industry, and was head of the training management department at the Aker Kvaerner Rosenberg facilities in Stavanger, before asked to take over the RKK.

Since then, RKK has expanded its activities both regionally and internationally, and has doubled the turn-over tenfold (Current turnover approx 50 mil NOK 2002). Ole Imsland has given speeches about innovation and competence on several occasions, last time in October 2003 in Moscow, after an invitation from the Norwegian Oil Directorate and Intsok, and in september this year on the South African Minister of Energy’s visit in Stavanger.

He represents RKK in several committees and boards, including top leader foras such as Innovation Rogaland, Finnova, Sauda Vekst, the Stavanger Region Chamber of Commerce and various oil related foras.

Leif Knudsen. He  has a permanent position on the administrative staff of Rogaland Training & Education Centre (RKK). He takes part in RKK projects as project developer and technical administrator in budget and planning,, the development of presentation material for projects, including web presentations of  RKK’s general activities and international projects. These tasks also include descriptions of RKK’s competence and areas of activity in connection with project applications, initiation and implementation.

Suzanne M. C. de Kok Selstad. Maastricht Hotel Management in The Netherlands and A 4-year bachelor education within the hotel and tourism sector. She attended different courses in service management, business plans, export. She has started at RKK in May 2003.  I am the project coordinator (administrative and budget responsibilities) for several projects, among them:

Norway Skills & Thrills, Norway applies for the 40th World Skills Competition in 2009.

ICT for SMEs, an Interreg IIIB program within the Nordsea region.

E-teachers for the Baltic region, an Interreg IIIA project Cedefop

## 13 - PWR - Politechnika Wroclawska, Wroclaw Center for Technology Transfer (WCTT), Technical University of Wroclaw, Poland

Wroclaw Center for Technology Transfer (WCTT) is a semi-independent department of Wroclaw University of Technology (University of 20.000 students), Poland. WCTT was created in March 1996 as a result of the TEMPUS Project S-JEP 07017 entitled ”Bridging the gap between University and Industry”. It employs 12 people. The director of the WCTT is prof. Jan Koch. He is a member of the Polish State Committee of Scientific Research, Polish representative to the 6th Framework Programme in the Nanotechnologies Programme Committee.

The mission of WCTT is to increase the productivity and competitiveness of Polish manufacturing industry. Joining the university know-how with industrial experience is the main advantage of WCTT activities and places it in the regional society. WCTT has developed the multidisciplinary approach towards new bottom-up initiatives, the institution liaise on the regional level with groups of steakholders: Local Government, researchers, Regional Development Agencies, SMEs, representatives of local industry, NGO’s, Trade Unions, Chambers of Commerce, Employers organizations and regional social dialogue tripartite institutions. WCTT initiates and facilitates regional projects through signposting and co-ordination with other regional/national service providers and actions including Commission-supported networks (IRC, NCP/RCPs, EIC and Eureka) and national- KSU (System of services for SMEs).

Projects on the national and regional level:

Creation of Centre of Advanced Technology in Wroclaw’s Park of Technology

Creation of enterprises incubator in Wrocław’s Park of Technology

Human recourses development training

Structural funds ERDF, ESF

In Cooperation with the Polish Agency for Enterprise Development WCTT has been creating - National Innovation System. The Ministry of Science and Informatisation is supporting the implementation of Regional Innovation Strategy for Lower Silesia

Main Activities:

Training

WCTT organizes regular training courses that have various forms. They range from one-day seminars to one semester post-graduate studies. They have been organized either “indoors” or “outdoors” by request of the company. Since WCTT was founded, more than 7000 people have taken part in them. The training program covers a wide range of topics connected with the enterprise such as: Quality management; Lean Manufacturing; Production planning and control; Technical preparation of the production; CAD/CAM; Controlling; Environmental management systems (for example the ISO 9000, ISO 14000 standards).

Consultancy

WCTT offers organizational and technical consulting. Consultants elaborate analyses and suggest new solutions. They raise awareness in the field of innovation and help with its implementation. WCTT prepares assists and monitors the implementation of new technologies and organizational methods in enterprises.

WCTT helps with finding industrial partners in Poland and abroad thanks to the participation in regional, national and trans-national innovative networks.

In the frame of info days and workshops WCTT offers support for SMEs in using PHARE funding as well as national programmes geared to SME development; export, innovations, quality management.

Programme of Research and Technological Development

The Wroclaw Centre for Technology Transfer acts as a Regional Contact Point for the 6th Framework Programme of Research and Technological Development of the European Union.

It provides information about the possibilities for Polish enterprises, research and scientific units and other organizations to participate in Research and Technology Development Programmes of the European Union, gives advice on how to prepare proposals and verifies them, facilitates finding foreign partners in order to submit a proposal to  the Framework Programme, it helps with the preparation of the Polish co-operation offers for foreign partners for co-operation in the European funded programmes.

Transnational Technology Transfer

WCTT is a member of the Innovation Relay Centre network as IRC West Poland -

offers access to foreign co-operation offers in the field of research and new technologies,

actively searches for foreign partners to assist in trans-national technology acquisition/sale and technological co-operation provides information about conferences, technology fair and brokerage events in Europe.

WCTT publishes:

- Bulletin called HIGH-TECH, 3000 copies, 4 issues per year, includes the information about new technologies, R&D European Union’s projects for SME, training courses organised by WCTT and information about the 6 th Framework Programme

- conference proceedings,

- leaflets, each year about 20, 3000 copies each.

Since 1999 Wroclaw Centre for Technology Transfer has been appointed as a  Regional Contact Point for the 5th and 6th Framework Programmes of the EU

Participation in other European Programmes

Since 1995 WCTT has participated in the following national and international projects regarding companies (including SMEs) and researchers:

PHARE SCI-TECH I : "Project of creation and development of the Innovation Relay Centre".

INCO-COPERNICUS 20644 : "Creation and development of The Innovation Relay Centre FEMIRC in Poland".

PHARE STEP I PL9511-02-02-52: "Development of training and consulting services for Small and Medium Enterprises in Poland ".

PHARE STEP I PL9511-02-02-69 : "Collecting offers for partners (SMEs) matching".

PHARE FIESTA II PL.9316/01.01/III-04 - Box Management "Organising an Association of Organisations that train managers of the manufacturing industry”

PHARE FIESTA II PL.9316/01.01/I-19  Box Management "Management for engineers – post graduate studies for upper level managers”

Wrocław Technology Park

Financing innovation projects - INCOME programme of Polish Science Foundation

Fabrykat 2000 financed by the US AID.

CV’s of Key Personnel

Jan Koch. He is a member of the Polish State Committee of Scientific Research, Polish representative to the 6th Framework Programme in the Nanotechnologies Programme Committee.

## 14 – BYWEB - Byweb 2 Formação e Informática Unipessoal Lda, Portugal

www.byweb.pt

BYWEB is a profit company born in 1999 and located in the north of Portugal – Santa Maria da Feira, its main goal is the development and implementation of innovative projects and activities concerned with information technologies, both in economic sector and social community. Since the foundation BYWEB is focused on research, networking projects and training. The company also offer among others web-based solutions, multimedia, and graphic design services. From our own experience we are happy to work with most types of organisations whether they are existing educational agents, schools, universities, governmental organisations, district councils, regional authorities or other companies. BYWEB works with high parameters of quality, deserving the trust and recognition of our customers, partners and several governmental ministries. The success and reputation of the company is mainly due to its highly professional and motivated, staff. The company and all our teachers are certified by national authorities.

Achievement and Projects

1999: Creation and development of the TiO (Seniors on Line) – an innovative and unique (in Portugal, till now) project that connects older people to new technologies. The Project had the high sponsorship of our first lady and the National Committee for the elderly, among other prizes: www.projectotio.net

2000: Organisation of an national seminar on Internet and multimedia: www.byweb.pt/desafios

2000: Drawing an intergenerational experience – Net@vo - that was supported been selected by the Innovation Institute of the national Education Ministry. The Projects provide the opportunity to several older persons become “the teachers” for one day, each, at a secondary Scholl. www.projectotio.net/netavo

2001. Participating in a Regional Project, involving 6 regions at North of Portugal – Dvnet – It aims to research and document the use of the internet and multimedia by the local companies. The project all so will produce a Portal for this group: www.dvnet.org

2002: We are the leading partner of an European project, approved under the EQUAL initiative: Developing Creative Intergerational Relations - www.viver.org. This project aims to prove that intergerational solidarity it’s a very useful tool in work family balance. The project involves 6 others European projects and more than 30 institutions. End of the project: March 2004. This Project has been recently (May 2003) chosen by the European Commission to take part on a Group, that aims to produce a New Model on Equal Opportunities at European level.

2002-2004: Under the Leonardo da Vince Mobility Programme, we are providing trainee to students from Lithuania, Spain, web design teachers from Sweden, etc. Under this same programme we are partners on the following pilot projects:

VISION 2000: IL GENERE NELLA CERTIFICAZIONE DI QUALITA - promoted by Progetto Donna - Italy

ENVEARTHONARY  - promoted by the  Universitatea Al.I.Cuza - Romania

SMEs COUNSELLING: development of a “front-line” advice - guidance - counselling scheme for SMEs’ employees – promoted by Institutul de Ştiinţe ale Educaţiei - Romania

2003: Organisation of the “European Week for the Conciliation of work, family and social life”

Since the foundation till now we promote Initial and vocational training, professional guidance and integration to children adult unemployed with a high degree education or disadvantage populations. Main areas of training: ICT, Equal opportunities, entrepreneurship and innovation, HR Management, social care of elder and young children over the perspective of intergenerational solidarity.

Our graphic department also worked to improve and enlarge our portfolio, by now with a large number of web sites or Portals and graphic works produced.

CV’s of Key Personnel

Maria Teresa Almeida Pinto. Experience in Project Design, organization and Management since 1996.

Research/papers written and published: 3 full articles, 23 abstracts and  several articles of opinion.

Member of the European Thematic Group “Equal Opportunities”, Facilitator of the Equal Portuguese Network on “work family balance”

Susana Cristina  da Silva Santos. Doctorate in Enterprise Administratrion – University of Santiago de Compostala – Spain. Master in Business Administration – IESF  - Instituto de Estudos Superiores Financeiros e Fiscais – V. N. Gaia. Post-graduation in Marketing and Business Management – IESF – Instituto  de Estudos Superiores Financeiros e Fiscais – V. N. Gaia. Graduated in Marketing – ISCET – Instituto Superior de Ciências Empresariais e do Turismo – Porto

## 15 - IST Instituto Superiore Tecnico, Potugal

www.ist.utl.pt

The IST (Technical Superior Institute) is one of the biggest Portuguese universities in the domain of engineering and technology. Teaching activities, which are lectured by a highly qualified academic staff of around 1000 lecturers, include 19 graduated programmes with the duration of 5 years. There are 23 master degrees and 19 doctorates according to the IST expertise. At the moment there are 10000 students of which 8300 are graduates and 1700 post-graduated. What distinguishes the School and ensures the quality of its teaching are the research and development activities it carries out. IST dynamism in this area can be seen in the number of publications, and its level of participation in conferences and seminars and the involvement in research projects both national and international. In parallel with its contributions in Education and R&D, IST aims to strengthen its links with society in the area of Engineering, Science and Technology. IST has been the driving force behind a series of institutions, which seek to act as interface between the universities and industry.

The main graduating specialisation of IST are: Architecture, Aerospace Engineering, Applied Mathematics and Computer Science, Biological Engineering, Biomedical Engineering, Chemical Engineering, Chemistry, Civil Engineering, Electrical Engineering and Computer Science, Environmental Engineering, Industrial Engineering, Industrial Engineering and Management, Information Science and Computer Engineering, Materials Engineering, Mechanical Engineering, Mining Engineering and Earth Resources, Naval Architecture and Marine Engineering, Physics Engineering, Territorial Engineering.

IST has good background in European co-operation and projects, as Leonardo da Vinci, Socrates-Grundvig, Erasmus etc. The good experience in postgraduate and continuing education enable IST to promote and share its good practice in VET, new methods and products, carrier guidance and counselling.

CV’s of Key Personnel

Maria Luísa Quintino. Diploma of Mechanical Engineering, Instituto Superior Técnico (IST), 1976-1977; Doctor of Philosophy, Cranfield Institute of Technology, May of 1986; PhD Mechanical Engineering, Instituto Superior Técnico, February of 1987; “Provas de Agregação” (Ability Doctorship), Instituto Superior Técnico, February 2003. Consultant, Advisor to the Board Directors of ISQ - Instituto de Soldadura e Qualidade, since 1984; Member of the Management Board of “Lasindústria”, a laser job-shop, since 1987; Chief Executive of the European Welding Federation, since 1992; Associate Professor, Mechanical Engineering, Instituto Superior Técnico, since 1994. She is experts in Physics of Welding, Welding Technologies and Equipment, Industrial Engineering, Research Projects Management, Vocational Training. She was Manager and / or Team Member in 18 international research projects. She was Project Evaluator for FP5: GROWH, CRAFT, SPRINT, BRITE/EURAM; Member in FP 5 – ECSC. She was also Evaluator for Portuguese projects: PRAXIS XXI, Expert for SMEs projects evaluation; Consultant of the European Commission initiative, EUROMANAGEMENT, 1994.

Rita Moya Santiago Coelho Tilak-Viegas. License in Business Management (5-year university degree), her professional interests were always markedly oriented towards innovation and knowledge management. Indeed, her first position as a University-Industry Liaison Officer (Faculty of Sciences and Technology, Universidade Nova de Lisboa) entailed the preparation of the launching of its S&T Park (MADAN Park), including its socio-economic feasibility study, financing and its negotiation and the marketing of its business incubator.

Interest: in the organisational and managerial aspects of innovation led to the acceptance of a position as Projects' Manager with a research institute of the Universidade de Lisboa, the Institute for Social Sciences. This experience was complemented through direct involvement with Gestão de Projectos e Negócios, an SME interested in developing applications of proprietary DNA technology.

Last year position: at Portugal's national quality certification research institute (Instituto de Soldadura e Qualidade), with the responsibility of operational management of a large and internationally (EC) funded research project targeting the promotion of technological and business integration in the European automobile and aeronautics industries. She is also carrying out her own research as part of this project, namely in what concerns the development of a new methodology to quantify and characterise the social and cultural factors determining the potential for innovations in SMEs. Her terms-of-reference include also a significant volume of international scientific co-operation within and outside Europe, as well as in-service training of junior staff at ISQ and partner organisations.

## 16 - IPA Automation Engineering, ROMANIA

http://www.ipacv.ro

IPA is a SME in Bucarest Romania, with department SC IPA SA CIFATT in Craiova, S-W of Romania. IPA was founded in 1962 and IPA CIFATT was founded in 1980 to develop, manufacture and trade intelligent computer systems, SCADA systems, IT, environment monitoring and industrial applications.

IPA is an industrial R & D company, engineering and integration systems, software developer in automation & IT field. IPA CIFATT is an Excellence Centre in Automation and IT field, Centre for Inovations Incubation, Entrepreneurial Formation, Technologyl Transfer. IPA CIFATT has an extended, rich xperience in the field of environment monitoring, management system, IT, educational and decision making field.

IPA is ISO 9001 certified company, is a regional point for European projects and has accomplished PHARE, FP5, Leonardo, EUREKA, BERD and PHARE TTQM projects. IPA CIFATT is member of the regional Unit for Projects Management.

IPA CIFATT have a regional (S-W of Romania) network with 420 partners (Universities, research units, NGOs, industrial units, SMEs, local - county, - regional administration, etc).

Our regional network have the aim to develop and implement of collaborative information system linking the members of the real-estate branch of industry and integrating with government information systems concerning real estate legislature with the main objective of technological modernization of SMEs from our region "Oltenia", increasing safety, transparency and quality of service, establishing equal standards within the branch, compatible with European standards.

The long objective is for E-Centre, Improving IT integration into the informational system, channel for diverse services responding to the needs of peoples, personalisation tools that are enable to help users access information they need, research - development, ICT integration in learning processes for improved education effectiveness and Europe Competitiveness, tester, integration in Romania and specialy in Oltenia - Romania S-W region, disemination of information.

The specialists which founded IPA CIFATT Craiova keep a permanent link with the Politechnical High School, trough the courses and seminaries organised, Conferences, Projects. A 23 years experience  accomplished by our specialists, not just in research and design, but also in production and  implementation of automation systems is one of the best, and is showed by our results and products.

CV’s of Key Personnel

Gabriel Catalin Vladut. Educational Background: Automation Engineering and Computers Science Faculty, graduated in: engineering of territorial distributed system, IT, Environmental Monitoring System

Professinal Background: Manager in Center for excellance and tehnological transfer in automation

Co_ordinated engineering projects: 1 BERD Project; 2 PHARE TTQM Projects; 1 PHARE Project; 1 EUREKA Project; 24 Romania projects

Member of: SOCER -  Romanian Energical Consumption Optimization Company; SIEAR - Romanian Controlling Engineering Company; IFAC - International Federation of Automatic Control – MMM 29 TC; 30 TC; IRC Regional Point for EU FP6 Projects.

Journals, Conferences and congresses : 59 articles and papers in Romania, Finland, Japan, Spain.

Diplomas: Honor Diploma Local Conseil of Craiova town ;

Diploma and Gold Medai "Genius" in Olimpiada Genius 2000 Budapest;

Diploma of Excelence in R&D 2000 Guvernul Romaniei, ANSTI;

“1000 World Leaders of Scientific Influence”-American Biographical Institute 2001;

Cojocaru Camelia Valentina. Educational Background: University of Craiova, Electrotechnic Faculty Graduated in Electrotetechnic

Professional Background: scientific researcher, degree III in IPA – CIFATT Craiova, Quality Assurance.

Responsible, Projects coordinator,

Member of SIAER (Electric and  Automation Installations Society) Skill to communication, english, PC and Internet.

Participated in many Nationals and internationals projects: Phare, Phare TTQM, ADR, FP5.

Co-ordinated projects focus on consulting for SME in FP5/FP6 projects in IRC Regional Partner Point and Consulting for SME aiming to introduce the ISO 9001 Quality assurance; Conferences and congresses

## 17 - UDJC - Universitatea Dunarea de Jos din Galati, ROMANIA

www.ugal.ro

Dunarea de Jos University of Galati is 54-year old higher education institution with 13 Faculties, 9 Colleges, 36 Departments, 97 specializations and 45 post-graduate specializations in different fields: polytechnic, sciences, letters, food industry, economics, law, tourism, sports etc. University has also special Departments: Center for Continuing Formation, Open and Distance Learning Department, Department for European Studies, Educational Advising Center, Inter-medium Science Shop Center. Thus, the activity covers both the initial vocational training and the lifelong learning.

The University developed an important number of European projects, like Tempus (24 projects since 1995), Leonardo, Socrates, 5thFP (INCO-Copernicus), ACE, PECO and join projects. In several cases, Dunarea de Jos University of Galati was the coordinator and/or the contractor. Projects in the field of ODL and Continuing Education development (including e-learning), training in TQM field, institutional development, new didactic activities, research projects in INCO frame (in computer sciences, robotics, electronics, energy saving, underwater technologies etc.), social and economic impact projects (targeting SMEs’ activity, training/retraining, initial vocational and lifelong training, disfavored people training) must be mentioned.

In the fields of Continuing Education and ODL, including ICTs involvement, a coherent series of international projects were developed: *TEMPUS CME-3024-97 (Library Management System), TEMPUS S_JEP-11243-96 (Colleges and Continuing Formation in Five Small and Medium Size Universities of Romania), TEMPUS S_JEP-11449-96 (Teachers training in multimedia technologies), TEMPUS S_JEP-12434-97 (University Departments Network for Enterprises-Universities-Organisations Cooperation), *TEMPUS S JEP 12466/96 (ODL Development by Underwater Technologies), *TEMPUS S JEP 11043/96 (New Formation for Engineers in TQM), TEMPUS IB JEP 14254/99 -OVIDE (European Level Training for Regional Development), *TEMPUS AS JEP 13468/98 (Continuing Education Centers Restructuring), TEMPUS JEP UM 13377/98-(QUEST: Services and Education Quality Assessment).

Leonardo da Vinci projects: I/01/B/C/PP-120550, Sofianet Odl Learning center European network – SOLE; F/99/2/07020/PL/II.1.2.a, VALEURTECH – Stages en entreprises pour les étudiants de College; E/99/1/061435/PI/III.3.a, The labor excluded qualification to promote their insertion through the new fields of employment: the potentialities of the school environment – Lleurescola – Dissemination; RO/00/B/F/PP-141037, Centre professionel pour formation continue en productique moderne – PRODUCTIQUE INNOVATRICE; I/99/2/013083/PI/II.1.1.b, ENTRAIN – Entrepreneurial Training Pathway; Right Person in the Right Job - Train the trainers in the field of career guidance – RIPERIJO, A/02/B/F/PP/124.208, New Using Methods of Information and Communication Technologies for Vocal Guidance and Training, 89056/EX.

Participation in 5FP: CIPACT 94/ 0109, “Robotic dimensional testing for manufacturing processes”, 1997, Copernicus, Dunarea de Jos University of Galati, Romania-coordinator & contractor; 2 projects (1988-2000) in Biotechnologies (Food and Fishery), coordinator-DJUG; Faculty of Electrical Engineering just finished a 3-year research project in Energy Saving.

Special notice for SIBIS -"Statistical Indicators for Benchmarking the Information Society", IST-2000-26276, coordinated by Empirica (Gesellschaft für Kommunikations und Technologieforschung mbH), Germany, which just finished (30 Sept. 2003) to assess the e-Society (IS) in 15 MS + 10 NAS + Switherland and USA, providing the biggest up-to-date data base available in this moment (see www.sibis-eu.org).

Other projects in ODL and e-learning: "Internet Educational System- Virtual Libraries- e-Book" INFOSOC - World Bank C1/142, Virtual Laboratory for Academic Applied Training INFOSOC-73 /02.09.2002, Communication Interfaces, 250/1999 & 228/1998.

Fields of interest relevant for MENTALCHANGE: Computer-Based Training; Artificial Intelligence; Remote / Distance Education and Training, Lifelong Learning; Adult Education, Permanent Education; Educational Multimedia; Company Re-Engineering; Entrepreneurship and New Technology Based Business.

Fields of Expertise relevant for MENTALCHANGE: Experience on development of European research networks, research infrastructure, virtual research institutes, and in the following fields: multimedia techniques and tools, interactive publishing, digital content; data acquisition and management; technologies and engineering for software, systems and services; efficient and intelligent industrial production; up-to-date methods on continuing education and training, lifelong learning, Open and Distance Learning (ODL), remote learning, remote tutorial; new educational multimedia products and techniques; ICTs techniques and tools for ODL and lifelong learning; European partnership on regional ODL development; Training/assistance for innovative enterprises; knowledge and expertise transfer for SMEs creation/management; regional development and human resources; on-the-job training in SMEs; entrepreneurship and new technology based business; RTD activities to validate and disseminate instruments and approaches to innovative enterprise creation and development.

Technical support for ODL platforms: Technical platforms provider for South-East Europe and Middle East belonging to the ARIADNE “community”. Internet/Intranet traffic for DJUG (MAN topology) is assured by optical fibbers network by the RoEdu Net, (which assures to the national university network a total of 120Mb/s), in lines of 8Mb/s IPv4 traffic + backup on 2Mb/s IPv4 traffic. RoEdu Net is connected through the GEANT and RDS providers to the European Network at 300Mb/s (100Mb/s assured by Uunet Europa). The TV station of CSIDD (ODL Department) of DJUG offers the necessary facilities for video conferencing using Internet/Intranet (Intranet-Romania video conferencing is possible - WAN type networking etc., as too). Several multimedia laboratories are in charge with the appropriate learning material production. An authorised Publishing House is facilitating and completing the development of e-learning activities.

Dunarea de Jos University of Galati is the biggest university in the southeast of Romania (more than 16 500 students) and is situated in an important geographic region (2SE-Romania, incl. 6 counties). Every year, more than 300 academics are involved in abroad activities (international research, academic projects, conferences, individual grants etc.).

CV’s of Key Personnel

Danut IORDACHESCU.

Academic qualifications: 1990-1995, Dunarea de Jos University of Galati, Romania, Technical Sciences, Welding Equipment and Technique, Doctor Engineer in Technical Sciences (PhD)

1983-1984,  Dunarea de Jos University of Galati, Romania, Mechanical Engineering, Modern Welding Technologies, post-graduate specialisation (MS)

1977-1982,  Dunarea de Jos University of Galati, Romania, Mechanical Engineering Faculty, Welding Equipment and Technique, Diploma of Engineer

Positions:

2003  – presently: Visiting Professor at Instituto Superior Tecnico, Lisbon, Portugal:

CP(RO) /09/C/2002/PO for research, STM-IST;

2003 - presently: Expert-evaluator of the European Commission for:

FP 6 expert no. EX2002B0019111;

INTAS expert ID. 4521

1982 – presently: Dunarea de Jos University of Galati, 47 Domneasca, 800008, Galati, Romania; presently: Professor; Ph.D. coordinator; international projects coordinator / manager.

Main specialisation field: Industrial Engineering

Other specialisation fields: Vocational Training, Open and Distance Learning; Multimedia Teaching Tools and Methods; Human Resources Development;

Research projects: Manager and / or Team Member in 13 national research projects

European Projects: Manager and / or Team Member in 11 international research/training projects (FP5, TEMPUS, Leonardo da Vinci, PHARE).

## 18 – ADC – ASOCIATIA pentru DEZVOLTAREA CREATIVITATII, ROMANIA

ACD –acts on the creative processes, as well as on the creativity incorporated in the product.

- ACD –members have got a rich experience and work in the following fields:

- Arts – by organizing exhibitions and exhibiting their works;

- Information Technology – especially data bases;

- Technical Sciences- by carrying out inventions and publishing numerous scientific works;

- EU –programmers – by participating with proposals of projects in FP5 (Fifth Framework Programme), such as:

- Improving human potential; No : SERD – 2000 – 00254 (The inferential method by analogy in spirit of time used to the enrichment of the socio-economic knowledge base).

- Innovation & SME (IPS- 200) ; No: IPS-2000-038 (Technology Transfer Growth by Developing

- Business within Product Re-Manufacturing Area);

- Innovative Products, Processes and Sustainable Growth; No: GTC1-2001-43003 (Growth – Innovative Products, Proceses and Organisations );

- Innovative Products, Processes and Sustainable Growth; No: GRD1-2001-40796 (Highly Flexible

- Assembly System – Configuration and Operational. (HIFAS);

- Innovative Products, Processes and Sustainable Growth; No:GRD1-2001-40436 ( Internet-enabled

- Total Automation of Enterprise. (ITAME);

ACD –acts on the creative processes, as well as on the creativity incorporated in the product and, we pursue:

- to facilitate business growth in the field of creativity;

- to involve individuals, groups and organisations in creative activities over Europe;

- to offer support to originators of creative ideas;

- to contribute to the development of techniques and methods required for artificially enhancing creativity.

Through its members, the ACD collaborates with AGIR (the General Association of the Engineers in Romania), Association of the Plastic Artists in Brasov, Association of Small and Medium Industries in Brasov, OSM (the Organization of Medicine Students in Cluj-Napoca) and IFAC (International Federation of Automatic Control).

CV’s of Key Personnel

VasileEnache. He has 22 years of experience in teaching and applied engineering, has led a lot of students’ in robotics and innovation in production systems. He specialises in the field of industrial Robotics and has achieved seven innovation and six inventions. He has the co-authored books on, “Flexible manufacturing” course. Vol I 1996 and “Manufacturing Systems”, Vol I 2001, (University of Brasov). Presently leading a research & design team working on environmental problems, creativity, eco-design, remanufacturing and development of products. The Ph. D. thesis treats about “Fuzzy logic used in researches of assembling flexible systems”.

## 19. BIC Group s. r. o., SLOVAKIA

www.bicba.sk/bicgroup

Established in 1993 is a consulting company specialising primarily in practical assistance. Along with the role of co-ordinator within the BIC Group Holding it also provides its own entrepreneurial activities. It offers complex consultancy for small and medium-sized businesses in:

- company analysis

- action plans design and implementation

- restructuring and revitalising projects

- introduction of new products and technologies

- procurement of funding and company matching.

BIC Group is closely co-operating also with private businesses, government, UNIDO and European Commission.

Besides these activities BIC Group, Ltd. takes part in various projects:

- as a partner organisation of the Innovation Relay Centre Slovakia, which was established in 1997 by the European Union as FEMIRC Slovakia and from July 2000 full member of the Innovation Relay Centres Network

- as a co-ordinator of the project Creation and implementation of Industrial Liaison Office clusters in Slovakia. The aim was to create a network of effective Industrial Liaison Offices in Slovak universities, scientific, technical and research institutions. The project was financed by UNIDO and British Council.

- as a partner in several Leonardo da Vinci Programme, e.g. the SMARTER (Student Monitoring And Remote Tutoring-Enlarging Regions) project, through. This project supports continual education and lifelong development and education for technicians in the field of computers and related activities in the multiplicative partnership, which involves SMEs , educational institutions, European organisations and a group of firms from 6 countries (Bulgary, Cyprus, France, Germany, Slovak Republic, Great Britain).

- As a partner in the project - PARTNER: Thematic Network - The PARTNER Thematic Network is a spin-out of the wider Innovating Regions in Europe (IRE) Network. The activities organised for PARTNER members will follow the project cycle of the current Regional Innovation Strategy (RIS-NAC) projects in Newly Associated Countries (NACs) and will evolve around issues of particular relevance to the NACs.

CV’s of Key Personnel

Olga CEKANOVA, she is BIC GROUP Ltd. junior consultant. Her Key qualifications (relevant to the programme) are as follows.

- preparation of the mirror project INTERREG III/Phare-CBC cross–border Operational Programme Slovak Republic/Austria (SR 0113.04),

- preparation of project under the FP6-2003-ACC-SSA-Energy,

- REGILOn East East team leader funded by the Open Society Foundation,

- skills with the project proposal and procedures within the Phare CBC Joint small projects fund and the International Visegrad fund

- project management,

- regional development.

Jan GREGA, she is BIC Group s.r.o. - financial manager. Her Key qualifications (relevant to the programme) are as follows:

- Company analysis and diagnosis, Company restructuring - spin-off method,

- Project management, Business planning, Financial analyses, Due diligence,

- Regional development,

- Property development,

- Risk financing.

## 20 - CSV - Amnim d.o.o. / Center za Znanstveno Vizualizacijo, SLOVENIA

www.bioanim.com

The Center for Scientific Visualization (CSV), Ljubljana produces scientific and educational software projects containing animations in virtual reality about the structure and function of the cell, tissue, human body and other topics from the field of biology or medicine. The company has a single employed person – Tomaz Amon (myself). I started with my own company five years ago because I have been convinced that modern educational software has great future. I have been always interested for both biology and computer science. I finished the study of biology and made my Ph.D. in electrophysiology. At the same time I was engaged in computer programming and I programmed in the computer language C the Neuro Event Manager (1986-1996) – a computer program for the analysis of the electrophysiological data which has 1MB source code and more than 200 batch commands. It is still used in the laboratory of Prof. Valentincic, Ljubljana, and constantly updated. So it was possible and very attractive for me to enter the field of visualization of biological structures and functions in 1996. I produced several projects, the most important being the software package “Cell-Tissue-Human Body” which the Ministry of Education of Slovenia recognized as an official educational tool in slovene schools. Its english version can be seen on my site www.bioanim.com It has been selected for inclusion in the Awesome Library, a collection of the top 5% of sites in the field of K-12 education and nominated for the Stockholm challenge award. I am able to produce a complete biological educational software package from the text and »classical« illustrations (which can also be published in form of a book) to the dynamic HTML and virtual reality web3D site.

CSV produces scientific or educational software enhancing the understanding of topics difficult to learn from the textbooks only. As we are running our projects in schools and on the web we see that in fact we are acting in a new branch of educational science. There is obviously a need for teams of researchers, educators and managers to be established and develop this new branch of education. Therefore we see our future to join the projects, which produce educational software and so help to form also the expert teams on this field

CV’s of Key Personnel

Dr. Toma Amon, SME Manager and Researcher

Position:	Director of the centre for the scientific visualization Amnim d.o.o.

Awards: 1979 Award of the Research Council of Slovenia for good students.

1980 Preleren award of the university of Ljubljana.

Appointments:

Grant DAAD 1983-1984 in Max-Planck-Institut für Verhaltensphysiologie Seewiesen, Abt. Huber,

Grant of the Max-Planck fondation 1984-1985 in Max-Planck-Institut für Verhaltensphysiologie Seewiesen, Abt. Huber.

Tempus grant 1993 in Freie Universitaet Berlin. I was investigating the Kenyon cells in the mushroom bodies of the bee Apis melifera with the whole-cell-patch-clamp methods to find out their role in the memory processes of the bee.

Researcher on the institute of biology 1986-1996.

1996-97 Multimedial software package “Electrical phenomena in the living cell” supported by Ministry of Education of Slovenia and acknowledged as an official educational tool in slovene schools.

1997 I have become the director of the centre for the scientific visualization Amnim d.o.o. I have kept this position up now.

1998 Sense organs – educational software package. Supported by Ministry of Education of Slovenia and acknowledged as an official educational tool in slovene schools

1999 Systems of Organs I. and Cell-Tissue-Human Body. Both Educational software packages were supported by Ministry of Education of Slovenia and acknowledged as an official educational tool in slovene schools.

2000 The software package “Cell-Tissue-Human Body” www.bioanim.com has been :

- selected for in- clusion in the Awesome Library, a collection of the top 5% of sites in the field of K-12 education.

- nominated for the the Stockholm Challenge Award

Main Research Topics:

1978-1996 Electrophysiological investigations of the central nervous system of the heteropteran, hymenopteran and orthopteran insects.

1986-1996 Design and programming of the Neuro Event Manager – a computer program for the analysis of the electrophysiological data.

1996-2001 Design and programming of the computer visualizations of the biological structures and functions

1999 – Participation in the IST project “Web-based Standard Educational Tools(WebSET, IST-1999-10632)”. The goal of the WebSET project is to develop and use advanced Web-based technologies to implement innovative cost-effective learning tools that can be run on any workstation platform including a standard PC of average capacity and ensure the adoption of WebSET surgical applications with major European learning centres e.g. Royal College of Surgeons of England and the Royal Belgian College of Surgeons.

2002 – partner in the EU Socrates-Minerva project CP 1-2002-1-EE-Minerva-M:LearningFolders (LeFo) - open source online educational publishing and support for primary schools.

2003 Tomaz Amon becomes a member in the research group LMSE - Laboratory of Microsensor Structures and Electronics, Faculty of Electrical Engineering, University of Ljubljana.

## 21. IJS - Institut "Jožef Stefan", Ljubljana, SLOVENIA

www.e5.ijs.si

Institut "Jožef Stefan" is a research organisation for pure and applied research in the natural sciences and technology. Both are closely interconnected in research departments composed of different task teams. Emphasis in basic research is given to the growth if young scientists, while applied research and development serve for the transfer of advanced knowledge, contributing to the development of the national economy and society in general. At present the Institute, totalling about 800, has a research staff nearly 550: about 250 of them are postgraduates temporarily employed while obtaining their degrees, almost 200 have doctorates and 100 have permanent professorships or temporary teaching assignments at the Universities. In view of its activities and status, IJS plays a role of a kind of national institute, complementing the role of universities and bridging the gap between science and applications.

Main activity of the Laboratory for open systems and networks, where the work in the project will be performed, is research and development in the following areas: e-learning technologies and approaches, security in computer networks, broad band technologies, and multimedia communication and services, communication and transfer of knowledge  in SMEs.

The Laboratory has rich experience in participating in EU funded projects like VALUE (III Framework Programme - the project PASSWORD/dealing with security technology for networking), EUREKA (COSINE - EUREKA 8), and IV. and V. Framework Programme projects:

UNIVERSAL (UNIVERSAL Exchange for Pan-European Higher Education, V. FP), where an open brokerage platform for exchange of learning resources between European institutions of higher education is being developed.

ELENA – Building Smart Space for Learning,  V FP, IST

Prolearn, Professional learning, Network of Excellence on e-learning, 6 FP, IST

Daidalos,  Integrated Project, Designing Advanced Interfaces for Delivery and Administration of Location Independent Optimised personal Services, 6 FP, IST

HYPERGEO (Easy and friendly access to geographic information for mobile users - on going, V. FP), where technical tools to enable value-added information services related to geographic information have been provided;

FAIN (Future IP Active Networks - on going, V. FP), where an open, flexible, programmable and dependable (reliable, secure, and manageable) network architecture based on novel active node concepts is being developed;

NICE (National Host Experiments with Global linkage, ACTS), where we provided ATM international connectivity for Slovenia, multimedia distributed events, services of the National Host for ACTS projects;

MAITS (Multilingual Application Interface for Telematic Services - Language Engineering in Telematics), where in co-operation with university of Salford an API has been developed which is currently used by Expert Translation ltd. for on-line translation on the WEB;

ICE-TEL (Interworking Public Key Certification Infrastructure for Europe - IV. FP, Telematics for Research), where services of the first public key certification authority in Slovenia have been developed and provided;

ICE-CAR (Interworking Public Key Certification Infrastructure for Commerce, Administration and Research - IV. FP, Telematics for Research), where security services for the Internet community in Slovenia have been provided:

EPRI-COM (ACTS), where video-on demand service for Slovenian Parliament were provided;

EXPERT (ACTS), where distributed events and trials have been performed over broadband networks.

The laboratory has good collaboration with governmental, industry, and service organisations, like ISPs, in Slovenia. The Laboratory and prof.dr.B.Jerman-Blažič are members of the EducaNext (www.EcucaNext.org)  consortium that is running the first European portal for brokerage and exchange of learning resources.

SETCCE is a joint not-for-profit research organisation set up by Telekom Slovenia, University of Ljubljana, Jožef Stefan Institute, and two companies from the telecommunication sector. The number of employees is 8.  It is set up under the law of Republic of Slovenia for promotion of the technological development. The basic research areas of SETCCE are security in information society technology and related applications for SMEs. The current research and development within SETCCE is focused on user applications for qualified electronic XML signatures, long-term archival of electronically signed documents, PKI-based services, security services for brokerage and delivery platforms in e-commerce applications, and secure end-user services in premium IP networks. SETCCE is involved in a national project eSlog, coordinated by Slovenian Chamber of Commerce, where it is responsible for preparation of rules and guidelines for storage of electronic documents in Slovenian commercial organisations. SETCCE is also maintaining the EuroPKI top-level certification authority for Slovenia (SI-CA). Researchers from  SETCCE were involved in a number of EU  projects, e.g. CADENUS, NASTEC, DAIDALOS.  NASTEC project (Building trust and confidence in New Associate States throug use of security technologies)  coordinated by SETCCE is typical  transfer of technology project with emphasis on education, training and awareness rising in the New Associated countries. Similar project that dealt with SMEs and introduction of open source code in their environment and production was the project INES. Most of the work is run as educational and training activities. SETCCE team has participated in the following projects from V and VI FP, IST:

CADENUS – Configuration and Provision of End-User Services in Premium IP Networks, where SETCCE team  the required security feature in the management mediator system developed for on-line end user provision services with guaranteed  QoS

NASTEC – Building trust  and confidence in NAS through usage of security technologies –the team is coordinating the project. The main issue is  transferring security technology, solutions and  knowledge and know-how  to NAS – Romania and Poland,

INES – Industrial Embedded Systems – our team is working as a competence centre providing take up of open systems software and tools in industrial environment

DAIDALOS  an IP from VI FO where the team is responsible for building privacy and identity management in pervasive networks.

CV’s of Key Personnel

Prof. dr. Borka Jerman Blažič. He is head of the Laboratory for open systems and networks at Jozef Stefan Institute, Ljubljana, Slovenia with more than 15 years of experiences in networking. She is also teaching postgraduate and undergraduate courses on Telecommunication Services, E-commerce and Security in information systems at the Faculty for Economics, University of Ljubljana where she is employed as part time staff. She was a member of TERENA Technical Committee and convenor of TERENA WG on Internationalisation (1992-1999). She was project team leader of many projects in the field of telematics and participated as a team leader from Slovenia in the following international projects: COSINE (Eureka), PASSWORD (Value), ICE-TEL, ICE-CAR, MAITS (Telematics), NICE, EPRICOM, and EXPERT (ACTS, AC 110, 035, 094), and UNIVERSAL, HYPERGEO, ELENA and FAIN (V. Framework Programme), Prolearn  (NoE) and DAIDALOS (IP) from 6 FP. She was also project manager and general secretary of the first academic network in former Yugoslavia (1989-1991). She is a member of the New York Academy of Science and is chairing the ISOC Chapter of Slovenia. She is chairing the national standardisation committee on information technologies (JTC1) for Slovenia and is representing Slovenia in ISO JTC1 SC2, JTC1 SC22WG20 and CEN TC 304. Her research currently focuses on security in telecommunications, multimedia network services, and advanced computer network technologies. She has a lot of experience in organizing Conferences, Workshops and Seminars. She was co-director of two NATO funded schools in the last few years.  She is also counselling through projects and personal engagement the Slovenian governmental bodies, Slovenian Telecom, CEN and CEC. She is author of more then 200 published scientific papers and books.

Dr. Toma Klobuar. He is team leader of SETCCE research unit. He is holding PhD from the Faculty of Computer Science and Informatics from University of Ljubljana. He has participated in most of the European projects run within SETCCE and has developed solutions required for security provision. He was also chair of several workshops in the are of activity of SETCCE. He has several publications in international journals from the field as well as in several books where he was acting as editor.

- Workpackage number: WP 1 – WP n.

- Number of the contractor leading the work in this workpackage.

- The total number of person-months allocated to each workpackage.

- Relative start date for the work in the specific workpackages, month 0 marking the start of the project, and all other start dates being relative to this start date.

- Relative end date, month 0 marking the start of the project, and all ends dates being relative to this start date.

- Deliverable number: Number for the deliverable(s)/result(s) mentioned in the workpackage: D1 - Dn.

- Deliverable numbers in order of delivery dates: D1 – Dn

- Month in which the deliverables will be available. Month 0 marking the start of the project, and all delivery dates being relative to this start date.

- Please indicate the nature of the deliverable using one of the following codes:

- R = Report

- P = Prototype

- D = Demonstrator

- O = Other

- Please indicate the dissemination level using one of the following codes:

- PU = Public

- PP = Restricted to other programme participants (including the Commission Services).

- RE = Restricted to a group specified by the consortium (including the Commission Services).

- CO = Confidential, only for members of the consortium (including the Commission Services).

- Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

- Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

- Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

- Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

- Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

- Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

- Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

- Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

- Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

Draft Council Resolution on Social and Human Capital  - Building social and human capital in the knowledge society: learning, working, social cohesion and gender (April, 2003)

Research relating to cancer treatment of the gonads can be financed

Applicants should note that the Council and the Commission have agreed that detailed implementing provisions concerning research activities involving the use of human embryos and human embryonic stem cells which may be funded under the 6th Framework Programme shall be established by 31 December 2003. The Commission has stated that, during that period and pending establishment of the detailed implementing provisions, it will not propose to fund such research, with the exception of the study of banked or isolated human embryonic stem cells in culture.